## Task_Export_Table
Texas Nodal Market Implementation Schedule to Meet 1/1/09 Oct5, 2005 version r2
ID | Name | Start | Finish | Duration | Predecessors | Comments
1 | Overall Project | 2005-08-15 08:00 | 2009-04-09 17:00 | 47.7 mons
2 | Milestones | 2006-01-13 08:00 | 2009-01-01 17:00 | 38.75 mons |  | The first milestone is over a year after the project has started. Need to add milestones to keep help assure you are on track. Suggest adding, signed vendor contracts, installation of EDS with communications systems working with most all QSEs and TDSPs, etc. The Transition Plan suggests four tracks as high level paths. Seems like the schedule should also be organized into these tracks. Is that the plan?
3 | Protocol Contested Case Completion | 2006-01-13 08:00 | 2006-01-13 08:00 | 0 days
4 | Telemetry Criteria Met | 2007-07-27 17:00 | 2007-07-27 17:00 | 0 days | 250 | There is more than just Telemetry Criteria that must be done. Verification of each SCADA point must be made by the TDSP, QSE and ERCOT once an EDS system is delivered by the vendor
5 | Outage Scheduler Ready | 2007-09-07 17:00 | 2007-09-07 17:00 | 0 days | 262 | This is only one of a whole list of functions that must individually be checked out. Why just the Outage Scheduler?
6 | Network Model Available for MP Testing | 2008-01-11 17:00 | 2008-01-11 17:00 | 0 days | 253 | Too late in project
7 | Network Security Applications (NSA) Test Complete | 2008-04-24 17:00 | 2008-04-24 17:00 | 0 days | 310 | These milestones do not seem to line up with the milestones suggested by the Transition Plan Outline. Too late in project
8 | SE 6-Months Stability Test Criteria Met | 2008-06-27 17:00 | 2008-06-27 17:00 | 0 days | 258
9 | CRR Auction Trial Completion | 2008-09-26 17:00 | 2008-09-26 17:00 | 0 days | 321
10 | SASM Market Test Completion | 2008-10-02 17:00 | 2008-10-02 17:00 | 0 mons | 335
11 | SCED 6-Months Posting of LMPs Criteria Met | 2008-10-09 17:00 | 2008-10-09 17:00 | 0 days | 315
12 | 168-Hour Real-time Market Test Completion | 2008-11-13 17:00 | 2008-11-13 17:00 | 0 days | 341
13 | Real-time Market Operation Ready | 2008-11-13 17:00 | 2008-11-13 17:00 | 0 days | 53,341
14 | RUC Test Completion | 2008-12-02 17:00 | 2008-12-02 17:00 | 0 days | 332
15 | DAM Test Completion | 2008-12-09 17:00 | 2008-12-09 17:00 | 0 days | 327
16 | TNT Go-Live | 2009-01-01 17:00 | 2009-01-01 17:00 | 0 days | 348
17 | MP Tasks | 2006-07-03 08:00 | 2008-10-03 17:00 | 29.5 mons
18 | MP's Systems Ready for TNT Scripted Market Trial | 2008-04-25 08:00 | 2008-04-25 08:00 | 0 days | 314SS-2 mons
19 | MP's Systems are Daylight Saving Time Ready | 2008-06-20 08:00 | 2008-06-20 08:00 | 0 mons
20 | MPs to Define Field Test (Market Trials) Requirements | 2006-07-03 08:00 | 2006-09-08 17:00 | 2.5 mons | 3
21 | QSE/CRR Account Holder Agreements Signed | 2008-01-07 08:00 | 2008-10-03 17:00 | 9.75 mons
22 | Project Mobilization and Planning | 2005-10-10 08:00 | 2008-05-30 17:00 | 34.5 mons
23 | Project Mobilization | 2005-10-10 08:00 | 2005-12-09 17:00 | 2.25 mons
24 | Approve Start | 2005-10-10 08:00 | 2005-10-14 17:00 | 1 wk
25 | Assign Core Project Team | 2005-10-17 08:00 | 2005-10-21 17:00 | 1 wk | 24
26 | Develop Procurement Approach and Requirements | 2005-10-17 08:00 | 2005-12-09 17:00 | 2 mons | 24
27 | Develop Plans | 2005-10-17 08:00 | 2008-05-30 17:00 | 34.25 mons
28 | Develop Project Plan | 2005-10-17 08:00 | 2005-11-11 17:00 | 1 mon | 24
29 | Define Architecture Approach and Requirements | 2005-10-17 08:00 | 2005-12-09 17:00 | 2 mons | 24
30 | Define the Systems and Facilities Requirements | 2005-12-12 08:00 | 2006-02-03 17:00 | 2 mons | 29
31 | Define ERCOT Integration Test Plan | 2005-12-12 08:00 | 2006-02-03 17:00 | 2 mons | 29
32 | Define Simulation Testing Environment | 2006-02-06 08:00 | 2006-03-31 17:00 | 2 mons | 31
33 | Develop Detail Test Plan with MPs | 2006-09-11 08:00 | 2006-12-01 17:00 | 3 mons | 31,20
34 | ERCOT to Implement TCR to CRR Transition | 2008-01-07 08:00 | 2008-05-30 17:00 | 5.25 mons
35 | Training | 2005-08-15 08:00 | 2008-06-19 17:00 | 37.2 mons
36 | MPs Training | 2006-01-13 08:00 | 2008-04-25 08:00 | 29.75 mons
37 | Develop and Conduct "How the nodal market will work" | 2006-01-13 08:00 | 2006-04-06 17:00 | 3 mons | 3
38 | Develop and Conduct "MPs and ERCOT staff roles" | 2006-02-24 08:00 | 2006-08-10 17:00 | 6 mons | 116
39 | Other Nodal Training Classes for MPs | 2007-05-25 08:00 | 2007-11-08 17:00 | 6 mons | 313SS-12 mons
40 | Assessment of MP Personnel Readiness | 2008-04-25 08:00 | 2008-04-25 08:00 | 0 mons | 39,18
41 | ERCOT Training | 2005-08-15 08:00 | 2008-06-19 17:00 | 37.2 mons
42 | Operator Training Simulator (OTS) | 2005-08-15 08:00 | 2008-02-22 17:00 | 33 mons |  | Why past start date? Should this be tracked as part of nodal installation?
43 | Startup and Vendor Selection Process (OTS) | 2005-08-15 08:00 | 2005-10-07 17:00 | 2 mons
44 | Update OTS Requirements for TNT | 2005-08-15 08:00 | 2005-12-02 17:00 | 4 mons | 43FF
45 | SOW/Vendor Selection (OTS) | 2005-11-07 08:00 | 2005-12-30 17:00 | 2 mons | 44FS-1 mon
46 | Initiation (OTS) | 2006-01-02 08:00 | 2006-01-13 17:00 | 0.5 mons | 45
47 | Development OTS | 2006-01-16 08:00 | 2007-06-01 17:00 | 18 mons | 46
48 | Product Testing/Vendor Site Testing (OTS) | 2007-06-04 08:00 | 2007-08-24 17:00 | 3 mons | 47
49 | Vendor ship/stage/startup/verify/update with patches (OTS) | 2007-08-27 08:00 | 2007-09-21 17:00 | 1 mon | 48
50 | Release /Field Testing (e.g., I-test and UAT) (OTS) | 2007-09-24 08:00 | 2008-02-22 17:00 | 5.5 mons | 49
51 | ERCOT Operator Training | 2007-09-24 08:00 | 2008-03-07 17:00 | 6 mons | 50SS
52 | Other ERCOT Staff Training | 2007-05-25 08:00 | 2008-04-24 17:00 | 12 mons | 313SS-12 mons
53 | Assessment of ERCOT Personnel Readiness | 2008-06-19 17:00 | 2008-06-19 17:00 | 0 mons | 52,51,311
54 | Develop/Buildout Facilities | 2006-02-06 08:00 | 2007-01-05 17:00 | 12 mons
55 | Define Facility Specification | 2006-02-06 08:00 | 2006-03-31 17:00 | 2 mons | 30
56 | Budget Approval/ Select Vendor/Award Contract | 2006-04-03 08:00 | 2006-06-23 17:00 | 3 mons | 55
57 | Complete Facilities | 2006-06-26 08:00 | 2007-01-05 17:00 | 7 mons | 56 | Does not seem to consider the need to house the EDS early in project
58 | Subsystem Requirements/SOW/Development/Test | 2005-10-17 08:00 | 2007-12-06 17:00 | 27.95 mons
59 | System Operations | 2005-10-24 08:00 | 2007-06-29 17:00 | 22 mons
60 | Network Model | 2005-10-24 08:00 | 2007-06-01 17:00 | 21 mons | 25
61 | Requirements finalized (Network Model) | 2005-10-24 08:00 | 2005-12-16 17:00 | 2 mons
62 | MP Review (Network Model) | 2005-12-19 08:00 | 2006-01-06 17:00 | 3 wks | 61
63 | Develop RFP (Network Model) | 2006-01-09 08:00 | 2006-01-27 17:00 | 3 wks | 62
64 | Vendor proposal (Network Model) | 2006-01-30 08:00 | 2006-03-10 17:00 | 6 wks | 63
65 | Select/Evaluate/Negiotate (Network Model) | 2006-03-13 08:00 | 2006-04-21 17:00 | 6 wks | 64
66 | SOW for Network Model | 2006-04-24 08:00 | 2006-05-19 17:00 | 1 mon | 65
67 | Vendor Development | 2006-05-22 08:00 | 2007-06-01 17:00 | 13.5 mons | 66 | Somehow the detail tasks that the Vendor develops to control his schedule delivery need to be able to drive these items where we reference a Vendor's task. Otherwise updating to multiple Vendors schedules to get a meaningful overall schedule becomes very difficult.
68 | Conceptual Design (Network Model) | 2006-05-22 08:00 | 2006-06-16 17:00 | 4 wks
69 | MP Review Conceptual (Network Model) | 2006-06-19 08:00 | 2006-06-30 17:00 | 2 wks | 68
70 | Detail Design (Network Model) | 2006-07-03 08:00 | 2006-09-22 17:00 | 3 mons | 69
71 | MP Detail Design Review (Network Model) | 2006-10-02 08:00 | 2006-10-13 17:00 | 2 wks | 70FS+1 wk
72 | Create DB for Model Testing (Network Model) | 2006-10-16 08:00 | 2007-01-05 17:00 | 3 mons | 71
73 | Develop (Network Model) | 2006-10-16 08:00 | 2007-03-30 17:00 | 6 mons | 71
74 | Vendor Product Test/ Problem Resolution | 2007-04-02 08:00 | 2007-05-04 17:00 | 5 wks | 73
75 | FAT (Network Model) | 2007-05-07 08:00 | 2007-06-01 17:00 | 4 wks | 74
76 | SE/Telemetry Enhancements | 2005-10-24 08:00 | 2006-10-06 17:00 | 12.5 mons | 25 | Do not understand the SE part of this? Is this installation of new telemetry to support SE? Assume ERCOT will totally replace their existing SE and SCADA system with a new one from the winning bidder to reduce ERCOT's risk and project schedule
77 | Define SE and Telemetry Requirements | 2005-10-24 08:00 | 2005-12-16 17:00 | 2 mons
78 | MP Review (SE/Telemetry) | 2005-12-19 08:00 | 2005-12-30 17:00 | 2 wks | 77
79 | Modify SE and Telemetry Systems | 2006-01-02 08:00 | 2006-10-06 17:00 | 10 mons | 78
80 | Outage Scheduling | 2005-12-12 08:00 | 2007-06-29 17:00 | 20.25 mons | 25 | Why is this task separated from all other tasks? If should be part of total vendor package to reduce risk.
81 | Requirements (Outage Scheduler) | 2005-12-12 08:00 | 2006-01-06 17:00 | 1 mon | 29FF+1 mon
82 | MP Review (Outage Scheduler) | 2005-12-26 08:00 | 2006-01-13 17:00 | 3 wks | 81FF+1 wk
83 | Develop RFP (Outage Scheduler) | 2006-01-09 08:00 | 2006-01-27 17:00 | 3 wks | 81
84 | Vendor proposal (Outage Scheduler) | 2006-01-30 08:00 | 2006-03-10 17:00 | 6 wks | 83
85 | Select/Evaluate/Negiotate (Outage Scheduler) | 2006-03-13 08:00 | 2006-04-21 17:00 | 6 wks | 84
86 | SOW (Outage Scheduler) | 2006-04-24 08:00 | 2006-05-19 17:00 | 1 mon | 85
87 | Vendor Development | 2006-05-22 08:00 | 2007-06-29 17:00 | 14.5 mons | 86
88 | Conceptual Design (Outage Scheduler) | 2006-05-22 08:00 | 2006-06-16 17:00 | 4 wks
89 | MP Review Conceptual (Outage Scheduler) | 2006-06-19 08:00 | 2006-06-30 17:00 | 2 wks | 88
90 | Detail Design (Outage Scheduler) | 2006-07-03 08:00 | 2006-08-25 17:00 | 2 mons | 89
91 | MP Detail Design Review (Outage Scheduler) | 2006-09-04 08:00 | 2006-09-15 17:00 | 2 wks | 90FS+1 wk
92 | Develop (Outage Scheduler) | 2006-09-18 08:00 | 2007-04-27 17:00 | 8 mons | 91
93 | Vendor Product Test/ Problem Resolution (Outage Scheduler) | 2007-04-30 08:00 | 2007-05-25 17:00 | 4 wks | 92
94 | FAT (Outage)/Variance Resolution (Outage Scheduler) | 2007-05-28 08:00 | 2007-06-29 17:00 | 5 wks | 93
95 | Network Security Analysis | 2005-10-24 08:00 | 2007-04-06 17:00 | 19 mons | 25
96 | Requirements finalized/SOW/Vendor selection | 2005-10-24 08:00 | 2006-05-05 17:00 | 7 mons
97 | Trans Constraints Management Enhancements | 2006-05-08 08:00 | 2007-04-06 17:00 | 12 mons | 96
98 | Dynamic Ratings Processor | 2006-05-08 08:00 | 2007-04-06 17:00 | 12 mons | 96
99 | Voltage / Transient Security Analysis Tool | 2006-05-08 08:00 | 2007-04-06 17:00 | 12 mons | 96
100 | Load/RPP Forecast | 2006-05-08 08:00 | 2006-10-20 17:00 | 6 mons | 96
101 | Study Network Analysis | 2006-05-08 08:00 | 2007-04-06 17:00 | 12 mons | 96
102 | Unit compliance Modeling | 2006-05-08 08:00 | 2007-04-06 17:00 | 12 mons | 96
103 | Resource Parameters | 2005-10-24 08:00 | 2006-05-05 17:00 | 7 mons | 25
104 | Modify Asset Registration Form | 2005-10-24 08:00 | 2005-11-18 17:00 | 1 mon
105 | MP Update Asset Registration Forms | 2005-11-21 08:00 | 2006-05-05 17:00 | 6 mons | 104
106 | LFC (AGC) | 2006-05-08 08:00 | 2007-04-06 17:00 | 12 mons | 96,25
107 | Market Operations | 2005-10-17 08:00 | 2007-12-06 17:00 | 27.95 mons |  | Using the term Market Operations looses its meaning in nodal world where real time control is a stretch to call it a market. I suggest organizing this along the terms used in the protocols and the names of protocol sections such as Day Ahead Operations, Real Time Operations etc. Need to use the terms in the protocols in the schedule as well when discussing the task to implement a named functional requirement required in the protocols.
108 | Preliminary Requirements Develop (Market Ops) | 2005-10-17 08:00 | 2005-12-30 17:00 | 2.75 mons
109 | Day Ahead/AS/COP Preliminary Market Requirements | 2005-10-17 08:00 | 2005-12-30 17:00 | 2.75 mons | 24
110 | Supplemental AS Preliminary Market Requirements | 2005-10-17 08:00 | 2005-12-30 17:00 | 2.75 mons | 24
111 | Reliability Units Commitment Preliminary Market Requirements | 2005-10-17 08:00 | 2005-12-30 17:00 | 2.75 mons | 24
112 | Real-time Preliminary Market Requirements | 2005-10-17 08:00 | 2005-12-30 17:00 | 2.75 mons | 24
113 | CRR Auction Engine Preliminary Market Requirements | 2005-10-17 08:00 | 2005-12-30 17:00 | 2.75 mons | 24
114 | Day Ahead / AS Market/Current Operating Plan (COP) | 2006-01-13 08:00 | 2007-12-06 17:00 | 24.75 mons | 25
115 | Requirements (DA/AS/COP) | 2006-01-13 08:00 | 2006-02-16 17:00 | 5 wks | 3,109
116 | MP Review (DA/AS/COP) | 2006-02-03 08:00 | 2006-02-23 17:00 | 3 wks | 115FF+1 wk
117 | Develop RFP (DA/AS/COP) | 2006-02-17 08:00 | 2006-03-09 17:00 | 3 wks | 115
118 | Vendor proposal (DA/AS/COP) | 2006-03-10 08:00 | 2006-04-20 17:00 | 6 wks | 117
119 | Select/Evaluate/Negiotate (DA/AS/COP) | 2006-04-21 08:00 | 2006-06-01 17:00 | 6 wks | 118
120 | SOW (DA/AS/COP) | 2006-05-19 08:00 | 2006-07-13 17:00 | 2 mons | 119FS-2 wks
121 | Vendor Development (DA/AS/COP) | 2006-07-14 08:00 | 2007-12-06 17:00 | 18.25 mons | 120
122 | Conceptual Design (DA/AS/COP) | 2006-07-14 08:00 | 2006-10-05 17:00 | 3 mons
123 | MP Review Conceptual (DA/AS/COP) | 2006-10-06 08:00 | 2006-10-26 17:00 | 3 wks | 122
124 | Detail Design (DA/AS/COP) | 2006-10-27 08:00 | 2007-01-18 17:00 | 3 mons | 123
125 | MP Detail Design Review (DA/AS/COP) | 2007-01-26 08:00 | 2007-02-15 17:00 | 3 wks | 124FS+1 wk
126 | Develop (DA/AS/COP) | 2007-02-16 08:00 | 2007-08-30 17:00 | 7 mons | 125
127 | Vendor Product Test/ Problem Resolution (DA/AS/COP) | 2007-08-31 08:00 | 2007-09-27 17:00 | 4 wks | 126
128 | FAT (DA/AS/COP) | 2007-09-28 08:00 | 2007-12-06 17:00 | 2.5 mons | 127
129 | Supplemental AS Market | 2006-01-13 08:00 | 2007-12-06 17:00 | 24.75 mons | 25
130 | Finalize Requirements (Supplemental AS) | 2006-01-13 08:00 | 2006-02-16 17:00 | 5 wks | 3,110
131 | MP Review (Supplemental AS) | 2006-02-03 08:00 | 2006-02-23 17:00 | 3 wks | 130FF+1 wk
132 | Develop RFP (Supplemental AS) | 2006-02-17 08:00 | 2006-03-09 17:00 | 3 wks | 130
133 | Vendor proposal (Supplemental AS) | 2006-03-10 08:00 | 2006-04-20 17:00 | 6 wks | 132
134 | Select/Evaluate/Negiotate (Supplemental AS) | 2006-04-21 08:00 | 2006-06-01 17:00 | 6 wks | 133
135 | SOW (Supplemental AS) | 2006-05-19 08:00 | 2006-07-13 17:00 | 2 mons | 134FS-2 wks
136 | Vendor Development (Supplemental AS) | 2006-07-14 08:00 | 2007-12-06 17:00 | 18.25 mons | 135
137 | Conceptual Design (Supplemental AS) | 2006-07-14 08:00 | 2006-10-05 17:00 | 3 mons
138 | MP Review Conceptual (Supplemental AS) | 2006-10-06 08:00 | 2006-10-26 17:00 | 3 wks | 137
139 | Detail Design (Supplemental AS) | 2006-10-27 08:00 | 2007-01-18 17:00 | 3 mons | 138
140 | MP Detail Design Review (Supplemental AS) | 2007-01-26 08:00 | 2007-02-15 17:00 | 3 wks | 139FS+1 wk
141 | Develop (Supplemental AS) | 2007-02-16 08:00 | 2007-08-30 17:00 | 7 mons | 140
142 | Vendor Product Test/ Problem Resolution | 2007-08-31 08:00 | 2007-09-27 17:00 | 4 wks | 141
143 | FAT (Supplemental AS) | 2007-09-28 08:00 | 2007-12-06 17:00 | 2.5 mons | 142
144 | Reliability Unit Commitment (RUC) | 2006-01-13 08:00 | 2007-12-06 17:00 | 24.75 mons | 25
145 | Finalize Requirements (RUC) | 2006-01-13 08:00 | 2006-02-16 17:00 | 5 wks | 3,111
146 | MP Review (RUC) | 2006-02-03 08:00 | 2006-02-23 17:00 | 3 wks | 145FF+1 wk
147 | Develop RFP (RUC) | 2006-02-17 08:00 | 2006-03-09 17:00 | 3 wks | 145
148 | Vendor proposal (RUC) | 2006-03-10 08:00 | 2006-04-20 17:00 | 6 wks | 147
149 | Select/Evaluate/Negiotate (RUC) | 2006-04-21 08:00 | 2006-06-01 17:00 | 6 wks | 148
150 | SOW (RUC) | 2006-05-19 08:00 | 2006-07-13 17:00 | 2 mons | 149FS-2 wks
151 | Vendor Development (RUC) | 2006-07-14 08:00 | 2007-12-06 17:00 | 18.25 mons | 150
152 | Conceptual Design (RUC) | 2006-07-14 08:00 | 2006-10-05 17:00 | 3 mons
153 | MP Review Conceptual (RUC) | 2006-10-06 08:00 | 2006-10-26 17:00 | 3 wks | 152
154 | Detail Design (RUC) | 2006-10-27 08:00 | 2007-01-18 17:00 | 3 mons | 153
155 | MP Detail Design Review (RUC) | 2007-01-26 08:00 | 2007-02-15 17:00 | 3 wks | 154FS+1 wk
156 | Develop (RUC) | 2007-02-16 08:00 | 2007-08-30 17:00 | 7 mons | 155
157 | Vendor Product Test/ Problem Resolution | 2007-08-31 08:00 | 2007-09-27 17:00 | 4 wks | 156
158 | FAT (RUC) | 2007-09-28 08:00 | 2007-12-06 17:00 | 2.5 mons | 157
159 | Real-time Market | 2006-01-13 08:00 | 2007-12-06 17:00 | 24.75 mons | 25 | Is this the SCED? Need to use same terms in protocols
160 | Finalize Requirements (RT Market) | 2006-01-13 08:00 | 2006-02-16 17:00 | 5 wks | 3,112
161 | MP Review (RT Market) | 2006-02-03 08:00 | 2006-02-23 17:00 | 3 wks | 160FF+1 wk
162 | Develop RFP (RT Market) | 2006-02-17 08:00 | 2006-03-09 17:00 | 3 wks | 160
163 | Vendor proposal (RT Market) | 2006-03-10 08:00 | 2006-04-20 17:00 | 6 wks | 162
164 | Select/Evaluate/Negiotate (RT Market) | 2006-04-21 08:00 | 2006-06-01 17:00 | 6 wks | 163
165 | SOW (RT Market) | 2006-05-19 08:00 | 2006-07-13 17:00 | 2 mons | 164FS-2 wks
166 | Vendor Development (RT Market) | 2006-07-14 08:00 | 2007-12-06 17:00 | 18.25 mons | 165
167 | Conceptual Design (RT Market) | 2006-07-14 08:00 | 2006-10-05 17:00 | 3 mons
168 | MP Review Conceptual (RT Market) | 2006-10-06 08:00 | 2006-10-26 17:00 | 3 wks | 167
169 | Detail Design (RT Market) | 2006-10-27 08:00 | 2007-01-18 17:00 | 3 mons | 168
170 | MP Detail Design Review (RT Market) | 2007-01-26 08:00 | 2007-02-15 17:00 | 3 wks | 169FS+1 wk
171 | Develop (RT Market) | 2007-02-16 08:00 | 2007-08-30 17:00 | 7 mons | 170
172 | Vendor Product Test/ Problem Resolution | 2007-08-31 08:00 | 2007-09-27 17:00 | 4 wks | 171
173 | FAT (RT Market) | 2007-09-28 08:00 | 2007-12-06 17:00 | 2.5 mons | 172
174 | CRR Auction Engine | 2006-01-13 08:00 | 2007-07-26 17:00 | 20 mons | 25
175 | Finalize Requirements (CRR Auction Engine) | 2006-01-13 08:00 | 2006-02-09 17:00 | 1 mon | 3,113
176 | MP Review (CRR Auction Engine) | 2006-01-27 08:00 | 2006-02-16 17:00 | 3 wks | 175FF+1 wk
177 | Develop RFP (CRR Auction Engine) | 2006-02-10 08:00 | 2006-03-02 17:00 | 3 wks | 175
178 | Vendor proposal (CRR Auction Engine) | 2006-03-03 08:00 | 2006-04-13 17:00 | 6 wks | 177
179 | Select/Evaluate/Negiotate (CRR Auction Engine) | 2006-04-14 08:00 | 2006-05-25 17:00 | 6 wks | 178
180 | SOW (CRR Auction Engine) | 2006-05-26 08:00 | 2006-06-22 17:00 | 1 mon | 179
181 | Vendor Development | 2006-06-23 08:00 | 2007-07-26 17:00 | 14.25 mons | 180
182 | Conceptual Design (CRR Auction Engine) | 2006-06-23 08:00 | 2006-07-20 17:00 | 4 wks
183 | MP Review Conceptual (CRR Auction Engine) | 2006-07-21 08:00 | 2006-08-03 17:00 | 2 wks | 182
184 | Detail Design (CRR Auction Engine) | 2006-08-04 08:00 | 2006-09-28 17:00 | 2 mons | 183
185 | MP Detail Design Review (CRR Auction Engine) | 2006-10-06 08:00 | 2006-10-19 17:00 | 2 wks | 184FS+1 wk
186 | Develop (CRR Auction Engine) | 2006-10-20 08:00 | 2007-05-31 17:00 | 8 mons | 185
187 | Vendor Product Test/ Problem Resolution | 2007-06-01 08:00 | 2007-06-28 17:00 | 4 wks | 186
188 | FAT (CRR Auction Engine) | 2007-06-29 08:00 | 2007-07-26 17:00 | 4 wks | 187
189 | Commercial Operations | 2006-01-13 08:00 | 2007-11-22 17:00 | 24.25 mons |  | Is this Settlement? Use same terms as Protocols.
190 | Lodestar | 2006-01-13 08:00 | 2007-11-22 17:00 | 24.25 mons | 25
191 | Startup and Contractor Selection Process | 2006-01-13 08:00 | 2006-03-09 17:00 | 2 mons | 3
192 | Requirements | 2006-03-10 08:00 | 2006-06-29 17:00 | 4 mons | 191
193 | SOW/Vendor Selection | 2006-03-10 08:00 | 2006-05-04 17:00 | 2 mons | 192SS
194 | Initiation | 2006-05-05 08:00 | 2006-05-18 17:00 | 0.5 mons | 193
195 | Planning (CSD/DSD) | 2006-05-19 08:00 | 2006-08-10 17:00 | 3 mons | 194
196 | Development | 2007-02-16 08:00 | 2007-07-05 17:00 | 5 mons | 195,126SS
197 | Product Testing/Vendor Site Testing | 2007-07-06 08:00 | 2007-11-22 17:00 | 5 mons | 196
198 | MOS2L* | 2006-01-13 08:00 | 2007-07-05 17:00 | 19.25 mons | 25
199 | Startup and Vendor Selection Process | 2006-01-13 08:00 | 2006-02-09 17:00 | 1 mon | 3
200 | Requirements | 2006-05-19 08:00 | 2006-07-27 17:00 | 2.5 mons | 192FF+1 mon
201 | SOW/Vendor Selection | 2006-06-30 08:00 | 2006-06-30 08:00 | 0 days | 200FS-1 mon
202 | Initiation | 2006-06-30 08:00 | 2006-07-13 17:00 | 0.5 mons | 201
203 | Planning (CSD/DSD) | 2006-07-14 08:00 | 2006-08-10 17:00 | 1 mon | 202
204 | Development | 2007-02-16 08:00 | 2007-04-26 17:00 | 2.5 mons | 203,126SS
205 | Product Testing/Vendor Site Testing | 2007-04-27 08:00 | 2007-07-05 17:00 | 2.5 mons | 204
206 | EDW/DA | 2006-07-14 08:00 | 2007-11-29 17:00 | 18 mons
207 | Startup and Vendor Selection Process | 2006-07-14 08:00 | 2006-08-10 17:00 | 1 mon | 25,122SS
208 | Requirements | 2006-07-14 08:00 | 2006-11-30 17:00 | 5 mons | 207SS
209 | SOW/Vendor Selection | 2006-11-03 08:00 | 2006-12-28 17:00 | 2 mons | 208FS-1 mon
210 | Initiation | 2006-12-29 08:00 | 2007-01-11 17:00 | 0.5 mons | 209
211 | Planning (CSD/DSD) | 2007-01-12 08:00 | 2007-04-05 17:00 | 3 mons | 210
212 | Development | 2007-04-06 08:00 | 2007-09-20 17:00 | 6 mons | 211
213 | Product Testing/Vendor Site Testing | 2007-09-21 08:00 | 2007-11-29 17:00 | 2.5 mons | 212
214 | Market Information System (MIS) | 2006-10-27 08:00 | 2007-11-22 17:00 | 14 mons
215 | Startup and Vendor Selection Process | 2006-10-27 08:00 | 2006-11-09 17:00 | 0.5 mons | 25,3,123
216 | Requirements | 2006-10-27 08:00 | 2006-12-21 17:00 | 2 mons | 215SS
217 | SOW/Vendor Selection | 2006-12-22 08:00 | 2007-01-18 17:00 | 1 mon | 216
218 | Initiation | 2007-01-19 08:00 | 2007-02-01 17:00 | 0.5 mons | 217
219 | Planning (CSD/DSD) | 2007-02-02 08:00 | 2007-04-12 17:00 | 2.5 mons | 218
220 | Development | 2007-04-13 08:00 | 2007-08-30 17:00 | 5 mons | 219
221 | Product Testing/Vendor Site Testing | 2007-08-31 08:00 | 2007-11-22 17:00 | 3 mons | 220
222 | Finance Systems (Credit Monitoring System) | 2006-10-27 08:00 | 2007-10-25 17:00 | 13 mons
223 | Requirements (Credit Monitoring System) | 2006-10-27 08:00 | 2006-11-09 17:00 | 2 wks | 3,25,123
224 | MP Review (Credit Monitoring System) | 2006-11-03 08:00 | 2006-11-16 17:00 | 2 wks | 223FF+1 wk
225 | Develop RFP (Credit Monitoring System) | 2006-11-10 08:00 | 2006-11-23 17:00 | 2 wks | 223
226 | Vendor Proposal (Credit Monitoring System) | 2006-11-24 08:00 | 2006-12-14 17:00 | 3 wks | 225
227 | Select/Evaluate/Negiotate (Credit Monitoring System) | 2006-12-15 08:00 | 2007-01-04 17:00 | 3 wks | 226
228 | SOW (Credit Monitoring System) | 2007-01-05 08:00 | 2007-02-01 17:00 | 1 mon | 227
229 | Vendor Development | 2007-02-02 08:00 | 2007-10-25 17:00 | 9.5 mons
230 | Conceptual Design (Credit Monitoring System) | 2007-02-02 08:00 | 2007-03-01 17:00 | 4 wks | 228
231 | MP Review Conceptual (Credit Monitoring System) | 2007-03-02 08:00 | 2007-03-15 17:00 | 2 wks | 230
232 | Detail Design (Credit Monitoring System) | 2007-03-16 08:00 | 2007-05-10 17:00 | 2 mons | 231
233 | MP Detail Design Review (Credit Monitoring System) | 2007-05-18 08:00 | 2007-05-31 17:00 | 2 wks | 232FS+1 wk
234 | Develop (Credit Monitoring System) | 2007-06-01 08:00 | 2007-09-20 17:00 | 4 mons | 233
235 | Vendor Product Test/ Problem Resolution | 2007-09-21 08:00 | 2007-10-11 17:00 | 3 wks | 234
236 | FAT (Credit Monitoring System) | 2007-10-12 08:00 | 2007-10-25 17:00 | 2 wks | 235
237 | PUCT Market Operations Monitoring System (MOMS) | 2007-02-16 08:00 | 2007-11-22 17:00 | 10 mons
238 | Develop Requirements | 2007-02-16 08:00 | 2007-05-10 17:00 | 3 mons | 25,125
239 | Build Extracts | 2007-05-11 08:00 | 2007-09-27 17:00 | 5 mons | 238
240 | Validate and test | 2007-09-28 08:00 | 2007-11-22 17:00 | 2 mons | 239
241 | Compliance and Performance Monitoring | 2007-02-16 08:00 | 2007-11-22 17:00 | 10 mons
242 | Develop Requirements | 2007-02-16 08:00 | 2007-05-10 17:00 | 3 mons | 25,125
243 | Build Extracts | 2007-05-11 08:00 | 2007-09-27 17:00 | 5 mons | 242
244 | Validate and Test | 2007-09-28 08:00 | 2007-11-22 17:00 | 2 mons | 243
245 | Subsystems/System Staging and Product Test | 2007-01-08 08:00 | 2008-11-06 17:00 | 23.95 mons |  | Too late in project. Need to this with Transition Plan requirements for testing and Early Delivery Systems testing The data base should be built and begin testing as early as possible in the schedule. I suggest the EDS could be delivered by most Vendors within 4-5 months after contract signing. This time is critical to be used to get all data and SCADA systems working with the selected Vendor. The tasks here need to follow the same language of the Transition Plan which has a lot of detail on testing requirements.
246 | IT Buildout / Staging (As needed) | 2007-01-08 08:00 | 2007-04-27 17:00 | 4 mons | 57,29
247 | System Operations Site Tests | 2007-04-30 08:00 | 2008-11-06 17:00 | 19.95 mons
248 | Network Model | 2007-06-04 08:00 | 2008-06-27 17:00 | 14 mons
249 | Vendor ship/stage/startup/verify/update with patches | 2007-06-04 08:00 | 2007-06-29 17:00 | 4 wks | 75,246
250 | Product Field Test | 2007-07-02 08:00 | 2007-07-27 17:00 | 4 wks | 249
251 | Forklift Database (ERCOT) | 2007-07-30 08:00 | 2007-10-19 17:00 | 3 mons | 250
252 | Clean Up DB | 2007-10-22 08:00 | 2008-01-11 17:00 | 3 mons | 251
253 | Network Model Available to MPs for Testing | 2008-01-11 17:00 | 2008-01-11 17:00 | 0 mons | 252
254 | Verify Database and MP Testing | 2008-01-14 08:00 | 2008-06-27 17:00 | 6 mons | 252
255 | State Estimator/Telemetry | 2007-04-30 08:00 | 2008-06-27 17:00 | 15.25 mons
256 | Test Topology Consistency Analyzer | 2007-04-30 08:00 | 2007-10-12 17:00 | 6 mons | 246,79
257 | Verify Accuracy of Telemetry | 2007-04-30 08:00 | 2007-10-12 17:00 | 6 mons | 246,79
258 | Verify and test State Estimator (6-Months Test) | 2008-01-14 08:00 | 2008-06-27 17:00 | 6 mons | 257,256,252
259 | Outage Installation | 2007-07-02 08:00 | 2007-09-07 17:00 | 2.5 mons
260 | Vendor ship/stage/startup/verify/update with patches | 2007-07-02 08:00 | 2007-07-27 17:00 | 4 wks | 94,246
261 | Product Field Test | 2007-07-30 08:00 | 2007-08-10 17:00 | 2 wks | 260
262 | MP Integration Testing (Outages) | 2007-08-13 08:00 | 2007-09-07 17:00 | 4 wks | 261
263 | Network Security Analysis Installation | 2007-04-30 08:00 | 2007-06-22 17:00 | 2 mons
264 | Vendor ship/stage/startup/verify/update with patches | 2007-04-30 08:00 | 2007-05-25 17:00 | 1 mon | 246,95
265 | Product Field Test | 2007-05-28 08:00 | 2007-06-22 17:00 | 1 mon | 264
266 | Resource Parameters (Accurately Passed To RUC/DAM) | 2008-04-25 08:00 | 2008-07-17 17:00 | 3 mons | 105,246,310
267 | LFC | 2007-04-30 08:00 | 2008-11-06 17:00 | 19.95 mons
268 | Vendor ship/stage/startup/verify/update with patches | 2007-04-30 08:00 | 2007-05-25 17:00 | 4 wks | 106,246
269 | Product Field Test | 2007-05-28 08:00 | 2007-06-15 17:00 | 3 wks | 268
270 | LFC QSE Qualification Tests | 2008-04-25 08:00 | 2008-10-09 17:00 | 6 mons | 269,310
271 | LFC QSE Deployment Testing | 2008-10-10 08:00 | 2008-11-06 17:00 | 1 mon | 270
272 | QSE Constant Frequency Tests | 2008-04-25 08:00 | 2008-11-06 17:00 | 7 mons | 270SS
273 | Market Operations Site Tests | 2007-07-27 08:00 | 2008-01-31 17:00 | 6.75 mons
274 | Day Ahead/AS/COP Site Tests | 2007-12-07 08:00 | 2008-01-31 17:00 | 2 mons
275 | Vendor ship/stage/startup/verify/update with patches | 2007-12-07 08:00 | 2008-01-03 17:00 | 1 mon | 128,246
276 | Product Field Test (DA/AS/COP) | 2008-01-04 08:00 | 2008-01-31 17:00 | 1 mon | 275
277 | Supplemental AS Installation | 2007-12-07 08:00 | 2008-01-31 17:00 | 2 mons
278 | Vendor ship/stage/startup/verify/update with patches | 2007-12-07 08:00 | 2008-01-03 17:00 | 1 mon | 143,246
279 | Product Field Test (Supplemental AS) | 2008-01-04 08:00 | 2008-01-31 17:00 | 1 mon | 278
280 | Reliability Unit Commitment Installation | 2007-12-07 08:00 | 2008-01-31 17:00 | 2 mons
281 | Vendor ship/stage/startup/verify/update with patches | 2007-12-07 08:00 | 2008-01-03 17:00 | 1 mon | 158,246
282 | Product Field Test (RUC) | 2008-01-04 08:00 | 2008-01-31 17:00 | 1 mon | 281
283 | Real-time Maket Installation | 2007-12-07 08:00 | 2008-01-31 17:00 | 2 mons
284 | Vendor ship/stage/startup/verify/update with patches | 2007-12-07 08:00 | 2008-01-03 17:00 | 1 mon | 173,246
285 | MPs create and enter offer curves | 2007-12-07 08:00 | 2008-01-03 17:00 | 1 mon | 173,246
286 | Product Field Test (Real-time Market) | 2008-01-04 08:00 | 2008-01-31 17:00 | 1 mon | 285
287 | CRR Installation | 2007-07-27 08:00 | 2007-08-23 17:00 | 1 mon
288 | Vendor ship/stage/startup/verify/update with patches | 2007-07-27 08:00 | 2007-08-09 17:00 | 0.5 mons | 188,246
289 | Product Field Test | 2007-08-10 08:00 | 2007-08-23 17:00 | 2 wks | 288
290 | Commercial Systems Site Tests | 2007-11-23 08:00 | 2007-12-06 17:00 | 0.5 mons |  | The use of Commercial and Market Operations seems to fit ERCOT's organization rather than the tasks need to implement protocols.
291 | Handover from ERCOT development | 2007-11-23 08:00 | 2007-12-06 17:00 | 0.5 mons | 246,197,205
292 | Product Field Test | 2007-12-06 17:00 | 2007-12-06 17:00 | 0 mons | 291
293 | EDW/DA Site Tests | 2007-11-30 08:00 | 2008-01-10 17:00 | 1.5 mons
294 | Vendor ship/stage/startup/verify/update with patches | 2007-11-30 08:00 | 2007-12-27 17:00 | 4 wks | 213,246
295 | Product Field Test | 2007-12-28 08:00 | 2008-01-10 17:00 | 2 wks | 294
296 | MIS Tests | 2007-11-23 08:00 | 2008-01-03 17:00 | 1.5 mons
297 | Vendor ship/stage/startup/verify/update with patches | 2007-11-23 08:00 | 2007-12-20 17:00 | 4 wks | 221,246
298 | Product Field Test | 2007-12-21 08:00 | 2008-01-03 17:00 | 2 wks | 297
299 | Finance Systems Site Tests | 2007-10-26 08:00 | 2007-12-06 17:00 | 1.5 mons
300 | Vendor ship/stage/startup/verify/update with patches | 2007-10-26 08:00 | 2007-11-22 17:00 | 4 wks | 236,246
301 | Product Field Test | 2007-11-23 08:00 | 2007-12-06 17:00 | 2 wks | 300
302 | PUCT MOMS Site Tests | 2007-11-23 08:00 | 2008-01-03 17:00 | 1.5 mons
303 | Vendor ship/stage/startup/verify/update with patches | 2007-11-23 08:00 | 2007-12-20 17:00 | 4 wks | 240,246
304 | Product Field Test | 2007-12-21 08:00 | 2008-01-03 17:00 | 2 wks | 303
305 | Compliance and Performance Monitoring Site Test | 2007-11-23 08:00 | 2008-01-03 17:00 | 1.5 mons
306 | Vendor ship/stage/startup/verify/update with patches | 2007-11-23 08:00 | 2007-12-20 17:00 | 4 wks | 244
307 | Product Field Test | 2007-12-21 08:00 | 2008-01-03 17:00 | 2 wks | 306
308 | ERCOT System Integration Tests | 2008-02-01 08:00 | 2008-07-17 17:00 | 6 mons
309 | Preparation/Coordination | 2008-02-01 08:00 | 2008-02-28 17:00 | 1 mon | 286,250,261,265,269,256,289,295,298,301,304,292,276,279,282
310 | System Integration Testing | 2008-02-29 08:00 | 2008-04-24 17:00 | 2 mons | 309
311 | Internal User Testing | 2008-03-28 08:00 | 2008-06-19 17:00 | 3 mons | 310SS+1 mon
312 | Daylight Saving Time Tests (DST) | 2008-06-20 08:00 | 2008-07-17 17:00 | 1 mon | 311
313 | Market Trials Parallel Operations | 2008-04-25 08:00 | 2008-12-09 17:00 | 8.15 mons
314 | Simulation (Scripted) | 2008-06-20 08:00 | 2008-09-11 17:00 | 3 mons | 311
315 | SCED 6-Months Posting of LMPs Test | 2008-04-25 08:00 | 2008-10-09 17:00 | 6 mons | 310
316 | Simulation (MP driven inputs) | 2008-06-30 08:00 | 2008-12-09 17:00 | 5.85 mons
317 | CRR | 2008-06-30 08:00 | 2008-09-26 17:00 | 3.25 mons
318 | Assign Test CRRs | 2008-06-30 08:00 | 2008-07-25 17:00 | 1 mon | 254
319 | MP Create Test Bids | 2008-07-28 08:00 | 2008-08-01 17:00 | 1 wk | 318
320 | ERCOT Test Setup | 2008-08-04 08:00 | 2008-09-12 17:00 | 6 wks | 319
321 | Run Trial Auction (Monthly, Seasonal and Annual) | 2008-09-15 08:00 | 2008-09-26 17:00 | 2 wks | 320
322 | DAM/AS | 2008-09-29 08:00 | 2008-12-09 17:00 | 2.6 mons | 321
323 | MP Create Test Bid and Offers | 2008-09-29 08:00 | 2008-10-03 17:00 | 1 wk
324 | ERCOT Setup Tests | 2008-10-06 08:00 | 2008-10-17 17:00 | 2 wks | 323
325 | Run DAM w/o Virtual Bids and Offers | 2008-10-20 08:00 | 2008-11-07 17:00 | 3 wks | 324
326 | Run DAM with Virtual Bids and Offers | 2008-11-10 08:00 | 2008-11-28 17:00 | 3 wks | 325
327 | Publish Settlement Statements | 2008-12-01 08:00 | 2008-12-09 17:00 | 7 days | 326
328 | RUC | 2008-09-29 08:00 | 2008-12-02 17:00 | 2.35 mons | 321
329 | MP Create Test Offers | 2008-09-29 08:00 | 2008-10-03 17:00 | 1 wk
330 | ERCOT to Setup Test | 2008-10-06 08:00 | 2008-10-17 17:00 | 2 wks | 329
331 | Run RUC | 2008-10-20 08:00 | 2008-11-21 17:00 | 5 wks | 330
332 | Publish Settlement Statement | 2008-11-24 08:00 | 2008-12-02 17:00 | 7 days | 331
333 | Supplemental AS (SASM) | 2008-09-12 08:00 | 2008-10-23 17:00 | 1.5 mons | 314
334 | MP Create Test Offers | 2008-09-12 08:00 | 2008-09-18 17:00 | 1 wk
335 | ERCOT to Setup Test | 2008-09-19 08:00 | 2008-10-02 17:00 | 2 wks | 334
336 | Run SASM | 2008-10-03 08:00 | 2008-10-23 17:00 | 3 wks | 335
337 | Real-Time Market | 2008-09-12 08:00 | 2008-11-13 17:00 | 2.25 mons | 314
338 | MP Create Test Offers | 2008-09-12 08:00 | 2008-09-18 17:00 | 1 wk
339 | ERCOT To Setup Test | 2008-09-19 08:00 | 2008-10-02 17:00 | 2 wks | 338
340 | 168 HourTest | 2008-10-03 08:00 | 2008-11-06 17:00 | 5 wks | 339
341 | Publish Settlement Statement | 2008-11-07 08:00 | 2008-11-13 17:00 | 1 wk | 340
342 | Cutover (Migration) Tests | 2008-01-07 08:00 | 2009-01-01 17:00 | 12.95 mons
343 | Develop Cutover Plan | 2008-01-07 08:00 | 2008-02-29 17:00 | 2 mons
344 | MP Approval of Cutover Plan | 2008-03-03 08:00 | 2008-03-28 17:00 | 1 mon | 343
345 | Prepare for Cutover/Simulate Cutover | 2008-09-12 08:00 | 2008-12-04 17:00 | 3 mons | 344,314
346 | Perform Cutover | 2008-12-10 08:00 | 2009-01-01 17:00 | 17 days | 345,316,272,258,315,21,254,266
347 | Post Go Live/Availability Test | 2009-01-01 17:00 | 2009-04-09 17:00 | 3.5 mons
348 | TNT Cutover Complete | 2009-01-01 17:00 | 2009-01-01 17:00 | 0 mons | 342
349 | System Initial Operation | 2009-01-02 08:00 | 2009-02-26 17:00 | 2 mons | 342
350 | Availability Test | 2009-02-27 08:00 | 2009-04-09 17:00 | 1.5 mons | 349