## Slide 1
Objectives:
Develop a solution to either enhance or replace the FasTrak tool
Scope/Why is this important?:
Increase the transparency for issues that are submitted via FasTrak
Allow users to have improved access to the data
Improve the reporting functionality
Improve search functionality associated
Improve monitoring and response capabilities
Improve the usability
Dependencies:
SOA Integration - dependent on SOA MID project for integration framework components needed by API (low risk to project)
Project Objectives / Scope / Dependencies
PR-50007 Enhancements to FasTrak
As of January 5, 2006
Page 1

## Slide 2
Phase:
Initiation – Completed in Feb 2005
Planning – Completed in Nov 2005
Execution/Implementation – Started November 14, 2005
Update:
Conducted meeting with MPs on December 9th to review Market Design Document
Posted original business requirements document and the document outlining the changes to the business requirements to ERCOT.com at http://www.ercot.com/services/comm/projects/current/50007/index.html under the Key Documents section
On schedule to deliver the Detailed Design Document to MPs on January 31st
The project is on schedule to meet milestone dates
Summary of Project Status
PR-50007 Enhancements to FasTrak
As of January 5, 2006
Page 2

## Slide 3
** All target dates will become firm after ERCOT design is complete and Execution plan finalized in January
Requirements complete – June 2005
Market Design Document published – November 30, 2005
Detailed Design Document – January 31, 2006
Market Test Scripts target – March 2006
User Guides target – April 2006
Training Materials target – April 2006
Market Test target – May 2006
Production target (‘go live’ with GUI & API) – end of May 2006
High level timeline
PR-50007 Enhancements to FasTrak
As of January 5, 2006
Page 3

## Slide 4
Bus Lead: Scott Egger
phone number: 512-248-3162
e-mail: segger@ercot.com
PPL: Source: Market Priority: 1.1 Rank: 9 Program Area: RO
What prompted the project:
  SCR 732
  SCR 738
Supporting business drivers:
  Practical usage feedback
Additional Information
PR-50007 Enhancements to FasTrak
As of January 5, 2006
Page 4