## Slide 1: Market Redesign Update
TAC
February 2, 2006

## Slide 2: Market Redesign Update
Nodal Budget Assessment
  Resources and Costs
  Timeline and Critical Projects
  Risks

## Slide 3: Resources and Cost
Resources:
  Estimated commitment of ~50 existing ERCOT FTEs, who all need to be backfilled
  Estimate requires ~ 40 additional contractors
Cost:
  Range of $95 – 130MM
Contrast to CBA:
  CBA estimated $59.4 – 76.2MM
  Several categories slightly higher
  Hardware costs significantly higher

## Slide 4: Timeline and Critical Path
For effort estimation assumed 1/1/2009 for Go Live
With 3 months for Pilot and 6 months for Mock Market, 27 months remain to complete all Nodal projects
A number of Nodal projects are now on the critical path (require ~27 months to deliver)
  NMMS, NSA Enhancements, Settlements and Billing, EDW framework, and Nodal training

## Slide 5: Risks
Staffing of Project Management Office
Project Team Staffing
Critical path projects