## Slide 1: Flight Update

## Slide 2: Flight 0106
Details
Flight Kick-off Conference Call 1/13
Flight Began 1/16
Flight 0106 scheduled to conclude 2/28

## Slide 3: Flight 0106 Update
Flight manifest
6 TDSPs
4 New REPs – 16 New Relationships
1 New Umbrella DUNs
1 Existing REP testing in new territory – 1 New Relationships
0 Existing REP testing new functionalities
0 Existing REPs changing Service Providers
2 Existing REPs changing Banks
4054 Tasks total

## Slide 4: Flight 1005 Update
Progress
Connectivity complete
Flight started on time
As of 2/8/2006 9:00 am
  Day 18
    57.13% complete
    59.57% by end of today
    Complete through Day 13
    3 outstanding transactions for week 3
      0 inbound to ERCOT
      0 outbound from ERCOT
      3 Point to Point
    31 overdue transactions for week 4
      8 inbound to ERCOT
      0 outbound from ERCOT
      23 Point to Point

## Slide 5: Flight 0406
Next Flight - 0406
All Market Participants will test for FasTrak
Orientation Meeting 3/7
  Not required for ‘FasTrak only’ testing
Flight Deadline 3/15
  Not required for ‘FasTrak only’ testing
Connectivity Kick-off Conference Call 3/21
Flight Kick-off Conference Call 4/17
Flight Begins 4/20
FasTrak testing 5/24 – 6/5
Flight scheduled to conclude 5/30