## Slide 1
Objectives:
Develop a solution to either enhance or replace the FasTrak tool
Scope/Why is this important?:
Increase the transparency for issues that are submitted via FasTrak
Allow users to have improved access to the data
Improve the reporting functionality
Improve search functionality associated
Improve monitoring and response capabilities
Improve the usability
Dependencies:
SOA Integration - dependent on SOA MID project for integration framework components needed by API (low risk to project)
Project Objectives / Scope / Dependencies
PR-50007 Enhancements to FasTrak
As of February 7, 2006
Page 1

## Slide 2
Phase:
Initiation – Completed in Feb 2005
Planning – Completed in Nov 2005
Execution/Implementation – Started November 14, 2005
Update:
Posted the Detail Design Document on ERCOT’s website on January 31st
The Development team has started coding the final product
Scheduled Market meeting on Monday, February 20th to discuss the detail design documents
Total project budget has increased from $1,631,804 to $2,492,935
  2005 spend was $881,665
  2006 forecasted spend is $1,611,270
The total project budget has increased $861,131
Impact to Project Priority List (PPL) – More detail will be provided at meeting
Reason for increased project budget:
  Augmenting development and testing efforts with contract employees
  Increased forecasted hours worked by ERCOT employees
Summary of Project Status
PR-50007 Enhancements to FasTrak
As of February 7, 2006
Page 2

## Slide 3
** All dates are were derived from ERCOT’s design and planning efforts.
Requirements complete – June 2005
Market Design Document published – November 30, 2005
Detailed Design Document published – January 31, 2006
Market Test Scripts – Starting to develop February 16th
  Script Sub Team kickoff meeting February 16th
  High level draft test scripts developed by ERCOT will be delivered on February 16th
  Scripts will be completed in time to review at the April TTPT meeting (Date TBD)
Project Timeline
PR-50007 Enhancements to FasTrak
As of February 7, 2006
Page 3

## Slide 4
** All dates are were derived from ERCOT’s design and planning efforts.
Market Participant product Demo – Tentatively scheduled for April 12th
ERCOT iTest – April 17th – May 19th
Market Training – Beginning of May 2006
  Training materials will be available to MPs May 8th
  Train the trainer format in Austin, Houston and Dallas
Market Test – May 22nd – June 9th
Final User Guides – June 13th
Tool Cutover Plan:
  Last day to submit new issues in old tool – June 16th
  After June 16th, all new issues submitted in new tool
  Data from old tool will not be converted to new tool
  Cutover plans will be finalized prior to May 22nd
Production (‘go live’ with GUI & API) – June 17, 2006
Project Timeline
PR-50007 Enhancements to FasTrak
As of February 7, 2006
Page 4

## Slide 5
Project Timeline
PR-50007 Enhancements to FasTrak
As of February 7, 2006
Page 5
February 2006
March 2006
April 2006
May 2006
June 2006
Develop Market Test Scripts
ERCOT iTest
MP Training
Market Testing
MP Product Demo
Final User Guides
Go Live on
New Tool

## Slide 6
Bus Lead: Scott Egger
phone number: 512-248-3162
e-mail: segger@ercot.com
PPL: Source: Market Priority: 1.1 Rank: 9 Program Area: RO
What prompted the project:
  SCR 732
  SCR 738
Supporting business drivers:
  Practical usage feedback
Additional Information
PR-50007 Enhancements to FasTrak
As of February 7, 2006
Page 6