## Sheet1
| Problem Statement: | Improve TCR calculation process to minimize the uplifted costs due to zonal congestion and maximize the quantity of TCRs available for auction
# | Issue to address | Initiated by | Current Process | Actions | Responsible party | Due Date | Resolution
1 | Desire by market participants for more visibility of TCR revenue adequacy | CMWG 5/13/05 meeting | As of Feb 14, TCR program quarterly reports through Q4 2005 have been posted. | Market participants are requested to review current reports and provide comments about format or content to Roy McCoy and/or Terry Madden.
2 | ERCOT to look for a better way to identify significant line outages as they're submitted | CMWG 5/13/05 meeting | Current process is that the 45 day Outage Scheduler determines whether an outage will have a significant impact based on a combination of factors: 1) outage duration, 2) volume of redispatched MWs required, 3) volume of recommitment MWs required, 4) opportunity to reschedule the outage to reduce its impact. Based on these factors, if an outage is judged to have a significant impact 45-day Outage Scheduler will request a study from the Resource Planning group quantifying the cost of that outage request. |  |  |  | Outage Sensitivity Factor Screening project has been identified. This will create a new tool allowing Outage Coordinators to more quickly identify the impacts of a specific outage. Project (30056-01) is on the 2006 prioritization list with a Priority of 1.3 and a rank of 90. Not scheduled to be initiated in 2006.
ERCOT will review and determine possible improvements to the following items as they relate to the TCR study:
3 | Line Outages & Construction
| Determine methodology to identify outages with "significant impact" for inclusion in TCR case | CMWG 5/13/05 meeting | Only outages of 5 days or longer are considered. Multiple groups of outages are developed and evaluated to determine which is most limiting on zonal transfers. That combination then used to determine the quantity of TCRs available.
|  |  | Tentative Outages are treated the same as a planned or approved Outage for the TCR calculation process but do not get analyzed by the Outage Coordinators as part of their coordination process. | Review the use of tentative outages with Transmission Operators' Outage Coordinators. | ERCOT
|  |  |  | Determine where Tentative Outages are publicly posted | ERCOT
TCR process could include a step to compare effects of including and excluding Tentative Outages. The difference will be communicated to Outage Coordinators who will coordinate with TOs.
4 | Load distribution
| What are the differences between load distribution in TCR case vs. daily operation case? | CMWG 5/13/05 meeting | TCR case uses loads from TOs. Daily Operations case uses load distribution from recent SCADA. | Should an analysis of the differences be performed? |  |  | No need to pursue additional analysis at this time
5 | Generation outages (and treatment of Mothballed units)
| Should generator outages be included in TCR case? | CMWG 5/13/05 meeting | Conundrum between Protocol requirement to post TCR case and protocol requirement to maintain Resource status as protected information for 180 days. | Three options considered. |  |  | Figure out how to include generator outages in the determination of TCR quantities. Pursue Option 3
1 - Modify the Protocol defining the protected information requirement of Resource status for those resources that effect TCR quantities and/or CSC limits 2 - Remove the Protocol requirement to post TCR cases
3 - Post the case but remove the generation. Wipe out flows on all lines except CSCs and CREs. Intent is not to be able to replicate ERCOT's TCR quantity analysis (run the case), but to be able to verfiy that the case supports the TCR quantities being auctioned.
|  |  |  | Review the Protocol language describing TCR case posting requirement to determine if PRR is needed to implement Option 3 | ERCOT
|  |  |  | Determine process / procedure for implementing a change to the TCR quantity detrmination process to include generator outages. - Timing of change? - Notices / approvals required? | ERCOT
Once generator outages are included in TCR quantity determination, all generator outages should be factored into the analysis (don't implement with the 5 day threshhold a la transmission outages)
6 | Ratings (Dynamic and seasonal) | CMWG 5/13/05 meeting | TCR case uses static ratings from seasonal planning case. Daily Operations case uses dynamic ratings for projected temperatures. |  |  |  | Issue leads to underselling of TCRs. No further analysis required.
7 | Day Ahead (STNET) vs. TCR (MUST) process comparison | CMWG 5/13/05 meeting
| creating transfers |  | Zonal transfers are created in Daily Operations case (STNET) by increasing and decreasing loads (Load/Load transfers). TCR process (MUST) creates transfers by increasing and decreasing generation (Gen/Gen transfers).
| analysis of reactive limits |  | VSAT is being implemented for Day ahead and real time analysis. No reactive limitations are considered in TCR quantity determination. During 2005 Daily CSC limits were set using voltage limits 62 days (includes month of April) for N_H and 3 days for S_H. N_H TCRs were not significantly oversold for April.
| resolution of Base case local congestion |  | Generation is redispatched to resolve base case overloads. | Should generation that was redispatched for local congestion be excluded from MUST analysis? That is, held constant so that when MUST creates gen/gen transfers, Base case overloads don't reappear. |  |  | Issue leads to underselling TCRs. No further analysis desired at this time.
8 | IDEF submittals vs. Service Request submittals
| Is there a way to force TO coordination of IDEF and Service Request submittals? | CMWG 5/13/05 meeting |  | Revise TPIT requests to include SR number | KDonohoo |  | complete
9 | 40% annual TCR Limit
| Is 40% the correct amount to sell in the annual auction? | CMWG 5/13/05 meeting | Protocol specified process to sell 40% in annual auction. | Prepare analysis of historical trend of annual and monthly auction quantities. | RMcCoy
10 | Improve accuracy of 45 day outage list | CMWG 5/13/05 meeting |  | ERCOT to email notice to TOs to update outage data prior to TCR study | JMoseley | July auction | complete
|  | CMWG 5/13/05 meeting |  | ERCOT to post Gantt chart, if possible | JMoseley | July auction | complete
11 | ERCOT will investigate the possibility of a delay from the time changes are submitted to the outage scheduler and when those changes are available on the public website. | CMWG 5/13/05 meeting | Public website info is updated concurrently with Outage Scheduler - no lag time |  |  |  | No action required
12 | TCR training for TO personnel |  |  | Discuss with Vann Weldon to include as an agenda item for 2006 Operator Seminar | BGarza |  | Operator Seminar committee chose not to include as topic for 2006 Seminar - complete
|  |  |  | Discuss issue at seasonal Outage Scheduler meeting | BGarza |  | Presentation given at August 2005 meeting - complete