## Slide 1: TPTF Update
Trip Doggett
TAC
March 9, 2006

## Slide 2: TPTF Update
Meetings February 6 & 7, February 20
Attendance approximately 40
Completed review of ERCOT’s clarification questions on Section 7
Training Update
Reviewed Architecture Document
Reviewed TAC Transition Issues
Next meetings
  Monday, March 6 and Tuesday, March 7
  Tuesday, March 28 and Wednesday, March 29

## Slide 3: ERCOT’s Clarification Questions
Reviewed questions from Sections 1, 3, 4, 5, 6, 7, 10, and 22F with TPTF
Questions from 2, 8, 9, 16, and 17 yet to be presented
ERCOT preparing Nodal PRRs, by section, to address synchronization requirements and address clarifications
Plan to present PRRs for Sections 1, 3, 4, 5, 6, and 7 beginning March 28

## Slide 4: TPTF Update – NMMS Requirements
First Business Requirements Document for TPTF approval is for the Network Model Management System
Primary objectives are:
  Ensure consistency between Network Operations Model, CRR Network Model, and Annual Planning Models
  Meet timing requirements to modify the Network Operations Model close to the time actual operations occur in the network
Process
  2 Feb - Posted proposed timeline / framework for approval
  6 Feb - Reviewed proposed timeline / framework for approval w/TPTF
  11 Feb - Posted a draft of the document for review
  17 Feb - Sent a note to TAC so other Subcommittee Chairs would be aware of
  the process
  20 Feb - Overview of document / Q&A with TPTF
  23 Feb - Comment deadline (Received 7 sets of comments from 6 companies)
  1 Mar - ERCOT distributed revised document addressing comments
  6 Mar - Goal - TPTF approve as being in compliance with applicable Protocols

## Slide 5: TPTF Update – NMMS Requirements
Received a number of comments around business processes impacted by the nodal requirement of consistency between the models. This may merit a workshop with TSPs to discuss the requirements in the Nodal Protocols.
The Transition Plan says, “Any declaration of the accomplishment of a major milestone (business requirements, conceptual design, and successful completion of Market Participant testing) or a decision to proceed is contingent on the approval of both ERCOT and TAC.” Should we bring each business requirement document to TAC for approval?

## Slide 6: TAC Transition issues
3.1.1 ERCOT must work with the appropriate TAC Subcommittee to develop procedures for characterizing a Simple Transmission Outage
3.10.7.1 Each Transmission Element must have a unique identifier using a consistent naming convention used between ERCOT and TSPs. ERCOT shall develop the naming convention with the assistance of the TSP and the approval of TAC
3.10.7.4 The appropriate TAC subcommittee shall establish a task force that is open to Market Participants, comprised of technical experts to develop a set of Telemetry Criteria consistent with the minimum requirements of the Protocols
3.10.9 The appropriate TAC subcommittee shall establish a task force that is open to Market Participants, comprised of technical experts to develop a State Estimator Performance Standard consistent with the minimum requirements of the Protocols.

## Slide 7: TAC Transition issues
3.19(2) An appropriate subcommittee approved by TAC (“TAC Subcommittee”) may develop an alternative list through the analysis described below for determining Competitive Constraints
3.19(3) The TAC Subcommittee shall perform the following analysis with the goal of developing an objective standard for determining Competitive Constraints:
5.61(4) The process for determining the verifiable actual costs must be developed by ERCOT, approved by the appropriate TAC subcommittee
5.6.3(3) The process for determining the verifiable actual costs for a startup attempt under paragraph (2) above must be developed by ERCOT, approved by the appropriate TAC subcommittee

## Slide 8: TAC Transition issues
6.5.7.6.1(2) ERCOT shall develop a methodology, subject to TAC approval, to determine the optimal frequency bias for given system conditions
6.5.7.6.2.3(1) ERCOT shall develop a procedure approved by TAC to deploy Resources providing Non-Spinning Reserve Service
6.5.9.4.1(2)(b) ERCOT shall develop a procedure for determining which Load Resources to interrupt and to equitably allocate Load Resources to one of two deployment stacks to enable a 50% deployment, which procedure must be approved in advance by TAC
7.2.1 The appropriate TAC subcommittee shall establish a task force that is open to Market Participants, comprised of technical experts, to develop a naming convention for CRRs consistent with the requirements of the Protocols
8.0 in some instances Section 8 requires ERCOT to develop other performance measures that must be approved by the Technical Advisory Committee (TAC)

## Slide 9: Questions
?