## Slide 1
Objectives:
Add remaining fields to the ESIID Look Up functions requested in PRR312.
Scope/Why is this important?:
Allow users to have improved access to ESIID data
Improve the reporting functionality
Improve the usability
Dependencies:
TIBCO Integration – API component dependent on TIBCO services that will be implemented with PR50007 - Fastrak
Project Objectives / Scope / Dependencies
PR-50025 Enhancements to Find ESIID
As of March 10, 2006
Page 1

## Slide 2
PR50025 Phase:
Initiation – Completed August 8, 2005
Planning – Completed December 19, 2005
Execution/Implementation – 2 phases
Phase1:
Addition of Siebel Data Fields to TDSP ESIID Reports
  Premise Type
  Power Region
  Open Service Orders
Addition of Additional Lodestar Data Fields to TDSP ESIID Reports
  Station ID(Station Name and Station Code)
  Metered/Unmetered Flag
Summary of Project Status
PR-50025 Enhancements to Find ESIID
As of March 10, 2006
Page 2

## Slide 3
  Phase 2
New ESIID data to be returned by the TML Find ESIID function and to be synchronized with the data delivery via the P2API and the TDSP ESIID Report.
  Station ID
  Metered / Unmetered
  Power Region
Enhance current API to be synchronized with the data delivery via TML ESIID Lookup function and the TDSP ESIID Report.
  Premise Type
  Open Service Orders
  Power Region
  Station ID
  Metered/Unmetered Flag
Summary of Project Status
PR-50025 Enhancements to Find ESIID
As of March 10, 2006
Page 3

## Slide 4
Project Timeline
PR-50025 Enhancements to Find ESIID
As of March 10, 2006
Page 4
 | Phase 1 - TDSP Extract | Phase 2 - PiAPP / GUI
Code / Unit Test | 4/10/06 | 06/2006
Product Test | 5/09/06 | 07/2006
ITEST | 06/01/06 | 10/2006
Go-Live | 06/05/2006 – ERCOT Stabilization 07/04/2006 – Market | 10/2006
**Original deployment dates Q405-Q106. Find ESIID functions of GUI and piApp will have to be redeveloped with PR50121_07:RBP. To reduce redevelopment and testing, these new functions will be delivered concurrently with the rollout of PR50121_07 that is currently in Planning. Will return to July RMS with actual dates.

## Slide 5
Additional Information:
Pre-Implementation – SIR 10251: Update TDSP ESIID Reports to include additional fields:
        Premise Type (populated value)
        Station ID (null value)
        Power Region (null value)
        Metered/Un-metered Flag (null value)
        Pending Move-in/Move-out (null value)
  Populate reports with null values until fields are available in Phase One. Premise Type values would be available immediately.
  Requires only one change to DDL available on March 9, 2006.
ERCOT Implementation: 04/03/2006
Market Implementation: 04/04/2006-Monthly Report and 04/05/2006 Weekly Report
PR-50025 Enhancements to Find ESIID
As of March 10, 2006
Page 5

## Slide 6
Bus Lead: Hope Satterfield
phone number: 512-248-6522
e-mail: hsatterfield@ercot.com
PPL: Source: Market Priority: 1.0a Rank: .06 Program Area: MO
What prompted the project:
  PRR 312
Additional Information
PR-50025 Enhancements to Find ESIID
As of March 10, 2006
Page 6