## Slide 1
Objectives:
Develop a solution to either enhance or replace the FasTrak tool
Scope/Why is this important?:
Increase the transparency for issues that are submitted via FasTrak
Allow users to have improved access to the data
Improve the reporting functionality
Improve search functionality associated
Improve monitoring and response capabilities
Improve the usability
Dependencies:
SOA Integration - dependent on SOA MID project for integration framework components needed by API (low risk to project)
Project Objectives / Scope / Dependencies
PR-50007 Enhancements to FasTrak
As of March 14, 2006
Page 1

## Slide 2
Project Budget
PR-50007 Enhancements to FasTrak
As of March 14, 2006
Page 2
Category | Original Estimate | Revised Estimate
Software | $290,000 | $320,666
Hardware | $25,000 | $55,476
Internal Labor | $325,000 | $643,445
External Labor | $510,000 | $1,227,687
Contingency | $400,000 | $109,419
Training |  | $16,627
Taxes and Interest |  | $119,616
Total | $1.55MM | $2.493M

## Slide 3
Phase:
Initiation – Completed in Feb 2005
Planning – Completed in Nov 2005
Execution/Implementation – Started November 14, 2005
Update:
February 20th Market meeting discussed detail design documents and provided product walk thru
March 1st announced MarkeTrak as the name of the new tool
February 28th sent notice to MPs requesting data on FasTrak Users and Digital Certificates
  ERCOT has received responses from 65 out of 123 DUNS numbers
  Week of April 3rd ERCOT is scheduled to start issuing Digital Certificates to new USA contacts
  Starting on May 1st USA contacts can start requesting additional Digital Certificates for its MarkeTrak users
Summary of Project Status
PR-50007 Enhancements to FasTrak
As of March 14, 2006
Page 3

## Slide 4
Update (cont.):
Digital Certificates cont.
  All users of MarkeTrak (GUI) will require a Digital Certificate
  If a user has an active Digital Certificate then will not require another Digital Certificate
  All Market Participants that wish to use the MarkeTrak API will require a Digital Certificate designated for API
  The issued Digital Certificate will not require a role for MarkeTrak
  MarkeTrak will define a user’s role/responsibilities/permissions
March 2nd posted updated detail design documents and FAQ to ERCOT’s website
March 6th Market meeting discussed notifications, user guides, and issue grids
March 14th Started weekly project conference calls with Market Participants
Summary of Project Status
PR-50007 Enhancements to FasTrak
As of March 14, 2006
Page 4

## Slide 5
** All dates are were derived from ERCOT’s design and planning efforts.
Requirements complete – June 2005
Market Design Document published – November 30, 2005
Detailed Design Document published – January 31, 2006
Market Test Scripts – Started to develop February 16th
  February 16th Script Sub Team met in Dallas to start developing market test scripts
  March 9th Script Sub Team met in Houston to continue developing market test scripts
  Scripts will be completed in time to review at the April TTPT meeting (Date TBD)
Project Timeline
PR-50007 Enhancements to FasTrak
As of March 14, 2006
Page 5

## Slide 6
** All dates are were derived from ERCOT’s design and planning efforts.
Market Testing – May 22nd – June 9th
  API testing is only required if you plan on using it
  GUI testing is voluntary – contact Susan Munson (smunson@ercot.com) to volunteer
Market Participant product Demo – Scheduled for April 11th from 9:30am – Noon in room 168
ERCOT Testing – April 17th – May 19th
Market Training – Beginning of May 2006
  Training materials will be available to MPs May 8th
  Train the trainer format in Austin, Houston and Dallas
Project Timeline
PR-50007 Enhancements to FasTrak
As of March 14, 2006
Page 6

## Slide 7
** All dates are were derived from ERCOT’s design and planning efforts.
Final User Guides – June 13th
Tool Cutover Plan:
  Last day to submit new issues in old tool – June 16th
  After June 16th, all new issues submitted in new tool
  Data from old tool will not be converted to new tool
  Cutover plans will be finalized prior to May 22nd
Production (‘go live’ with GUI & API) – June 17, 2006
Project Timeline
PR-50007 Enhancements to FasTrak
As of March 14, 2006
Page 7

## Slide 8
Project Timeline
PR-50007 Enhancements to FasTrak
As of March 14, 2006
Page 8
February 2006
March 2006
April 2006
May 2006
June 2006
Develop Market Test Scripts
ERCOT iTest
MP Training
Market Testing
MP Product Demo
Final User Guides
Go Live on
New Tool

## Slide 9
Bus Lead: Scott Egger
phone number: 512-248-3162
e-mail: segger@ercot.com
PPL: Source: Market Priority: 1.1 Rank: 9 Program Area: RO
What prompted the project:
  SCR 732
  SCR 738
Supporting business drivers:
  Practical usage feedback
Additional Information
PR-50007 Enhancements to FasTrak
As of March 14, 2006
Page 9