## Slide 1: PMO Update to RMS
Troy Anderson
Program Management Office
March 15, 2006

## Slide 2
PMO Process Review
Recent Organizational Changes
  Project Managers now report to Business Teams
  Divisional PPLs have been created with defined budgets
    RO budget = $6.75 M
    Adam Martinez leads RO project efforts
  Program Management Office provides process support and overall portfolio reporting
Impact on Retail Projects
  Less impact on Retail projects when changes occur in other Program Areas

## Slide 3
PMO Process Review
Project Cost Estimates & Budgeting
  Step 1 – Initial Project Idea Proposed
    Impact Analysis provides budget range based on reviews with Subject Matter Experts
    “<$100k”, ”$100k-$500k”, “$500k-$1M”, “$1M-$3M”
  Step 2 – Project Idea is Approved
    Detailed Time & Cost Estimate is prepared by CART team
    This estimate includes a 35% contingency due to high level nature of project requirements
    Project is added to division portfolio based on logical fit and resource plans

## Slide 4
PMO Process Review
Project Cost Estimates & Budgeting (continued)
  Step 3 – Project Initiation/Planning
    CART initiates project based on resource plans
    During Planning Phase, estimate is refined based on detailed design work
    Exit criteria for planning: project plan, resource plan, final requirements, and revised budget
  Step 4 – Project enters Execution
    Request for final Execution budget is presented to Strategic Review Team (SRT = ERCOT directors)
    This estimate includes 10% contingency
    If total project budget exceeds $1M, approval to proceed by the Board of Directors is required
    Any change to scope, schedule or budget requires an approved change control
    Change controls are approved by sponsor (and SRT and Board of Directors, if necessary)

## Slide 5
FasTrak Budget Change Impact
Situation: FasTrak budget increased by $860k
  Two Primary Causes
    Additional contractors needed for development & testing
    Increased forecasted hours worked by ERCOT employees
Potential Impact on Other Retail Projects
  Scenario 1
    PR-60010_01 “Extend SOA Footprint” is in queue behind PR-50121_07 “Retail Business Processes”
    It is likely that 60010_01 will run into 2007, freeing up funds in 2006
  Scenario 2
    Either “Performance Measures Reporting” and/or “Terms & Conditions” could extend into 2007, freeing up funds in 2006

## Slide 6: Potential CIR Timeline
Approximate Timeline to Initiate Customer Information Repository (CIR) Project (assumes approval at each level and no other events impacting the schedule)
August
2006
Board Vote
3/15
2006
PRR Submitted
4/21
2006
RMS Review of PRR
6/1
2006
TAC Vote
5/18
2006
Initial PRS Vote
7/18
2006
Retail Operations Program Area Review
Project Initiation
Sept/Oct
2006
3/8
2006
Final PRS Vote (includes IA, CBA and Prioritization)
3/17
2006
3/27
2006
4/4
2006
ERCOT Questions to Market
v1
ERCOT Questions to Market
v2
Market
Answers
v1
Market
Answers
v2
5/11
2006
IA and CBA Due Date for Posting
5/2
2006
Final Market
CBA Data Due