## Slide 1: PMO Update to RMS
Troy Anderson
Program Management Office
March 15, 2006

## Slide 2
FasTrak Budget Change Impact
Situation: FasTrak budget increased by $860k
  Two Primary Causes
    Additional contractors needed for development & testing
    Increased forecasted hours worked by ERCOT employees
Potential Impact on Other Retail Projects
  Scenario 1
    PR-60010_01 “Extend SOA Footprint” is in queue behind PR-50121_07 “Retail Business Processes”
    It is likely that 60010_01 will run into 2007, freeing up funds in 2006
  Scenario 2
    Either “Performance Measures Reporting” and/or “Terms & Conditions” could extend into 2007, freeing up funds in 2006

## Slide 3: Potential CIR Timeline
Approximate Timeline to Initiate Customer Information Repository (CIR) Project (assumes approval at each level and no other events impacting the schedule)
August
2006
Board Vote
3/15
2006
PRR Submitted
4/21
2006
RMS Review of PRR
6/1
2006
TAC Vote
5/18
2006
Initial PRS Vote
7/18
2006
Retail Operations Program Area Review
Project Initiation
Sept/Oct
2006
3/8
2006
Final PRS Vote (includes IA, CBA and Prioritization)
3/17
2006
3/27
2006
4/4
2006
ERCOT Questions to Market
v1
ERCOT Questions to Market
v2
Market
Answers
v1
Market
Answers
v2
5/11
2006
IA and CBA Due Date for Posting
5/2
2006
Final Market
CBA Data Due