|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Technical Advisory Committee Reliability and Operations Subcommittee for March 2006 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  | Section |
| 1. | Interconnection Requests Increase by 5,328 MW in March: Ten new generation interconnection requests were received by ERCOT for screening studies in March. The total capacity in all generation interconnection requests is 25,946 MW. |  |  |  |  |  |  | 1.0 |
| 2. | RMR Cancellation Notice Sent to La Palma: On March 31st ERCOT sent notice to Sempra Texas Services that the RMR contract for La Palma Units #5, 6, & 7 (222 MW) would be cancelled effective June 30, 2006. |  |  |  |  |  |  | 2.0 |
| 3. | ERCOT Presents Initial Entergy-TX Integration Report. On March 29th, ERCOT presented the results of the initial phase of the ERCOT/Entergy-TX Integration Study during a PUCT workshop. Scope of this study was to find the minimum capital cost plan that resolves constraints for the potential electrical integration of Entergy-TX into ERCOT. |  |  |  |  |  |  | 3.0 |
| 4. | ERCOT Completes Short Circuit Study. ERCOT staff has completed the 2006 Current Year Short Circuit study. The results of this study are posted on the ERCOT website. |  |  |  |  |  |  | 4.0 |
| 5. | ERCOT Files FERC Form 715 Report. ERCOT staff has completed and filed with the Federal Energy Regulatory Commission (FERC), the Annual Transmission Planning and Evaluation Report (FERC Form 715). An Overview of the FERC Form 715 Report can be found at: FERC: eForms - Form 715 Overview |  |  |  |  |  |  | 4.0 |
| 6. | ERCOT Files DOE EIA-411 Report. ERCOT staff has completed and filed with the North American Electric Reliability Council (NERC) the annual U.S Department of Energy (DOE) Coordinated Bulk Power Supply Program Report (EIA-411). An overview of the DOE EIA-411 Report can be found at: http://www.eia.doe.gov/cneaf/electricity/forms/eia411/eia411.pdf |  |  |  |  |  |  | 4.0 |

1.0	Status of Active Generation Interconnection Requests

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” data folder posted in the “Operations and System Planning” data area on the ERCOT website.

1.1	New Generation Beginning Commercial Operations.

There were no generation projects placed into commercial activity in March, 2006.

1.2	Active Generation Interconnection Requests.

The table below summarizes the active generation interconnection requests currently being processed by ERCOT System Planning.  The current 81 projects reflecting 25,946 MW of capacity in an increase of 10 projects and 5,328 MW of capacity respectively over the February totals of 71 projects and 20,618 MW of capacity.

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Currently tracking 81 active generation interconnection or change requests |  |  |  |  |  |
|  |  | North | South | West | Total |
| Security Screening Study |  | 2 | 2 | 14 | 18 |
| SSS Completed |  | 1 | 3 | 11 | 15 |
| Full Interconnect Study |  | 9 | 6 | 20 | 35 |
| FIS Completed |  | 0 | 0 | 0 | 0 |
| Interconnect Agreement Completed (Includes public letters) |  | 6 | 4 | 10 | 20 |
| Capacity for Grid, MW |  | 6,905 | 8,947 | 10,094 | 25,946 |
| Wind MW (under development) |  | 180 | 2,130 | 9,340 | 11,650 |

1.3	Potential Future Generation Interconnections.

The table below summarizes the publicly-known potential future generation projects for the ERCOT region.

| FUTURE GENERATION INTERCONNECTIONS (PUBLIC PROJECTS) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR # | Site Name | Status | County | Region | Fuel | In Service Date | MW into Grid | Change from Last Report |
| 01INR0028 | Orion Delaware Mountain Wind Farm | Interconnect Agreement | Culberson | West | Wind | Dec-07 | 175 |  |
| 03INR0034 | Silver Star Project | Interconnect Agreement | Erath | West | Wind | Mar-07 | 60 |  |
| 04INR0011 | Mesquite Wind Farm 1 | Interconnect Agreement | Shackelford | West | Wind | Dec-06 | 200 |  |
| 04INR0015 | Cirello 1 (Buffalo Gap 2) | Interconnect Agreement | Taylor | West | Wind | Mar-07 | 120 | Name Change |
| 04INR0020 | WKN Wind 1 Snyder | Interconnect Agreement | Scurry | West | Wind | Dec-06 | 60 |  |
| 05INR0011 | Forest Creek 1 | Interconnect Agreement | Sterling | West | Wind | Dec-06 | 215 |  |
| 05INR0015 | Gulf Wind | Public Letter | Kenedy | South | Wind | Sep-07 | 1,200 |  |
| 05INR0017 | Red Canyon 1 | Interconnect Agreement | Borden | West | Wind | Jun-06 | 84 |  |
| 05INR0018 | Horse Hollow 2 | Interconnect Agreement | Taylor | West | Wind | Jun-06 Dec-06 | 127 | In-Service Date Change |
| 06INR0006 | Cobisa-Greenville | Public Letter | Hunt | North | Gas | May-08 | 1,750 |  |
| 06INR0035 | Colorado Bend Energy Center | Interconnect Agreement | Wharton | South | Gas | Dec-06 | 275 | New |
| 06INR0036 | Quail Run Energy Center | Interconnect Agreement | Ector | West | Gas | Dec-06 | 275 | New |
| 06INR0016 | Dow 9 | Interconnect Agreement | Brazoria | South | Gas | Oct-06 | 0 |  |
| 06INR0017 | Limestone Upgrade | Interconnect Agreement | Limestone | North | Coal | May-06 | 110 |  |
| 06INR0008 | Big Spring Carbon Plant Electricity Generating Facility | Interconnect Agreement | Howard | West | Waste heat | Apr-06 | 12 | Name Change |
| 09INR0001 | Sandy Creek | Public Letter | McLennan | North | Coal | Jul-09 | 800 |  |
| 09INR0002 | J K Spruce 2 | Public Letter | Bexar | South | Coal | Aug-09 | 750 |  |
| 09INR0006 | Oak Grove | Public Letter | Robertson | North | Coal | Mar-09 | 1,660 |  |
| 10INR0002 | Hugo Plant | Public Letter | Choctaw, OK | North | Coal | Dec-10 | 500 |  |
| 11INR0001 | Twin Oaks 3 | Public Letter | Robertson | North | Coal | Jun-11 | 630 |  |
|  |  |  |  |  |  | Totals: | 9,003 |  |

2.0	Status of RMR Contracts

The table below summaries generating units currently under RMR Contract as of March 31, 2006.

| Unit | Generation Capacity (MW, Net) | RMR Contract Status | Contract Date | Current Anticipated Exit Date | Change Since Last Report |
| --- | --- | --- | --- | --- | --- |
| BM Davis 1 | 335 | Under Contract. Termination Letter Sent | 1/1/06-12/31/06 | 5/19/06 | N/A |
| La Palma 5, 6, &7 | 222 | Under Contract. Termination Letter Sent | 1/1/06-12/31/06 | 6/30/06 | 90 Day Termination Notice Sent 3/31/06. |
| Laredo 1, 2, & 3 | 172 | Under Contract | 1/1/06-12/31/06 | 3Q 2010 under review | N/A |
| Atkins 3, 4, 5, 6 | 97 | ERCOT in negotiations for RMR services for Units 4, 5, and 6 starting in June 2006. |  |  | N/A |
| Total MW Under RMR Contract as of March 31, 2006 | 729 |  |  |  |  |

3.0	Regional Planning Activities

The following summarizes numerous significant activities associated with regional planning issues.

3.1	Long-term System Study (Senate Bill 20).

  - A sufficient number of bids were received from vendors in response to the Wind Generation Assessment RFP.  Telephone interviews with vendors selected as finalists have been scheduled for the week of April 3 – 7th.

  - Comments on the generation scenario drivers and the modeling process for this study were requested of the Regional Planning Groups by April 12th.  Also, a workshop to develop scenarios for this study will be held on April 21st.

3.2	Pre-Nodal (Five-Year) Study Follow-up.

- Studying 2007 projects on which TSPs have requested timely decisions prior to the completion of the Five-Year Study.

- Completed, distributed and requested TSP input on differences between 2006 – 2007 TPIT vs SSWG Basecase in order to know what projects that do not need RPG approval.  Started the 2007-2008 and 2008-2009 TPIT vs SSWG basecase comparisons.  Next phase is to complete annual basecases and work a year at a time through the RPG-level projects in order to determine appropriate timing of projects from pre-nodal analysis.

- Completed an update of the wind generation portfolio in the Planning Model for 2007.  The expected MW-level for signed interconnects will be near the 2009 RPS level.

3.3	Entergy Study (PUCT Project No. 32217:  Entergy Gulf States Inc.’s  Plan for Identifying Applicable Power Region Pursuant to PURA 39.452(F)).

  - ERCOT presented the results of the initial phase of the ERCOT/Entergy-TX Integration Study at the PUCT workshop on March 29th.  Scope of this study was to find the minimum capital cost plan that resolves thermal constraints for the combination of with and without the Entergy steam units and with different sizes of DC interconnection.  ERCOT identified several transmission projects that would be necessary to reliably integrate the two systems together and other transmission projects that would be economic.  The estimated capital cost of the integration would be $160-$460M, depending on assumptions.  Details of the presentation can be found at http://oldercot.ercot.com/tmaps/login.cfm in the Long Term Study folder.  Several additional studies are required, but ERCOT is waiting for Commission feedback before starting follow-up studies.

3.4	Regional Planning Group (RPG) Project Reviews.

  - Comments were received during the RPG comment period on the Centerpoint dynamic reactive project.  The primary issue on this project is what criteria should be met regarding dynamic or static reactive compensation.  System Planning will work with the ROS/DWG to address this issue.

  - TXUED submitted the addition of a second 345/138kV auto at Sandow for RPG review; and STEC submitted two small 69kV projects.  The comment period for both of these projects ends April 17th.

  - ERCOT sent a letter to AEP concurring with AEP’s decision  to incur extra cost to expedite construction on the Hamilton Rd – Uvalde 138kV line and temporarily install the phase shifter planned for the Sonora-Hamilton Rd. line in this line for summer 2006.

4.0	Transmission Services Activities

The following summarizes numerous significant activities associated with the Transmission Services group.

4.1 	Dynamic Analysis and Modeling.

- Combined Cycle Stability Model Development RFP is being finalized and expected to be reviewed by TAC ROS and Dynamics Working Group in April.

4.2	Case Building.

- ERCOT System Planning staff updated the Data Set A and Data Set B quarterly Transmission Project Information Tracking (TPIT) cases.

4.3	Network Model Management System (NMMS) Support.

- ERCOT System Planning staff provided support at the recent Nodal Modeling Forum meeting (development of the NMMS project).

4.4	Load Forecasting.

- ERCOT staff continued developing a new long-term load and energy forecast.  In this phase, determined the weather sensitivity of the weather zone forecast using a higher than normal weather profile. Also, calculated forecast limits (variability) by performing Monte Carlo simulation on a system model.

- ERCOT staff is continuing work on the 2006 Capacity Demand and Reserve (CDR) Report.

4.5	Other.

- The 2006 Current Year Short Circuit study case has been completed and is posted on the ERCOT website, within the Operations and Planning folder “System Protection Short Circuit Data…”

- An update of the Transmission Project Information Tracking (TPIT) workbook was completed in March and posted for review.  The next update is due to ERCOT May 1st and will be posted by June 1st.

- ERCOT Staff completed and filed with NERC, the DOE EIA-411; Coordinated Bulk Power Supply Program Report.

- In March, ERCOT staff completed and filed the annual FERC Form 715; Annual Transmission Planning and Evaluation Report.  Work is now ongoing to complete by June 1, the annual FERC Form 714; Annual Electric Control and Planning Area Report.

5.0	Upcoming Events/Deadlines

April

- ERCOT Operator Training Seminars; March-April.

- NERC Standards Evaluation Subcommittee Conference call; April 4th.

- ERCOT will hold a public meeting on April 6th to receive comments from market participants and other interested persons concerning the Federal Energy Regulatory Commission’s newly adopted Rules Concerning Certification of the Electric Reliability Organization (“ERO Reliability Rule” or “rule”), which were issued on February 3, 2006.

- NERC Data Coordination Working Group (DCWG) meeting; usually in April-no date set yet.

- ERCOT to make presentation at United Wind Interest Group (UWIG); meeting April 5-7th, Washington DC.

- Non-Opt In Entities (NOIES) generation dispatch data due to ERCOT SSWG; April 21st.

- Regional Planning Group (RPG) workshop to develop scenarios for Long-Term System Assessment; April 21st.

- NERC Multiregional Modeling Working Group (MMWG) meeting; April 24.

- Siemens PTI MUST User Group meeting; April 24.

- Siemens PSS/e User Group meeting; April 25.

- Meeting with AEP and TxU to verify existing and future transmission information.

May

- TPIT update information due to ERCOT; May 1st.

- RAW data files for base case development due to ERCOT SSWG; May 5th.

- NERC Transmission Issues Subcommittee (TIS) meeting; May 10-11th.

- TAC ROS Dynamics Working Group (DWG) meeting; May 17-18.