## Slide 1: RO Project Priority List Update EDW Projects Update RMS Meeting
Adam Martinez
Mgr, Market Ops Divisional Projects Organization
ERCOT
April 12, 2006

## Slide 2: Recent Impacts to RO Project Portfolio
2006 RO allocation = $6.75M; estimate for projects above “cut line” = $7M
  Not started, Initiation, Planning phases – Project budgets are still approximations; not based on completed Requirements or Design specifications
  Execution, Closing phases – Project budget “locked” with baseline budget and 10% contingency
Projects above “cut line”
  No current impact to projects above the “cut line” resulting from MarkeTrak increase and anticipated SOA increase
  Market still has $1.5M identified for 2 projects not yet initiated
    Performance Measures Reporting Requirements
    Terms and Conditions Requirements
Projects below “cut line,” within “capability” range
  ERCOT initiates projects in rank order, unless constraints prevent initiation
    SOA Extend Footprint – Not started; env. & resource constraint with RBP project
    Enhancements to Digital Certificates – Initiating; transferred to IO portfolio
    ESI ID Account Table Split – Not started; resource constraint with RBP Project
  ERCOT.com Secured Area project – continuing with Initiation phase
  EDW transition projects – initiating several of these projects this week

## Slide 3: Current Status of RO Portfolio*
Source | Comm | Prog Area | Project | Project No. | Status | 2006 Priority | 2006 Rank | 2006 Budget Range
Market | RO | RO | Enhancement to FasTrak Tools | 50007 | Execution | 1.0a | 0.03 | $1M-$3M
ERCOT | RO | RO | Service Oriented Architecture (SeeBeyond Replacement) | 50121 | Execution | 1.0a | 0.08 | N/A
ERCOT | RO | RO | Endpoint Services - Phase I | 50121_06 | Closing | 1.0a | 0.08 | $100k-$500k
ERCOT | RO | RO | Retail Business Processes | 50121_07 | Planning | 1.0a | 0.08 | $1M-$3M
ERCOT | RO | RO | Endpoint Services - Phase II & III | 50121_08 | Planning | 1.0a | 0.08 | $100-$500K
ERCOT | RO | RO | TX SET 2.1 | 40034 | Closing | 1.0a | 0.09 | <$100k
ERCOT | RO | RO | 2005 SIR Enhancements | 50026 | Execution | 1.0b | 0.89 | $100k-$500k
Market | RMS | RO | ERCOT Outage Evaluation and Resolution, Ph. I & II | 60006_01 | Planning | 1.1 | 8 | $1M-$3M
Market | RMS | RO | Performance Measures Reporting | 60007_01 | Not Started | 1.1 | 9 | $1M
Market | RMS | RO | Terms and Conditions Requirements | 60008_01 | Not Started | 1.1 | 10 | $500k
RO Cut Line (Initial placement based on consolidated ERCOT PPL; RO allocation = $6.75M) |  |  |  |  |  |  |  | 
ERCOT | RO | RO | SOA Extend Footprint | 60010_01 | Not Started | 1.1 | 13 | $1M-$3M
ERCOT | RO | IO | Enhance Digital Certificate Program | 60013_01 | Trans. to IO | 1.1 | 17 | $100k-$500k
ERCOT | RO | RO | ESI ID Account Table Split | 60015_01 | Not Started | 1.1 | 23 | $100k-$500k
ERCOT | RO | RO | ERCOT.com Secured Area | 60077_01 | Initiation | 1.1 | 25.5 | $100k-$500k
ERCOT | RO | RO | EDW Siebel Transition | 50059_01 | Initiation | 1.1 | 26 | $500k-$1M
ERCOT | RO | RO | EDW TCH Transition | 50060_01 | Initiation | 1.1 | 27 | $100k-$500k
ERCOT | RO | RO | EDW EAI Transition | 50061_01 | Not Started | 1.1 | 28 | $100k-$500k
ERCOT | RO | RO | ETS Transition to EDW | 50088_01 | Not Started | 1.1 | 29 | $500k-$1M
RO Capability Range (Line placement varies based on Forecasted Spend for Portfolio) |  |  |  |  |  |  |  | 
Market | RMS | RO | Calculation of Losses for Settlement | 60068_01 | Not Started | 1.1 | 32.6 | <$100k
Market | RMS | RO | Mass Customer Transition | 40038_01 | Not started | 1.2 | 54 | $1M-$3M
* Changes noted in this slide are not yet reflected on PPL posted to ERCOT.com as of 4/12/06
RO PPL on ERCOT.com – http://www.ercot.com/services/comm/projects/index.html

## Slide 4: Portfolio Management & Reporting
Revised ERCOT PMO/DPO Procedures to be implemented in May
  Centralized Program Management Office (PMO) focusing on fostering project management excellence through standardized processes, procedures, tools, training and support functions for all ERCOT projects
  Decentralized Divisional Projects Organization (DPO) focusing on accountability and responsibility for business area project portfolio management and delivery
    MO (Commercial/Retail Ops), SO (System Ops), CO (Corp Ops), IO (IT Ops)
DPO accountable & responsible for project scope, schedule, budget; reports through governance process for updates, changes and approvals
Market Services leading effort to identify appropriate external reporting format, delivery mechanism, forums and frequency
  4 different DPOs, interest varies across committees
MO DPO will provide additional information regarding governance process and revisions to organizational, procedural, and reporting processes
  Working with RMS Leadership to finalize agenda/content
  Target May 2006 RMS meeting

## Slide 5
RO Portfolio
  PR 50059_01 EDW Siebel Transition
  PR 50060_01 EDW TCH Transition
  PR 50061_01 EDW EAI Transition
  PR 50088 ETS Transition to EDW
MO Portfolio
  PR 50024_01 SCR 740 Enhancements to SCR 727
  PR 60005_01 EIS Data Marts I
2006 EIS Retail Projects
Notes: <number>
<footer>
<header>
<date/time>

## Slide 6
Priority 1.1, Rank 26
Initial Budget: $500K - $1M
Status: Initiation
Summary
  Build Operational Data Store for Siebel
  Transition of Siebel extracts to EDW
  Position Data Archive components for retirement
Benefit
  Provide a mirrored, very near real-time environment, intended to offset reporting demands and contention
  Integrate with Enterprise information delivery strategic direction
  Net (Cost) / Benefit ($): 448,938 Score: 23
Target Date for Planning = 05/01/2006
PR 50059_01 EDW Siebel Transition
Notes: <number>
<footer>
<header>
<date/time>

## Slide 7
Priority 1.1, Rank 27
Initial Budget: $100K - $500K
Status: Initiation
Summary
  Build Operational Data Store for Transaction Clearinghouse
  Transition TCH extracts to EDW
  Position Data Archive components for retirement
Benefit
  Provide a mirrored, very near real-time environment, intended to offset reporting demands and contention
  Integrate with Enterprise information delivery strategic direction
  Net (Cost) / Benefit ($): 743,338 Score: 23
Target Date for Planning = 05/01/2006
PR 50060_01 EDW TCH Transition
Notes: <number>
<footer>
<header>
<date/time>

## Slide 8
Priority 1.1, Rank 28
Initial Budget: $100 - $500K
Status: Not Started
Summary
  Build Operational Data Store for Paperfree & NAESB
  Transition PF/NAESB extracts to EDW
  Position Data Archive components for retirement
Benefit
  Provide a mirrored, very near real-time environment, intended to offset reporting demands and contention
  Integrate with Enterprise information delivery strategic direction
  Net (Cost) / Benefit ($): 743,338 Score: 23
Target Date for Initiation = late Q2 2006
PR 50061_01 EDW EAI Transition
Notes: <number>
<footer>
<header>
<date/time>

## Slide 9
Priority 1.1, Rank 29
Initial Budget: $500K - $1M
Status: Not Started
Summary
  Build Operational Data Store for ETS
  Transition ETS extracts to EDW
  Position Data Archive components for retirement
Benefit
  Utilize the Conformed Data Warehouse for integrating cross system data in a very near real-time environment, intended to offset reporting demands and contention
  Allows for performance enhanced querying on large data sets
  Integrate with Enterprise information delivery strategic direction
  Net (Cost) / Benefit ($): 1,185,671 Score: 21
Target Date for Initiation = Q4 2006
PR 50088_01 ETS Transition to EDW
Notes: <number>
<footer>
<header>
<date/time>

## Slide 10
Priority 1.0a, Rank .05
Execution Budget: $1,095,000
Status: Execution
Summary
  Provide Market Participants access to SCR 727 ESIID level data in ERCOT systems via Web Services.
Status
  Developing integrated prototypes for Web Services
  Reviewing GUI prototypes and market suggestions from 11/04/2006 market meeting to finalize workflow process
  Finalizing project re-planning effort to incorporate integrated development efforts and EIS delivery 2006 delivery timelines
Milestone Target Dates (re-plan efforts underway)
  ITEST = September 2006
  Production Migration = November 2006
  Market Delivery = December 2006
PR 50024_01 SCR 727 Enhancements (SCR 740)
Notes: <number>
<footer>
<header>
<date/time>

## Slide 11
Priority 1.1, Rank 6
Initial Budget: $500K - $1M
Summary
  Roll out first wave of data marts in the conformed data warehouse environment
  Position Data Archive components for retirement
Benefit
  Utilize the Conformed Data Warehouse for integrating cross system data in a very near real-time environment, intended to offset reporting demands and contention
  Allows for performance enhanced querying on large data sets
  Integrate with Enterprise information delivery strategic direction
  Net (Cost) / Benefit ($): 24,350,470 Score: 25
Target Date for Initiation = Q4 2006
PR 60005_01 EIS CDW Data Marts
Notes: <number>
<footer>
<header>
<date/time>

## Slide 12
Questions?