## Slide 1
Objectives:
Develop a solution to either enhance or replace the FasTrak tool
Scope/Why is this important?:
Increase the transparency for issues that are submitted via FasTrak
Allow users to have improved access to the data
Improve the reporting functionality
Improve search functionality associated
Improve monitoring and response capabilities
Improve the usability
Dependencies:
SOA Integration - dependent on SOA MID project for integration framework components needed by API (low risk to project)
Project Objectives / Scope / Dependencies
PR-50007 Enhancements to FasTrak
As of April 7, 2006
Page 1

## Slide 2: MarkeTrak Budget Revision
Category | Original Estimate | Revised Estimate
Software | $290K | $321K
Hardware | $25K | $55K
Internal Labor | $325K | $643K
External Labor | $510K | $1.23M
Contingency | $400K | $109K
Training | $0 | $17K
Taxes and Interest | $0 | $120K
Total | $1.55M | $2.49M
$861K increase to 2006 budget resulting from completion of Planning phase
Original estimate assumed solution using existing technology platform at ERCOT
  Assumed in-house technology expertise available
  Assumed limited HW requirement
Chosen solution resulted in changes
  Slight increase in final negotiated SW cost
  Additional HW required to implement
  Limited and/or no in-house expertise with Serena SW & TIBCO integration
  Change to internal/external resource mix
Increase to dev & test efforts from final design
  Increase in overall hours to code, integrate, test
  Increase in external resources
    TIBCO integration services, Serena software resources, Testing resources
Page 2
As of April 7, 2006

## Slide 3
Phase:
Initiation – Completed in Feb 2005
Planning – Completed in Nov 2005
Execution/Implementation – Started November 14, 2005
Update:
February 28th sent notice to MPs requesting data on FasTrak Users and Digital Certificates
  ERCOT has received responses from 66 out of 123 DUNS numbers
  Week of April 3rd ERCOT is scheduled to start issuing Digital Certificates to new USA contacts
  Starting on May 1st USA contacts can start requesting additional Digital Certificates for its MarkeTrak users
Summary of Project Status
PR-50007 Enhancements to FasTrak
As of April 7, 2006
Page 3

## Slide 4
Update (cont.):
Digital Certificates cont.
  All users of MarkeTrak (GUI) will require a Digital Certificate
  If a user has an active Digital Certificate then will not require another Digital Certificate
  All Market Participants that wish to use the MarkeTrak API will require a Digital Certificate designated for API
  The issued Digital Certificate will not require a role for MarkeTrak
  MarkeTrak will define a user’s role/responsibilities/permissions
March 23rd MP conference call regarding MP readiness plan – no changes to project schedule
Weekly project conference calls have been moved to Monday’s at 3:30pm
  Call in number is 800-211-0633 Password: 844736
April 4th Attended Market Metrics meeting to discuss MarkeTrak’s reporting capabilities
Summary of Project Status
PR-50007 Enhancements to FasTrak
As of April 7, 2006
Page 4

## Slide 5
** All dates are were derived from ERCOT’s design and planning efforts.
Requirements complete – June 2005
Market Design Document published – November 30, 2005
Detailed Design Document published – January 31, 2006
Market Test Scripts:
  April 5th meeting - reviewed the market test scripts written by market participants
  MPs requested to review scripts at the product demo on Tuesday, April 11th
  Script Sub-team will hold weekly conference calls starting late the week of 4/10
  Next Script Sub-Team meeting will be the first week of May
  MPs are continuing to complete writing of scripts
  After the scripts are complete, the script load will be balanced over the two week MP testing period (5/22 – 6/2)
Project Timeline
PR-50007 Enhancements to FasTrak
As of April 7, 2006
Page 5

## Slide 6
** All dates are were derived from ERCOT’s design and planning efforts.
Market Testing – May 22nd – June 2nd
  API testing is only required if you plan on using it
  GUI testing is voluntary – contact Susan Munson (smunson@ercot.com) to volunteer
Market Participant product Demo – Scheduled for April 11th from 9:30am – Noon in room 168
ERCOT Testing – April 17th – May 19th
Project Timeline
PR-50007 Enhancements to FasTrak
As of April 7, 2006
Page 6

## Slide 7
** All dates are were derived from ERCOT’s design and planning efforts.
Market Training
  Houston training is May 2-5 at Centerpoint
  Dallas training is May 9-12 at TXU
  Austin training is May 15th at ERCOT Taylor
  All training sessions will run from 9:00am to 3:30pm
  Individuals only need to attend one session
  Each session in Houston and Dallas is limited to 24 individuals
  Austin session at ERCOT Taylor is limited to 20 individuals
Project Timeline
PR-50007 Enhancements to FasTrak
As of April 7, 2006
Page 7

## Slide 8
** All dates are were derived from ERCOT’s design and planning efforts.
Final User Guides – June 13th
Tool Cutover Plan:
  Last day to submit new issues in old tool – June 16th
  After June 16th, all new issues submitted in new tool
  Data from old tool will not be converted to new tool
  Cutover plans will be finalized prior to May 22nd
Production (‘go live’ with GUI & API) – June 17, 2006
Project Timeline
PR-50007 Enhancements to FasTrak
As of April 7, 2006
Page 8

## Slide 9
Project Timeline
PR-50007 Enhancements to FasTrak
As of April 7, 2006
Page 9
February 2006
March 2006
April 2006
May 2006
June 2006
Develop Market Test Scripts
ERCOT iTest
MP Training
Market Testing
MP Product Demo
Final User Guides
Go Live on
New Tool

## Slide 10
Bus Lead: Scott Egger
phone number: 512-248-3162
e-mail: segger@ercot.com
PPL: Source: Market Priority: 1.1 Rank: 9 Program Area: RO
What prompted the project:
  SCR 732
  SCR 738
Supporting business drivers:
  Practical usage feedback
Additional Information
PR-50007 Enhancements to FasTrak
As of April 7, 2006
Page 10