## Slide 1: Market Redesign Update
ERCOT Board of Directors Meeting
April 18, 2006
Ron Hinsley
Chief Information Officer
rhinsley@ERCOT.com

## Slide 2: Key points
Predicted program completion date of 7/1/2009
  Much effort has gone into the time line
  High confidence in this projection based on known factors
  Based on critical path review of each work package
  Assumption sets clearly defined and understood
  Meets the needs of transition plan requirements
Next forecast will review and solidify time line
  Vendor discussions
    RFPs will be returned and reviewed (starting Mid-May)
    Vendor awards in June
    Discuss with vendors how time line can be shortened
  Work with Market Participants
    What can be changed in assumption set?
    Are there trade-offs?
ERCOT recognizes the importance of a firm, achievable date
  Market Participants need a firm date to plan business activity accordingly
  Benefits of Nodal are well-documented and the new market is essential as soon as possible
  We are all in this together and need to make it work

## Slide 3: Program Charter
Scope
  Design and implement the nodal market system and transition from the current zonal market to the nodal market as defined by the Protocols approved by the PUCT on April 5, 2006.
  Specific exclusions are those items not yet embodied in the Protocols (e.g. Real Time Co-optimization) that have a material impact on the scope, time and cost of the program.
Objectives
  ERCOT is charged with delivering the capability to:
    Directly assign congestion costs
    Increase transparency of energy prices
    Increase reliability and market efficiency
  By:
    Computing LMPs for 100% of settlement points, 100% of the time
    Moving from portfolio-based dispatch to resource-specific dispatch
    Running and settling the Nodal markets to comply with 100% of the protocol requirements as measured by the accuracy of the calculations and compliance with prescribed operational timeline
  While achieving agreed program targets of:
    Zonal market continuity as measured by adherence to existing target levels
    Timeliness as measured by achievement of key program milestones
    Budget as measured by achievement of budget goals

## Slide 4: Spending Update
O&M(1)
  Internal labor $698K
  Equipment, tools, supplies $ 2K
  Outside services $121K
  Facilities and Utilities $ 36K
  Employee expenses $ 9K
  Interest and fees $ 5K
  Total O&M: $871K
Capital
  Total Capital $149K
Total spending through March $1,020K
(1) – Final values. Status report shows preliminary figures

## Slide 5: Early Milestones
Program charter complete – April 14
Critical RFPs issued – April 14
RFP responses received – May 10
Overall business and IT architecture plan approved – May 15
Update budget forecast – May 15
Vendors selected – June 7
Vendors on board and begin work – June 30
Project-based RUP phase gates – July 1

## Slide 6: Program time line
2006
RFP’s sent 4/14
RFP responses 5/10
2007
2008
2009
EMS
Net Model Mgmt sys.
Zonal Gensys Operational
Market Mgmt. sys.
SCED
Design (conceptual/detail)
Build
Factory acceptance test
System acceptance test
Outage Scheduler
CRR
Commercial Systems
Market Information Systems (SCED)
Electronic Data Warehouse
ERCOT and MP readiness
Early Delivery Systems
Mini-Market Credit Monitoring
Non-binding settlements
Financial transfer
Stabilization period Qualification blackout
TXMACS 0.3
TXMACS
0.4
TXMACS
0.5
TXMACS
1.0
(Live)
Market Trials
Pilot (168 hr test)
NMMS User Interface and business processes
UI in
Prod
MIS (EMS/MMS/CRR)
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4
Q1
Q2
Q3
Q4

## Slide 7: Early Delivery System Sequence
2006
2007
2008
2009
EDS 1
Demonstrate current
State Estimator
Model meets
Nodal criteria
EDS 2 and 3 enablers
EMS upgrade
Network security analysis
Topology consistency analyzer
Forced outage detection
SCED
15 minute point price calcs
Outage scheduler
LFC
Load/RPP forecasting NMMS CIM
Model functionality
Transmission constraints manager
8X5 support
EDS 4 enablers
DAM
RUC
CRR auction
SASM
EMS/MMS interface
OTS
Settlement &
Billing
8X5 support
ERCOT and MP
Readiness criteria
Approved
EDW and MIS
components
EDS 5 enablers
NMMS UI in prod
Training complete
EDW & MIS
Components
24X7 support
Final configuration
Nice to have:
Credit monitoring
Financial transfer
(CRR)
EDS 6 enablers
Final EDW and MIS
Components
Credit monitoring
Financial transfer
Production
Environment
NMMS in prod
90 days in advance
Outage scheduler
In prod 45 days
In advance
EDS 3 outcomes
6 month SCED test done
SCADA and ICCP
Enhancement complete
MP offers
Publish LMPs
LFC, OS, RPP complete
EDS 4 outcomes
All MP registration done
OTS complete
All market-facing interfaces
Testing of all markets done
EDS 5 outcomes
168 hour test complete
MP financial and operational
qualifications complete
Readiness declarations met
Interfaces validates
CM, FT complete
Training complete
Major deliverables
TXMACS 0.3
TXMACS 0.4
TXMACS 0.5

## Slide 8: KEMA comparison
KEMA time line covers October 2005 to April 2009 Go-live
ERCOT Time line covers December 2005 to July 2009 Go-live

## Slide 9: Requests for Proposals
Eleven work packages have been identified
  External bid
    Market operations
      Day Ahead Market
      Supplemental ancillary service market
      Reliability unit commitment
      Real time market
      Emergency operations enhancements
      Price correction
      Administration and mitigation
      Asset registration interfaces
      EMS/MMS interfaces
    Congestion Revenue Rights
    Financial Transfer
    Credit Monitoring
    Outage Scheduling
    Load forecasting
    Network Model and Telemetry
  Internal deliverables
    Registration
    Settlements and billing
    Infrastructure
  Request for Information
    Network Model Management System

## Slide 10: Assumptions for success
State Estimator meets necessary criteria
Zonal PRRs – discussion on appropriate limitations needs to start – Date TBD
SCED work can start as soon as possible
Vendor selection to be completed by Mid-June
Vendors will share detail designs with other vendors
TDSP’s will enter data in new NMMS and GENSYS
  ERCOT will have enough staff to handle this work
ERCOT will deploy COGNOS and SAS to PUCT
Six months integration testing will be required
TPTF will review requirements and conceptual design documents when produced

## Slide 11: Progress Reporting
Monthly Board reports
  Program progress
  Deliverables
  Near-term deliverables
  Monthly spending reviews
  Monthly staffing forecasts
Quarterly spending forecasts
Periodic external program reviews
  Program assessment
  Time-line review
  Spending review
  Staffing effectiveness
  Vendor reviews