| PRR Number | 660 | PRR Title | Texas SET Transactional Solution for a Mass Transition Event |
| --- | --- | --- | --- |
| Impact Analysis Date |  | 04/25/2006 |  |
| Credit Impacts |  | YES _______ NO ______ If No, skip the next two boxes. |  |
| Has the Credit Workgroup reviewed the PRR? |  | YES _______ NO ______ |  |
| Outcome of Credit Workgroup review |  |  |  |
| Cost/Budgetary Impact |  | $3M - $5M |  |
| Estimated Project Time Requirements* *Unless otherwise indicated, project time requirements begin upon project initiation. |  | 11-14 Months from the date of initiation - Initiation – 1 week - Planning – 4 months - Development and Unit Test – 2.25 months - Integration and User Acceptance Testing – 2 months - Flight Testing – none - Implementation – 2 months - Contingency – 3 months |  |
| ERCOT Staffing Impacts (across all areas) |  | No long term staffing impacts identified at this time. |  |
| ERCOT Computer System Impacts |  | Implementation of this logic in the ERCOT system would be equivalent to a major Texas SET release. Modified Texas SET transaction types would be implemented on the new EIF (Enterprise Integration Framework), TIBCO. The following systems would be impacted: - Siebel - Paperfree - TIBCO - ETS (ESI ID Tracking System) - TML (Texas Market Link) |  |
| ERCOT Business Function Impacts |  | There is a potential, depending on design, for a new retail business process type. |  |
| Grid Operations & Practices Impacts |  | None. |  |

Alternatives for a More Efficient Implementation (include explanation of impacts)

None.

Evaluation of Interim Solutions (e.g., manual workarounds)

The current interim solution is manual performance of system updates and monitoring required to transfer ESI IDs from one Competitive Retailer (CR) to another CR.

Feasibility of Implementation

Resource availability Project work for PRR660 has the potential to impact resources on the following projects: - PR-50121_07 – Retail Business Processes - PR-60015 – ESI ID Account Table Split - PR-50088 – ETS Transition to EDW (Enterprise Data Warehouse) - PR-60007 – Performance Measures Reporting Requirements - PR-60008 – Terms & Conditions Requirements, Not Limited to TX SET Changes - PR-60010 – SOA (Service Oriented Architecture) Extend Footprint - PR-50059 - EDW Siebel Transition - PR-50060 – EDW TCH (Transaction Clearing House) Transition - PR-50061 – EDW EAI (Enterprise Application Integration) Transition The Texas Nodal Market effort has the potential to impact project resources for PRR660. Impact to Nodal will be minimized if Mass Transition solution is deployed after completion of PR-50121_07. Impact to other projects Technical dependency on other projects: - There is a technical code dependency on PR- 50121_07 Retail Business Processes project. Modified TX SET transaction types would have to be implemented on the new EIF, TIBCO, which will be implemented with PR-50121_07. Changes to the Retail Transactions applications in support of the TIBCO framework are currently in progress and not scheduled to be implemented until October 2006. - There is a potential dependency on PR-50059 – EDW Siebel Transition, PR-50060 – EDW TCH Transition and PR-50061- EDW EAI Transition, to be confirmed during project planning for PRR660.

Comments

Modifications to ERCOT systems will be developed as a full, not phased, solution.