## Slide 1: EIS Projects Update COPS Meeting
Adam D. Martinez
Mgr, Market Ops Divisional Projects Organization
ERCOT
April 28, 2006

## Slide 2
CART | Project # | Project Name
Active Projects as of Today |  | 
MO | PR 30026 | EPS Meter Data Extract/Resource ID Extract
MO | PR 40042_06 | Lodestar Batch Extracts
MO | PR 40007 | SCR727 Phase II
RO | PR 50059_01 | EDW Siebel Transition
RO | PR 50060_01 | EDW TCH Transition
MO | PR 50024_01 | SCR 740 Enhancements to SCR 727
MO | PR 50030 | Lodestar Data Archive Decommission
Future Projects in 2006 |  | 
IO | PR 60004_01 | EIS CDW Foundations
RO | PR 50061_01 | EDW EAI Transition
MO | PR 60005_01 | EIS CDW Data Marts
RO | PR 50088 | ETS Transition to EIS
2006 EIS MO & RO Projects

## Slide 3
MO CART
  Priority 1.0b, Rank – .54
Baseline Budget
  $104,000
Description
  PRR283 / PIP204
  Provides Resource ID data to Market Participant owners
Status
  Execution Phase
  Testing in ITEST
Milestone Dates
  Production Migration on 06/01/2006
  Market Delivery on 06/22/2006
PR 30026 EPS Meter Data/Resource ID Extract
Notes: <number>
<footer>
<header>
<date/time>

## Slide 4
MO CART
  Priority 1.0a, Rank – .18
Baseline Budget
  $479,055
Description
  Transitions Lodestar Batch Extracts from the Data Archive to the Lodestar ODS environment
Status
  Execution Phase
  Testing in PTEST
Milestone Dates
  ERCOT UAT (ITEST) on 07/25/2006
  Production Migration on 09/21/2006
  Market Delivery on 10/2006 (exact date TBD)
PR 40042_06 Lodestar Batch Extracts
Notes: <number>
<footer>
<header>
<date/time>

## Slide 5
MO CART
  Priority 1.0b, Rank – .71
Baseline Budget
  $389,348
Description
  Transitions SCR 727 Extract from the Data Archive to the Lodestar ODS environment
Status
  Execution Phase
  Currently on-hold until PR 40042_06 Lodestar Batch Extracts enters ITEST for resource management purposes
Milestone Dates
  ERCOT UAT (ITEST) on 09/26/2006
  Production Migration on 11/16/2006
  Market Delivery on 12/2006 (exact date TBD)
PR 40007 SCR 727 Phase II
Notes: <number>
<footer>
<header>
<date/time>

## Slide 6
RO CART
  Priority 1.1, Rank – 26
Initial Budget
  $500K-$1MM
Description
  Builds relevant ODS Siebel infrastructure, then transitions extracts
  Positions Data Archive components for retirement
  Benefits
    Provides a mirrored, very near real-time environment, intended to offset reporting demands and contention
    Integrates with Enterprise information delivery strategic direction
    Net (Cost) / Benefit ($): 448,938 Score: 23
Status
  Initiation Phase
Milestone Dates
  Planning Start on 05/01/2006
PR 50059_01 EDW Siebel Transition
Notes: <number>
<footer>
<header>
<date/time>

## Slide 7
RO CART
  Priority 1.1, Rank – 27
Initial Budget
  $100K-$500K
Description
  Builds relevant ODS Transaction Clearinghouse infrastructure, then transitions extracts
  Position Data Archive components for retirement
  Benefits
    Provides a mirrored, very near real-time environment, intended to offset reporting demands and contention
    Integrates with Enterprise information delivery strategic direction
    Net (Cost) / Benefit ($): 743,338 Score: 23
Status
  Initiation Phase
Milestone Dates
  Planning Start on 05/01/2006
PR 50060_01 EDW TCH Transition
Notes: <number>
<footer>
<header>
<date/time>

## Slide 8
MO CART
  Priority 1.0a, Rank – .05
Baseline Budget
  $1,095,000
Description
  SCR 740; provides Market Participants access to SCR 727 ESIID level data in ERCOT systems via Web Services
  PR 50024_02 & PR 50024_03 are additional sub-projects to deliver and implement the necessary hardware required by this project.
Status
  Execution Phase
  Developing integrated prototypes for Web Services
  Reviewing GUI prototypes and market suggestions from 11/04/2005 market meeting to finalize workflow process
  Finalizing project re-planning effort to incorporate integrated development efforts and EIS delivery 2006 delivery timelines
Milestone Dates
  Test Start (ITEST) on 09/26/2006
  Production Migration on 11/16/2006
  Market Delivery on 12/2006 (exact date TBD)
PR 50024_01 SCR 727 Enhancements (SCR 740)
Notes: <number>
<footer>
<header>
<date/time>

## Slide 9
MO CART
  Priority 1.1, Rank – 44
Initial Budget
  $100-$500K
Description
  Transitions Lodestar Data Archive extracts and business users to Lodestar ODS environment
  Retires Lodestar Data Archive components
Status
  Planning Phase (On Hold)
Milestone Dates
  Planning re-engagement on 05/01/2006
PR 50030 Lodestar Data Archive Decommission
Notes: <number>
<footer>
<header>
<date/time>

## Slide 10
IO CART
  Priority 1.1, Rank – 5
Initial Budget
  $1MM-$3MM
Description
  Rolls out architecture & framework for next generation DW env.
  Directly supports Section 17 of the Protocols and is a required element to support the PUCT and the Market
  Positions Data Archive components for retirement
  Benefits
    Provides a Conformed Data Warehouse integrating cross system data in a very near real-time environment, intended to offset reporting demands and contention
    Allows for establishing Data Marts
    Integrates with Enterprise information delivery strategic direction
    Net (Cost) / Benefit ($): 48,620,154 Score: 29
Status
  Initiation Phase
Milestone Dates
  Initiated in 04/2006
PR 60004_01 EIS CDW Foundations
Notes: <number>
<footer>
<header>
<date/time>

## Slide 11
RO CART
  Priority 1.1, Rank – 28
Initial Budget
  $100K-$500K
Description
  Builds relevant ODS Paperfree and NAESB infrastructure, then transitions extracts
  Positions Data Archive components for retirement
  Benefits
    Provides a mirrored, very near real-time environment, intended to offset reporting demands and contention
    Integrates with Enterprise information delivery strategic direction
    Net (Cost) / Benefit ($): 743,338 Score: 23
Status
  Not Started
Milestone Dates
  Planned for initiation in late 06/2006
PR 50061_01 EDW EAI Transition
Notes: <number>
<footer>
<header>
<date/time>

## Slide 12
MO CART
  Priority 1.1, Rank – 6
Initial Budget
  $500K-$1MM
Description
  Rolls out first wave of data marts in the next generation data warehouse environment
  Positions Data Archive components for retirement
  Benefits
    Utilizes the Conformed Data Warehouse for integrating cross system data in a very near real-time environment, intended to offset reporting demands and contention
    Allows for performance enhanced querying on large data sets
    Integrates with Enterprise information delivery strategic direction
    Net (Cost) / Benefit ($): 24,350,470 Score: 25
Status
  Not Started
Milestone Dates
  Planned for initiation in Q4 2006
PR 60005_01 EIS CDW Data Marts
Notes: <number>
<footer>
<header>
<date/time>

## Slide 13
RO CART
  Priority 1.1, Rank – 29
Initial Budget
  $500K-$1MM
Description
  Transitions ETS reporting to Enterprise Data Warehouse
  Positions Data Archive components for retirement
  Benefits
    Utilizes the Conformed Data Warehouse for integrating cross system data in a very near real-time environment, intended to offset reporting demands and contention
    Allows for performance enhanced querying on large data sets
    Integrates with Enterprise information delivery strategic direction
    Net (Cost) / Benefit ($): 1,185,671 Score: 21
Status
  Not started
Milestone Dates
  Planned for initiation in Q4 2006
PR 50088_01 ETS Transition to EDW
Notes: <number>
<footer>
<header>
<date/time>

## Slide 14
Questions?
Contact Information
Adam D. Martinez
Mgr, Market Operations Divisional Projects Organization
ERCOT
(512) 248-3883
amartinez@ercot.com
Notes: <number>
<footer>
<header>
<date/time>