## Slide 1
Program Charter | Texas Nodal |  | 
Project Number | NP-60C00_01 | Charter Date | April 27th, 2006
Program Sponsor | Ron Hinsley | Program Director | Kathy Hager
Program Scope | Design and implement the nodal market system and transition from the current zonal market to the nodal market by <date not certain> as defined in the Protocols approved in the Order signed by the PUCT on April 5th, 2006. Specific exclusions are those items not yet embodied in the Protocols (e.g. Real Time Co-optimization) that have a material impact on the scope, time and cost of the program. |  | 
Objectives | ERCOT is charged with delivering the capability to: Directly assign congestion costs Increase transparency of energy prices Enhance reliability and increase market efficiency (CHANGED - TPTF) By Computing LMPs for 100% of settlement points, 100% of the time Moving from portfolio based dispatch to resource-specific dispatch Running and settling the Nodal markets to comply with 100% of the Nodal protocol requirements as measured by the accuracy of calculations and compliance with prescribed operational timelines Creating a CRR market to adequately hedge the directly assigned congestion charges/credits (ADDED - TPTF) While achieving agreed Program Targets of: Zonal Market continuity – as measured by adherence to existing target levels of availability Customer satisfaction – as measured by surveys of Market Participant and internal satisfaction of the Program and constituent projects (ADDED – Steering Board) Timeliness – as measured by achievement of key Program milestones Budget – as measured by achievement of budget goals |  | 
Current Zonal market characteristics |  | Nodal Market Characteristics | 
Transmission Congestion Rights (flowgates) |  | Congestion Revenue Rights (PTP Options, Obligations, Flowgates) | 
No Day-Ahead Energy Market Ancillary Services Market Day-Ahead |  | Day-Ahead Energy and Ancillary Services Co-optimized Market | 
Replacement Reserve Service (RPRS) / OOMC (CHANGED - TPTF) |  | Daily Reliability Unit Commitment (DRUC) | 
Hour Ahead Studies |  | Hourly Reliability Unit Commitment (HRUC) | 
Portfolio based offers by Zone (ADDED - TPTF) |  | Resource specific offers (ADDED - TPTF) | 
Balancing Energy Service every 15 minutes Zonal by portfolio for CSCs Resource Specific for Local (CHANGED - TPTF) |  | Security Constrained Economic Dispatch typically every 5 minutes (still 15 minute settlement) (CHANGED - TPTF) All Resource Specific (CHANGED - TPTF) Enhanced Load Frequency Control (ADDED - TPTF) | 
Zonal Average Shift Factors for Resources |  | Actual Shift Factors for Resources | 
Zonal Market Clearing Price for Balancing Energy for Generation and Loads |  | Nodal Locational Marginal Prices (LMP) for Generation Zonal weighted LMPs for Loads | 

## Slide 2
Program Charter | Texas Nodal | 
Deliverables | The going-in position on high-level components is as follows. Processes: Integration testing – substantial replacement (100% new) Training – education and training for ERCOT Staff and Operators, and Market Participants (100% new) (CHANGED - TPTF) Market Participant readiness – communication, impact assessment, Readiness Criteria, development and testing (100% new) ERCOT, Inc readiness – communication, impact assessment, business process change (all Markets), organizational preparation and testing (100% new) Market Trials – preparation, execution and Readiness Declaration (100% new) Transition to live operations – cut-over & business continuity (100%) Systems: Registration System – minor enhancements (<10% functionality) Network Model Management System (NMMS) – replacement of Genesys (100% replacement plus significant additional functionality) Energy Management System (EMS) – substantial upgrades and enhancements (>50% of functionality, 100% technology refresh) (CHANGED - TPTF) Market Management System (MMS) – replacement (100% replacement) Congestion Revenue Rights (CRR) – new (100% new) Market Information System (MIS) – new (100% new) (ADDED - TPTF) Commercial Systems (Settlements and Billing) – substantial upgrades and enhancements (>50% of functionality) Monitoring applications for Credit, Market & Compliance – substantial upgrades and enhancements (>50% of functionality) Reporting/Analysis (Enterprise Data warehouse/Enterprise Information Services) – substantial upgrades and enhancements (>50% of functionality) Interfaces within ERCOT, and external Interfaces between ERCOT and participants – substantial enhancements (>50%) Infrastructure – substantial enhancements (>50%) | 
Key Risks |  | Risk Mitigation Strategy
Ineffective engagement, mobilization of the organization |  | Visible leadership from the Executives down. Demonstration of the “right” behaviors through rapid decision-making, communication, signals to the organization.
Delays & rework due to complexity |  | Focus on architecture, early design, development of critical components, quality assurance, phased integration releases and testing, proactive communication and interaction with the selected vendors.
Poor integration |  | Focus on architecture, early interface definition, integrated project planning. Significant testing will happen frequently and as early in the process as practical. Additionally, testing will be considered throughout the program design. External auditors will be appointed to certify, periodically, the validity of Program Management Plans and accuracy of status reports. (CHANGED – Steering Board)
Ineffective engagement of, response from, market participants |  | Program Director and TPTF Chairman will take active steps to set mutual expectations and commitments, provide timely and appropriate information, in person meetings will be followed with detailed documentation; the program will actively follow up with the TPTF for responses, ensure mutual progress is highly visible, and escalate as needed.
Zonal v. Nodal |  | Zonal projects will compete with the Nodal program for resources and focus, ERCOT Executives will be expected to make a commitment to the Nodal program. Additionally, the PUCT & TAC will be requested to rationalize and minimize Zonal PRRs. (CHANGED - TPTF)
Scope creep |  | If an activity is not necessary for the transition to, and implementation of, nodal protocols, it will be considered out of the program scope and must be negotiated with the Program Director and, if required, the Steering Board. (CHANGED - TPTF)
Staff morale, turn-over and motivation |  | Job satisfaction and morale are based more on a sense of accomplishment, fairness and belonging. The program will challenge team members as much as possible and define work in achievable chunks. The program will also recognize accomplishments and superior achievement.
Core team capability |  | Begin selecting the team that can move the program forward from its early stages. Selection of ‘super’ PMs – with project delivery accountability & authority – will be the highest staffing priority. Then we can re-introduce the rest of the organization under a more positive model and staffing plan.
Key resource bottlenecks |  | The bottlenecks with key resources will be identified and their focus will be managed to minimize impact at critical times.
Software immaturity |  | Implementation of “green” software – applications, infrastructure and tools – inevitably leads to substantial defects. The program will use test systems to implement green software as early as possible. When LMPs are calculated for settlement purposes, the program will limit development and deployment of unproven software as a matter of policy. (CHANGED - TPTF)

## Slide 3
Program Charter | Texas Nodal
Key Milestones | The master schedule and critical path are being defined, early critical milestones are shaping up: Program Charter complete - April 14, 2006 Program Charter signed off – April 25, 2006 Critical path RFPs issued – April 14, 2006 Minimize and rationalize Zonal PRRs – June 1, 2006 (CHANGED - TPTF) Overall business and IT architecture (top level) approved – May 15, 2006 Vendors selected – June 7, 2006 Vendors on board and begin work – June 30, 2006 Project-based RUP phase gates established – July 1, 2006
Planning hierarchy | 
Approach | Key elements of the required approach are clear: This Charter establishes the Program scope, schedule and budget baseline – any changes will be subject to formal change control. The management of the program will follow the Rational Unified Process (RUP) Methodology of iterative development. All critical documentation will go through a quality assurance process comprising Project- and independent Program-level assurance. The resource model envisages a lean core team (including “super” Project Managers and assurance functions) – ‘contracting’ with internal and external providers for deliverables (rather than resources). RFPs will be expedited – detailed requirements will be developed together with vendors for critical applications. Project approval will be by phase – passage through each phase gate will require a detailed estimate for the subsequent phase, together with an estimate to complete the entire project (Estimate At Completion – EAC). Project work breakdown for the impending phase will require definition and assignment of 40 hour deliverables for each resource Engagement with Market Participants will comply with the requirements of the ERCOT Nodal Transition Plan (dated November 3, 2005) Projects will be subject to periodic critical examination and health-checks

## Slide 4
Program Charter | Texas Nodal
Organizational model | 
Core Program Organization | 
Note – this is a simplified diagram:
Projects will deliver in accordance with the Release Strategy – and will provide support for existing releases as they prepare for subsequent releases.
Business & IT Operations will have substantial involvement prior to “go Live” in readiness preparations, business trials etc and will, for example, provide support for Early Delivery Systems (EDS) as they are established.
Implications
  Those with delivery accountability are core Program Team members.
  Each needs to produce a Charter, including team & resource requirements.

## Slide 5
Program Charter | Texas Nodal
Budget | The budget process envisions at least 3 cycles leading to the PUCT cost recovery plan Initial submission – Mid March Detailed Work-Product Plan – +2 months Post-Procurement Strategy – +3 months
Resourcing and facilities | 
Next Steps | This Program Charter will be expanded into a broader Program Management Plan (the “how” at a program level). Additionally, the Program Charter is intended to be a requirements document for the more detailed Project Charters and detailed plans to follow.

## Slide 6
Program Charter |  | Texas Nodal
 | The release strategy and critical path are built around the Early Delivery System sequence agreed with TPTF | 

## Slide 7
Program Charter |  | Texas Nodal
 | Going-in critical path analysis – 1/1/09 is not feasible. This revised timeline is unconstrained and needs validating through resourced project schedules. | 
Note
Over the next few weeks we will be reviewing the schedule to ensure it is based on correct assumptions. ERCOT will also ask for legal advice concerning the implementation date the PUCT established in the protocols order and whether a motion for a rehearing of that order should be filed. ERCOT estimates this review will be completed by June 30.

## Slide 8
Program Charter | Texas Nodal | 
Approver(s) |  | Signature attests that the Charter is an accurate and true reflection of the program requirements at the current level of definition.
Kathy Hager (Program Director) |  | 
Approver(s) |  | Signature attests that the Charter has been reviewed and approved from the signatory’s perspective.
Ron Hinsley (Program Sponsor) |  | 
Tom Schrader |  | 
Steve Byone |  | 
Sam Jones |  | 
Ray Giuliani |  | 
Carolyn Shellman |  | 
Pam Fisher |  |