## Slide 1: Budget Impacts of MarkeTrak TAC Meeting
4/07/05 Adam Martinez, MO Divisional Projects Organization

## Slide 2: MarkeTrak Budget Revision
Category | Original Estimate | Revised Estimate
Software | $290K | $321K
Hardware | $25K | $55K
Internal Labor | $325K | $643K
External Labor | $510K | $1.23M
Contingency | $400K | $109K
Training | $0 | $17K
Taxes and Interest | $0 | $120K
Total | $1.55M | $2.49M
$861K increase to 2006 budget resulting from completion of Planning phase
Original estimate assumed solution using existing technology platform at ERCOT
  Assumed in-house technology expertise available
  Assumed limited HW requirement
Chosen solution resulted in changes
  Slight increase in final negotiated SW cost
  Additional HW required to implement
  Limited and/or no in-house expertise with Serena SW & TIBCO integration
  Change to internal/external resource mix
Increase to dev & test efforts from final design
  Increase in overall hours to code, integrate, test
  Increase in external resources
    TIBCO integration services, Serena software resources, Testing resources
Notes: <number>
<footer>
<header>
<date/time>

## Slide 3: Impacts to RO Project Portfolio
2006 RO approved budget = 6.75M; est. budget for projects above “cut line” = $4.8M
Projects above “cut line”
  No impact to projects above the “cut line”
  Market has $1.5M available for 2 projects not yet initiated
    Performance Measures Reporting Requirements
    Terms and Conditions Requirements
Projects below “cut line,” within “capability”
  ERCOT initiates projects in rank order, unless constraints prevent initiation
    SOA Extend Footprint – environment & resource constraint with Retail Business Processes (RBP) project
    Enhancements to Digital Certificates – transferred to IO portfolio, initiating
    ESI ID Account Table Split – resource constraint with RBP Project
  ERCOT.com Secured Area project – continuing with Initiation phase
  EDW transition projects – initiating next week
DPO monitors financials, reports through governance process for changes and approvals
If forecasted CART portfolio budget exceeds approved amount
  CART may vote to “hold” a project in order to release funds to other initiatives
  CART may request budget increase funds released by other CARTS
  ERCOT may initiate request to BoD for increased capital project budget
RO PPL on ERCOT.com – http://www.ercot.com/services/comm/projects/index.html

## Slide 4
Questions?