## Slide 1: RMS Update to TAC
April 7, 2006

## Slide 2
RMS Voting Items
RMGRR032- Transaction Timing Matrix Corrections
  Includes updates to Appendix D to correct examples for Move In, Drop to AREP, Permit , Historical Usage, Final Usage transactions
Unanimously approved at RMS

## Slide 3
RMS Voting Items
RMGRR033- Process for Retail Market Guide Revisions
  Impact Analysis
  Board Approval of Project Priority
  Processes to withdraw, reject, appeal an RMGRR
  Administrative revisions by ERCOT Staff
Approved at RMS with two abstentions from Generator segment

## Slide 4
RMS Voting Items
RMS Procedures Revisions Include
  Updated references to Retail Documents
  Added references to approval process at PRS, TAC and the BOD
  Removed references to Profile Working Group
  Updated details on the Subcommittee Responsibilities
  References to standing Working Groups and materials requiring RMS approval.
Approved at RMS with one abstention from Consumer segment

## Slide 5: Mass Transition Update
TX SET reviewed Long Term solution for phased approach as directed by TAC
Phase I Changes
  ERCOT initiating switch transaction as Next Retail Business Day instead of POLR with FASD
  New code in the existing switch transaction identifying Mass Transition ESI IDs
  Requires system changes for CRs who do not currently accept a drop transaction today
Phase I Assumptions
  Assumes customer information will be provided from defaulting REP under current market process
  Leverage existing transactions and current Protocol timing
  All pending transaction exceptions will be handled under current process

## Slide 6: Mass Transition Update
Phase II changes
  Defines processes and business rules to address pending transactions for 56 scenarios
  Additional codes to specifically identify rejected or unexecuteable conditions.
Phase II Assumptions
  Assumes customer information will be provided from defaulting REP under current market process

## Slide 7: Mass Transition- Phase I Timeline Protocol
Day 0
Day 1
Day 6
Customer transition should be completed in 3 Business Days
Customer transition in progress
ERCOT Announces Mass Transition and Performs ESI ID sync with TDSPs
TDSP ESI ID Verification Completed
ERCOT generates Mass Transition Drop transactions for requesting off cycle read for next business day
Day 2
Day 3
Day 4
TDSP sends response to drop transaction with meter read date
ERCOT forwards Drop transaction and Historical Usage to POLR
Day 5
Completed meter read transactions are sent to ERCOT
ERCOT receives meter reads completing Mass Transition
Day 10
Effective Date of Meter Read

## Slide 8: Mass Transition- Phase I Timeline Actual
Day 0
Day 1
Day 6
Customer transition should be completed in 3 Business Days
Customer transition in progress
ERCOT Announces Mass Transition and Performs ESI ID sync with TDSPs
TDSP ESI ID Verification Completed
ERCOT generates Mass Transition Drop transactions for requesting off cycle read for next business day
Day 2
Day 3
Day 4
TDSP sends response to drop transaction with meter read date
ERCOT forwards Drop transaction and Historical Usage to POLR
Day 5
Completed meter read transactions are sent to ERCOT
ERCOT receives meter reads completing Mass Transition
Day 10
Effective Date of Meter Read

## Slide 9: Market Participant Implementation Schedules
        Phase I Full
        POLR CRs
        Constellation Energy 12-2006
        Direct Energy 12-2006 12-2006
        Gexa Energy Q1 2007
        Reliant Energy Will Support Market Majority
        Non POLR CRs
        Accent Energy 12-2006
        Cirro Energy 12-2006 12-2006
        Commerce Energy 12-2006
        First Choice Q2 2007
        Green Mountain 12-2006
        STEC 12-2006
        TXU Energy 12-2006 10-2007
        TDSPs
        AEP 12-2006 10-2007
        CNP 12-2006 10-2007
        TNMP Q1 2007
        TXU ED 12-2006 10-2007
        ERCOT 3-31-2007

## Slide 10: Market Participant Implementation Schedules
ERCOT Schedule Details
Board Approval - 5/16/06 Project Initiation - 5/22/06 Beginning of Planning Phase - 6/5/06 Business Requirements Development - 6/5/06 to 7/17/06 Business Requirements Sign-off - 7/17/24 to 7/24/06 Conceptual Design Development - 7/24/06 to 8/7/06 Detail Design Development - 8/07/06 to 9/18/06 Detail Design Sign-off - 9/18/06 to 10/02/06 Build / Unit and Product Testing - 10/02/06 to 12/11/06 Integration and User Acceptance Testing - 12/11/06 to 2/5/07 Flight - End of flight 0107 as defined by TTPT Best implementation date - 3/31/07

## Slide 11: Mass Transition Next Steps
PRR requesting urgent status submitted to PRS for reprioritizing project
RMGRR will be submitted to RMS for consideration in May

## Slide 12
RMS Update to TAC
Questions?