## Slide 1: 2006 CDR Status Report
Technical Advisory Committee
May 4, 2006
Bill Bojorquez

## Slide 2: Major Assumptions Checklist
Load Forecasts
LAARs
Existing Resources
Mothballed Units
Private Networks
New Generation (with concerns)
In order to adequately prepare the CDR, ERCOT planners must compile the best information available with regards to forecasted load demands and available resources.
To date, ERCOT planners have addressed:
Load Forecasts
Peak Demand
-LARRs
Resource Forecast
Existing
-Retired/Mothballed
+Private
+New
Available Resources
-Firm Load
Reserves
CDR
Firm Load
Available Resources

## Slide 3: New Generation Illustration
The table below contains a partial list of the publicly announced new generation (fossil fuel only) projects compiled by ERCOT staff.
Site Name | Status | County | Region | Fuel | In Service Date | MW into Grid
Cobisa-Greenville | Public Letter | Hunt | North | Gas | May-08 | 1,750
Colorado Bend Energy Center | Interconnect Agreement | Wharton | South | Gas | Dec-06 | 275
Quail Run Energy Center | Interconnect Agreement | Ector | West | Gas | Dec-06 | 275
Limestone Upgrade | Interconnect Agreement | Limestone | North | Coal | May-06 | 110
Big Spring Electricity Generating Facility | Interconnect Agreement | Howard | West | Waste Heat | Apr-06 | 12
Sandow 5 | Public Letter | Milam | North | Coal | Jul-08 | 0
Sandy Creek | Public Letter | McLennan | North | Coal | Jul-09 | 800
J K Spruce 2 | Public Letter | Bexar | South | Coal | Aug-09 | 750
Oak Grove | Public Letter | Robertson | North | Coal | Mar-09 | 1,660
Hugo Plant | Public Letter | Choctaw, OK | North | Coal | Dec-10 | 500
Twin Oaks 3 | Public Letter | Robertson | North | Coal | Jun-11 | 630
 |  |  |  |  | Totals: | 6,762
As shown in the table, only 672 MW of publicly announced capacity has an executed Interconnection Agreement at this time.
Notes: A Public Commitment Letter is needed from the owners of J.K. Spruce and Hugo. Part of the Interconnection Procedures – an official letter from the municipal utility or CoOp will serve as the public commitment.

## Slide 4: Treatment of New Generation in CDR (Example)
Assuming a Firm Peak Demand forecast of 67,000 MW for summer 2011:
  The total list of new fossil resources (6,762 MW) provided in the preceding table represents an incremental reserve margin of 10.1%.
  However, current ERCOT practice is to include only those projects with an executed Interconnection Agreement (672 MW) in the CDR; which in this example represents an incremental reserve margin of only 1.0%.
  Only projects with signed IAs are included in transmission base cases
Use of these two methodologies results in extreme outcomes:
  1.0% 10.1%.

## Slide 5: Next Step
ERCOT System Planning is requesting that TAC assign the GATF to work with ERCOT staff in determining the most appropriate methodology for the treatment of new generation projects in the CDR calculation.

## Slide 6
Questions?