## Slide 1: MarkeTrak Project Update
Adam D. Martinez
Mgr, Market Ops Divisional Projects Organization
ERCOT
RMS Meeting
May 10, 2006

## Slide 2: Project Status Update
April 26th – ERCOT announces schedule delay
  Driven by errors in XSD document for API; no impact to GUI
  ERCOT proposes new schedule with August release
  Market review / input to schedule solicited
Root Cause
  Errors found in XSD (API mapping document to MarkeTrak business processes)
    Impacts select MPs & ERCOT for delivery of Bulk Insert & API functionality
    ERCOT relied on vendor expertise to review quality at time of initial XSD release
  Errors require additional time by ERCOT to complete XSD quality review
  Changes to XSD increase development efforts and delay testing efforts
Impacts to Timeline
  New production release schedule for August 26th
    API development extended into end of May
    API testing cannot complete prior to QA Build Out project lockdown of UAT & Market test environments (June 2 – July 10)
    API testing scheduled after lockdown; subsequent delay to dependent activities
Impacts to Budget
  No budget impact to ERCOT; additional Dev resource needs for UAT support covered with existing budget

## Slide 3: Revised Project Timeline
April
May
June
July
August
QA Build-out Project Lock Down
UAT & Mkt Test Environments unavailable for 5 wks
7/10
Mkt Connectivity Testing
4/28
ERCOT Post of XSD Revision to Mkt
7/17
“Train the Trainer” Sessions Start
(2 wks)
8/11
Final User Guides Avail
7/10
API & Bulk Insert UAT Start
(3 wks)
4/21
GUI UAT Start
(4 wks)
5/5
User Guide Draft (v2) Released
8/18
GUI & API Mkt Test Completes
5/1
Mkt Begins to Submit Requests for Digital Certs
8/26
MarkeTrak Production Release
5/19
GUI UAT Complete
7/31
“Train the Trainer” Sessions Complete
6/1
API & Bulk Insert Migration to UAT Environment
----------
GUI Migration to Mkt Test Environment
5/31
API & Bulk Insert Dev/Unit Test Complete
7/13
API & Bulk Insert Migration to Mkt Test Environment
8/7
GUI & API Mkt Test Start
(2 wks)
5/10
We Are Here – RMS Update
Today
Key ERCOT Dates
Key Market Dates
Production Release Date
API Connectivity
TBD
Legend
8/25
MPs Complete Internal Training

## Slide 4: Training Plan Revision
ERCOT “Train the Trainer” Sessions
  All sessions run from 9:00am to 4:00pm; individuals need to attend only one session
  Houston – 4 sessions
    July 18th – 21st at Centerpoint
    Limited to 24 individuals
  Dallas – 4 sessions
    July 25th – 28th at TXU
    Limited to 24 individuals
  Austin
    July 31st at ERCOT Taylor
    Limited to 20 individuals
Market Participant Internal Training Sessions
  MP “trainers” taught by ERCOT will deliver internal MP training
  Delivery timeframe between July 19th – August 25th

## Slide 5
Prior to Migration Weekend
  Reports of Issues >6 months old
    ERCOT will provide a report to MPs of issues older than 6 months
  Closing Issues >12 months old
    Two weeks prior to product migration ERCOT will close issues greater than 12 months old and make available a report to MPs
Migration Weekend
  Disable Entry of New Issues in FasTrak
    At 4:00pm on Friday prior to implementation (Aug 25th), ERCOT will disable entry of new issues in FasTrak
  In progress Issues in FasTrak
    MPs will have the ability to work in progress issues in FasTrak
MarkeTrak is Operational in Production
  Entry of New Issues
    ERCOT will start accepting new issues into MarkeTrak on Monday at 8:00am CST
As of May 9, 2006
Page 4
FasTrak to MarkeTrak Cut Over Plan
Notes: <number>
<footer>
<header>
<date/time>

## Slide 6
FasTrak Data
  FasTrak Availability
    ERCOT will keep the FasTrak tool on-line (view and update only) for 90 calendar days after MarkeTrak is implemented (~end of Nov 2006)
  Shutdown of Access to FasTrak
    One month prior to shutdown of FasTrak – ERCOT will provide MPs a report of remaining open issues
    One week prior to shutdown of FasTrak – ERCOT will close remaining open issues and provide report to MPs
Request for FasTrak Data After Shutdown
  ERCOT will maintain FasTrak data for a period of no longer than 7 years
    MPs can request FasTrak data from ERCOT after MarkeTrak implementation
    Lead times for these types of requests will be 7-10 business days
As of May 9, 2006
Page 5
FasTrak to MarkeTrak Cut Over Plan (cont.)
Notes: <number>
<footer>
<header>
<date/time>

## Slide 7: Questions / Contact Information
Adam D. Martinez
Mgr, Market Ops Divisional Projects Organization
(512) 248-3883 / amartinez@ercot.com
Scott Egger
Sr. Business Analyst / MarkeTrak Project
(512) 248-3162 / segger@ercot.com
Notes: <number>
<footer>
<header>
<date/time>