## Slide 1: Project Process Discussion
Adam D. Martinez
Mgr, Market Ops Divisional Projects Organization
ERCOT
RMS Meeting
May 10, 2006

## Slide 2: Training Agenda
Segment 1: Introduction
(5 Min)
  Background
  Organizational Change Summary
  PMO Standard and Supporting Procedures
Segment 2: Program and Project Governance (10 Min)
  Governance Hierarchy
  Divisional Projects Organization (DPO)
  Roles and Responsibilities
  Project Authorizations
Segment 3: Portfolio Management (10 Min)
  Origin of Projects
  Project Pre-Concept and Concept Process
  Divisional Projects Portfolio Planning Process
Segment 4: Project Management (10 Min)
  Project Structure
  Project Management & Development Process
  Project Phase Gating Deliverables
Segment 5: Project Metrics and Compliance (10 Min)
  Project Goals and Milestones
  Project Quality Assurance and Compliance
Questions and Answers (15 Min)

## Slide 3: Program Objectives
Communicate Organizational Changes.
Describe the Revised Governance Structure.
Present the New Portfolio Management Process.
Review the Project Management Process.
Present the Revised Reporting Requirements and Formats.
Present the Quality Assurance and Compliance Process.

## Slide 4: Session Road Map
Segment 1 - Introduction
  Background
  Organizational Change Summary
  PMO Standard and Supporting Procedures
Segment 2 - Program and Project Governance
Segment 3 - Portfolio Management
Segment 4 - Project Management
Segment 5 – Projects Metrics and Compliance

## Slide 5: Background
During Q3 2005, a PMO review was performed that provided “Quick Hit”, short term, and long term recommendations to help improve the effectiveness of the PMO and project delivery.
ERCOT process improvement team has completed the implementation of the following “Quick-Hit” recommendations to improve project delivery:
  Address project accountability, responsibility and basic management practices with specific focus on organizational structures and corresponding roles and responsibilities.
  Establish effective project reporting and communications at both the project and enterprise levels.
  Establish a resource utilization process that reflects accurate allocations for use in forecasting, scheduling, tracking and budgeting of projects. [Implementation has been delayed]
Notes: <number>
<footer>
<header>
<date/time>

## Slide 6: Organizational Change Summary
Implemented the following organizational structures:
  Update current Centralized Program Management Office (PMO) focusing on fostering project management excellence through standardized processes, procedures, tools, training and support functions for all ERCOT projects.
  Establish Decentralized Divisional Projects Organization (DPO) focusing on accountability and responsibility for business area project portfolio management and delivery.
Established Divisional-PPL’s assigning accountability and responsibility to each ERCOT Executive for managing their resulting business area projects portfolio.
Clarified, documented and communicated Roles and Responsibilities to revised organizational structures.

## Slide 7: Organization Structure Changes
The project management teams will report directly to their corresponding business area establishing a Divisional Projects Organization (DPO) that will be supported by the Program Management Office (PMO).
Notes: <number>
<footer>
<header>
<date/time>
Instructor Notes:
Describe the new organization focusing on the PMO, and DPO organizations. Explain that the roles and responsibilities for the new groups will be described in coming slides.

## Slide 8: PMO Standard and Supporting Procedures
The following outlines the structure for the PMO operating procedures. Each operating procedure details one of the major processes described in the Program Management Standard.
Corporate Standard
Program Management Standard
Operating Procedure #1
PROGRAM AND PROJECT GOVERNANCE
Operating Procedure #2
PROJECT CONCEPT AND PROPOSAL
Operating Procedure #3
PROJECT PRIORITIZATION AND FUNDING
Operating Procedure #4
PROJECT DELIVERY AND CONTROL
Operating Procedure #5
PROJECT QUALITY REVIEW AND COMPLIANCE
Operating Procedure #6
PROJECT, DIVISIONAL, AND ENTERPRISE REPORTING
Operating Procedure #7
PROJECT METHODOLOGY AND TOOLS
Please contact Cheryl Mosley for location of approved PMO Operating Procedures.
Notes: Instructor Notes:
Describe the organization and focus of each Operating Procedure.
Show the cover and tables of contents of each document as needed.
Described where the procedures can be found and used.
Finally, explain that the remaining segments of the training will describe the new PMO standards and supporting procedures.

## Slide 9: Session Road Map
Segment 1 - Introduction
Segment 2 – Program and Project Governance
  Governance Hierarchy
  Divisional Projects Organization (DPO)
  Roles and Responsibilities
  Project Authorizations
Segment 3 - Portfolio Management
Segment 4 - Project Management
Segment 5 – Project Metrics and Compliance
Corporate Standard
Program Management Standard
Operating Procedure #1
PROGRAM AND PROJECT GOVERNANCE
Operating Procedure #2
PROJECT CONCEPT AND PROPOSAL
Operating Procedure #3
PROJECT PRIORITIZATION AND FUNDING
Operating Procedure #4
PROJECT DELIVERY AND CONTROL
Operating Procedure #5
PROJECT QUALITY REVIEW AND COMPLIANCE
Operating Procedure #6
PROJECT, DIVISIONAL, AND ENTERPRISE REPORTING
Operating Procedure #7
PROJECT METHODOLOGY AND TOOLS
This segment covers information outlined in the Operating Procedures highlighted below.

## Slide 10: Governance Hierarchy
Notes: Instructor Notes:
Describe the new Governance Hierarchy concepts. Explain that the roles and responsibilities will be described in the next few slides.

## Slide 11: Divisional Projects Organization (DPO)
The Divisional Projects Organization (DPO) is:
Responsible/accountable for business area project portfolio management.
Responsible/accountable for successful completion of projects.
Notes: Instructor Notes:
Describe the new DPO positions and their roles and responsibilities.

## Slide 12: Roles and Responsibilities
Executive Committee (EC)
  Reviews approvals and recommendations provided by Strategic Review Team.
  Provides approval via simple majority for final funding and prioritization for all programs and projects.
Strategic Review Team (SRT)
  Responsible for evaluating the strategic and tactical relevance of new and ongoing programs and projects, along with the related benefits, across ERCOT.
  Manages the ERCOT portfolio in a collective manner to ensure all cross-functional impacts to projects are assessed on a cumulative basis.
  When appropriate, the SRT reviews projects and/or change orders and recommend them to the EC for approval.
  Conducts overall reviews and recommends transfers of funding between divisions.
Continuous Analysis and Requirements Teams (CART)
  Responsible for the management of all programs and projects.
  Approves projects moving through the gating process.
  Manages Change Control process.
Notes: Instructor Notes:
Describe any changes to existing positions (EC and CARTs), roles and responsibilities.
Also describe the roles and responsibilities of the new SRT.

## Slide 13: Roles and Responsibilities
Divisional Projects Organization (DPO)
  Responsible for managing program and project formulation and implementation, and providing oversight and direction to their divisions.
  Specific DPO responsibilities include
    Develops the Divisional-PPL strategy.
    Develops the high-level project release plans.
    Develops resource plans to support the project plans.
    Responsible for delivering all funded projects contained in the Divisional-PPL portfolio on time, within budget and meeting the business requirements.
Notes: Instructor Notes:
Describe the new DPO positions, roles and responsibilities.

## Slide 14: PMO Roles and Responsibilities
The Program Management Office (PMO) focuses on:
Fostering project management excellence through standardized processes, procedures, tools, training and support functions for all ERCOT projects.
Notes: Instructor Notes:
Describe each of the new PMO positions, roles and responsibilities.

## Slide 15: Project Authorizations
Organization | Approval Description | Budget Approval
Board of Directors | Authorizes annual projects budget for all projects. Authorized to approve the project phase gating into Execution where the total project budget is more than $1MM. Authorized to approve cumulative change control requests that are greater than $1MM. Authorized to approve vendor contracts greater than $1MM. | New budget or changes greater than or equal to $1MM
Executive Committee | Authorized to approve the project phase gating for new projects where the total project cost is less than $1MM. Authorized to approve cumulative change control requests that are less than $1,000,000. Authorized to approve vendor contracts less than $1MM. | Within approved budget and new projects or changes less than $1MM
SRT | Authorized to approve the project phase gating for new projects where the total project cost is under $500,000. Authorized to approve cumulative change control requests that are between $100,000 and $500,000. | Within approved budget and new projects under $500,000 and changes between $100,000 and $500,000
CART and DPO | Authorized to approve the project phase gating for new and active projects where the total project cost is within the approved budget. Authorized to approve cumulative change control requests that are less than $100,000. Note: If the cumulative change control requests for a single project exceed $100K, the change control request will require the review and approval from the SRT. | Within approved budget and changes less than $100,000
Notes: Instructor Notes:
Discuss the project signature authorization levels and definitions.

## Slide 16: Session Road Map
Segment 1 - Introduction
Segment 2 - Program and Project Governance
Segment 3 - Portfolio Management
  Origin of Projects
  Project Pre-Concept and Concept Process
  Divisional Projects Portfolio Planning Process
Segment 4 - Project Management
Segment 5 – Project Metrics and Compliance
Corporate Standard
Program Management Standard
Operating Procedure #1
PROGRAM AND PROJECT GOVERNANCE
Operating Procedure #2
PROJECT CONCEPT AND PROPOSAL
Operating Procedure #3
PROJECT PRIORITIZATION AND FUNDING
Operating Procedure #4
PROJECT DELIVERY AND CONTROL
Operating Procedure #5
PROJECT QUALITY REVIEW AND COMPLIANCE
Operating Procedure #6
PROJECT, DIVISIONAL, AND ENTERPRISE REPORTING
Operating Procedure #7
PROJECT METHODOLOGY AND TOOLS
This segment covers information outlined in the Operating Procedures highlighted below.

## Slide 17: Origin of Projects
Divisional Projects Organization
Overall Management of:
Portfolio of Projects
Program Area Structure
Project, Priorities & Reporting and Monitoring
Project Management Process
Management of:
Budgets and Approvals
Project Delivery
Resources, Costs, Timelines
Initiation of Project Requests:
PUCT Rulings
System Change Requests (SCRs)
Protocol Revision Requests (PRRs)
ERCOT Project Requests (PRs)
ERCOT
DPO /
Executive Committee
ERCOT
PM Process
PUCT
Market
Participants
ERCOT
Projects Pipeline
Notes: Instructor Notes:
State that the project pipeline inputs and outputs have not changed.
Discuss the new conceptual differences adopted for Project Management and Development processes.

## Slide 18: Project Pre-Concept/Concept Process

## Slide 19: Divisional Projects Portfolio Planning Process
Identify Divisional Carry-Over Projects
Assign Project Priority and Rank
  PUCT Projects
  Market Projects
  ERCOT Projects
Establish Divisional Annual Budget Projects Requirements
(This utilizes the Quarterly Processes)
Establish Overall ERCOT Annual Projects Budget Request
Finalize ERCOT Annual Projects Budget
Evaluate Proposed Changes to Divisional Projects
Update Project Priority and Rank
  PUCT Projects
  Market Projects
  ERCOT Projects
Revise Divisional Portfolio Requirements
  Project Execution Plans
  Supporting Resource Plans
  Projected Spend
Update Divisional Portfolio Plans
Consolidate Divisional Portfolio Plans
Identify Enterprise-Wide Conflicts
Resolve Enterprise-Wide Conflicts
Finalize/Publish Divisional Portfolio Plans
Finalize/Publish Enterprise-Wide Portfolio Plans
Evaluate Impacts to Divisional Projects from Project Status Updates
Identify Divisional Conflicts
Resolve Divisional Conflicts
Update Divisional Portfolio Plans
Consolidate Divisional Portfolio Plans
Identify Enterprise-Wide Conflicts
Resolve Enterprise-Wide Conflicts
Finalize/Publish Divisional Portfolio Plans
Finalize/Publish Enterprise-Wide Portfolio Plans
Annual Process
“Project Prioritization and Annual Funding ”
Quarterly Process
“Project Prioritization, Funding,
and Portfolio Management”
Monthly Process
“Portfolio Management”

## Slide 20: Session Road Map
Segment 1 - Introduction
Segment 2 - Program and Project Governance
Segment 3 - Portfolio Management
Segment 4 - Project Management
  Project Structure
  Project Management & Development Process
  Project Phase Gating Deliverables
Segment 5 – Project Metrics and Compliance
Corporate Standard
Program Management Standard
Operating Procedure #1
PROGRAM AND PROJECT GOVERNANCE
Operating Procedure #2
PROJECT CONCEPT AND PROPOSAL
Operating Procedure #3
PROJECT PRIORITIZATION AND FUNDING
Operating Procedure #4
PROJECT DELIVERY AND CONTROL
Operating Procedure #5
PROJECT QUALITY REVIEW AND COMPLIANCE
Operating Procedure #6
PROJECT, DIVISIONAL, AND ENTERPRISE REPORTING
Operating Procedure #7
PROJECT METHODOLOGY AND TOOLS
This segment covers information outlined in the Operating Procedures highlighted below.

## Slide 21: Project Structure
Stronger organizational matrix established for the following project delivery structure.
Notes: Instructor Notes:
Discuss the new project structure and organization.

## Slide 22: Project Development Life Cycle
The following diagram illustrates the Project Lifecycle Process:
Notes: Instructor Notes:
Discuss the new conceptual differences adopted for the Project Development Life Cycle.

## Slide 23: Project Phase Gating Deliverables
Project Charter
Planning Phase Schedule
Planning Phase Resource Plan
Initial Estimated Cash Flow
RFI/RFP/SOW (if applicable)
Tollgate Documentation
Execution Phase Schedule
Execution Phase Resource Plan
Updated TCE (if applicable)
Updated Cash Flow
Detailed Business Requirements
Conceptual Design
Technical Architecture
Detailed Design
Test Cases
Tollgate Documentation
Change Control Documentation
RFI/RFP/SOW (if applicable)
Vendor Selection & Contract
Vendor Product Delivery
Install Hardware and Software
Code, Unit Test, Product Test
Test Plan, Test Script
Defect Tracking
Integration & User Acceptance Test
Market Certification Test
User Training Document
User Training
Production Support Documentation
Migration Control Document (MCD)
Migration to Production
Production Stabilization
Version Control Procedure
As Built Detailed Business Requirements, Technical Architecture, & Detailed Design
Tollgate Documentation
Project Signoff
Lessons Learned
  Report Card
  Survey
  Summary
Tollgate Documentation
Tollgate
“Initiation”
Tollgate
“Planning”
Tollgate
“Execution”
Tollgate
“Closure”

## Slide 24: Session Road Map
Segment 1 - Introduction
Segment 2 - Program and Project Governance
Segment 3 - Portfolio Management
Segment 4 - Project Management
Segment 5 – Project Metrics and Compliance
  ERCOT Project Reporting Information Flow
  Project Goals and Milestones
  Project Quality Assurance and Compliance
Corporate Standard
Program Management Standard
Operating Procedure #1
PROGRAM AND PROJECT GOVERNANCE
Operating Procedure #2
PROJECT CONCEPT AND PROPOSAL
Operating Procedure #3
PROJECT PRIORITIZATION AND FUNDING
Operating Procedure #4
PROJECT DELIVERY AND CONTROL
Operating Procedure #5
PROJECT QUALITY REVIEW AND COMPLIANCE
Operating Procedure #6
PROJECT, DIVISIONAL, AND ENTERPRISE REPORTING
Operating Procedure #7
PROJECT METHODOLOGY AND TOOLS
This segment covers information outlined in the Operating Procedures highlighted below.

## Slide 25: ERCOT Project Reporting Information Flow
SO
Divisional
Projects
Report
MO/RO
Divisional
Projects
Report
IO
Divisional
Projects
Report
CO
Divisional
Projects
Report
Enterprise Projects Summary Report
CO
Project
Status
Reports
IO
Project
Status
Reports
MO/RO
Project
Status
Reports
SO
Project
Status
Reports

## Slide 26: Project Goals and Milestones
2006 Goals for On-Time and On-Budget
  All projects for 2006 will be measured for these goals.
  Integral part of the Project and Divisional Projects Organization Status Reports.
Three On-Budget Milestone goals
  Planning (Planned vs. Actual) Cost.
  Execution (Planned vs. Actual) Cost.
  Overall Project (Planned vs. Actual) Cost.
Ten On-Time Milestone goals (listed on the next page).

## Slide 27: Project On-time Milestone Goals
Project Milestones (10 – On-time Milestones)
Milestone
1. Project Started
2. Requirements Complete
3. Detail Design Complete
4. Technical Architecture Complete
5. Planning Complete
6. Development Complete
7. Unit/P-test Complete
8. I-Test / User Acceptance Test (UAT) Complete
9. Go Live Complete
10. Project Complete
Notes: Instructor Notes:
Emphasize the 10 project milestones. Encourage the audience to study the definitions and refer to OP 4 document for details. Goals can be found in the ERCOT Corporate goals program documentation.

## Slide 28: Project Quality Assurance and Compliance
Planning, Quality, and Reporting (PQR) provides:
  Enterprise Portfolio Management and Reporting.
  Program and Project Management Standards, Procedures, Training and Support.
  Project and Portfolio Management Tools, Training and Support on Tools.
  Program and Project Management, and SDLC Process Compliance.
PQR ensures that:
  The enterprise and divisional portfolio management processes, standards, procedures and supporting tools are being used in a consistent fashion.
  Projects are following the established ERCOT Program and Project Management standards and procedures.

## Slide 29: PQR Review and Compliance
Notes: Instructor Notes:
Emphasize the new PRQ role and the compliance items that will be required.

## Slide 30: Questions / Contact Information
Adam D. Martinez
Mgr, Market Operations Divisional Projects Organization
ERCOT
(512) 248-3883
amartinez@ercot.com
Notes: <number>
<footer>
<header>
<date/time>