|  |  | System Planning Division |
| --- | --- | --- |
|  |  | Monthly Status Report to Technical Advisory Committee Reliability and Operations Subcommittee for April 2006 |
|  | Report Highlights |  |
| Item |  | Section |
| 1. | Interconnection Requests Increase by 1,919 MW in April: Four new generation interconnection requests were received by ERCOT for screening studies in April. The total capacity of active generation interconnection requests is 27,865 MW. | 1.0 |
| 2. | CREZ Consultant Selected: ERCOT has contracted with AWS Truewind to define specific areas to be considered as potential Competitive Renewable Energy Zones (CREZs). | 3.0 |
| 3. | ERCOT Reviewing Fuel Forecast: ERCOT is working cooperatively with SPP staff to investigate potential fuel price forecasts. | 3.0 |
| 4. | Combined Cycle Stability Model RFP Finalized: ERCOT has finalized an RFP to be issued to assist in the development of a Combined Cycle Stability Model. | 4.0 |
| 5. | Private Network Survey Distributed: ERCOT has distributed a survey to Private Networks in order to accurately account for their respective generation/resources as part of the on-going project to update the CDR. | 4.0 |

1.0	Status of Active Generation Interconnection Requests

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” data folder posted in the “Operations and System Planning” data area on the ERCOT website.

1.1	New Generation Beginning Commercial Operations.

There were no generation projects placed into commercial activity in April, 2006.

1.2	Active Generation Interconnection Requests.

The table below summarizes the active generation interconnection requests currently being processed by ERCOT System Planning.  The current 85 projects reflecting 27,865 MW of capacity in an increase of 4 projects and 1,919 MW of capacity respectively over the March totals of 81 projects and 25,946 MW of capacity.

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |
| --- |
| Currently tracking 81 active generation interconnection or change requests |
|  | North | South | West | Total |
| Security Screening Study |  | 4 | 2 | 4 | 10 |
| SSS Completed |  | 2 | 2 | 13 | 17 |
| Full Interconnect Study |  | 9 | 7 | 26 | 42 |
| FIS Completed |  | 0 | 1 | 0 | 1 |
| Interconnect Agreements Completed |  | 2 | 2 | 11 | 15 |
| Capacity for Grid, MW |  | 8,405 | 9,147 | 10,313 | 27,865 |
| Wind MW (under development) |  | 330 | 2,330 | 9,559 | 12,219 |

The table below summarizes the primary fuel-type of the active generation interconnection requests currently being processed by ERCOT System Planning.

| INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED BY FUEL TYPE |
| --- |
| Fuel-Type | Public Projects | Confidential (Non-public) | Total Capacity Under Review (MW) | % |
| Natural gas | 2,300 | 3,900 | 6,200 | 22% |
| Coal | 4,450 | 4,009 | 8,459 | 31% |
| Wind | 2,929 | 9,290 | 12,219 | 44% |
| Other | 12 | 975 | 987 | 3% |
| Totals | 9,691 | 18,174 | 27,865 | 100% |

1.3	Potential Future Generation Interconnections.

The table below summarizes the publicly-known potential future generation projects for the ERCOT region.

| FUTURE GENERATION INTERCONNECTIONS (PUBLIC PROJECTS) |
| --- |
| INR # | Site Name | Status | County | Region | Fuel | In Service Date | MW into Grid | Change from Last Report |
| 09INR0017 | Limestone Upgrade | Interconnect Agreement | Limestone | North | Coal | May-06 | 110 |  |
| 05INR0018 | Horse Hollow 2 | Interconnect Agreement | Nolan | West | Wind | Oct-06 | 186 | Date Change |
| 06INR0040 | Horse Hollow 3 | Interconnect Agreement | Nolan | West | Wind | Jul-06 | 400 | Date Change |
| 07INR0019 | Horse Hollow 4 | Interconnect Agreement | Nolan | West | Wind | Aug-06 | 116 | Date Change |
| 06INR0008 | Big Spring Electricity Generating Facility 1 | Interconnect Agreement | Howard | West | Waste heat | Jun-06 | 12 |  |
| 05INR0017 | Red Canyon 1 | Interconnect Agreement | Borden | West | Wind | Jun-06 | 84 |  |
| 06INR0016 | Dow 9 | Interconnect Agreement | Brazoria | South | Gas | Oct-06 | 0 |  |
| 04INR0020 | WKN Wind 1 Snyder | Interconnect Agreement | Scurry | West | Wind | Dec-06 | 60 |  |
| 05INR0011 | Forest Creek | Interconnect Agreement | Sterling | West | Wind | Dec-06 | 215 |  |
| 04INR0011 | Mesquite Wind 1 | Interconnect Agreement | Shackelford | West | Wind | Dec-06 | 200 |  |
| 06INR0035 | Colorado Bend Energy Center | Interconnect Agreement | Wharton | South | Gas | Dec-06 | 275 |  |
| 06INR0036 | Quail Run Energy Center | Interconnect Agreement | Ector | West | Gas | Dec-06 | 275 |  |
| 03INR0034 | Silver Star Project | Interconnect Agreement | Erath | West | Wind | Mar-07 | 60 |  |
| 04INR0015 | Cirello 1 | Interconnect Agreement | Taylor | West | Wind | Mar-07 | 233 | Formally Buffalo Gap 2 |
| 05INR0015 | Gulf Wind | Public Letter | Kenedy | South | Wind | Sep-07/08/09/10 | 1,200 | Four Phases, 300 MW Each |
| 01INR0028 | Orion Delaware Mountain Wind Farm | Interconnect Agreement | Culberson | West | Wind | Dec-07 | 175 |  |
| 06INR0006 | Cobisa-Greenville | Public Letter | Hunt | North | Gas | May-08 | 1,750 |  |
| 08INR0003 | Sandow 5 | Public Letter | Milam | North | Coal | Jul-08 | 0 | New |
| 09INR0006 | Oak Grove | Public Letter | Robertson | North | Coal | Mar-09 | 1,660 |  |
| 09INR0001 | Sandy Creek | Public Letter | McLennan | North | Coal | Jul-09 | 800 |  |
| 09INR0002 | J K Spruce 2 | Public Letter | Bexar | South | Coal | Aug-09 | 750 |  |
| 10INR0002 | Hugo Plant | Public Letter | Choctaw, OK | North | Coal | Dec-10 | 500 |  |
| 11INR0001 | Twin Oaks 3 | Public Letter | Robertson | North | Coal | Jun-11 | 630 |  |
|  |  |  |  |  |  | Totals: | 9,691 |  |

2.0	Status of RMR Contracts

The table below summaries generating units currently under RMR Contract as of April 30, 2006.

| Unit | Generation Capacity (MW, Net) | RMR Contract Status | Contract Date | Current Anticipated Exit Date | Change Since Last Report |
| --- | --- | --- | --- | --- | --- |
| BM Davis 1 | 335 | Under Contract. Termination Letter Sent | 1/1/06-12/31/06 | 5/19/06 | N/A |
| La Palma 5, 6, &7 | 222 | Under Contract. Termination Letter Sent | 1/1/06-12/31/06 | 6/30/06 | N/A |
| Laredo 1, 2, & 3 | 172 | Under Contract | 1/1/06-12/31/06 | 3Q 2010 under review | N/A |
| Atkins 3, 4, 5, 6 | 97 | ERCOT in negotiations for RMR services for Units 4, 5, and 6 starting in June 2006. |  |  | N/A |
| Total MW Under RMR Contract as of April 30, 2006 | 729 |  |  |  |  |

3.0	Regional Planning Activities

The following summarizes numerous significant activities associated with regional planning issues.

3.1	Long-term System Study (SB20).

  - A contract has been reached with AWS Truewind as a result of the Wind Consultant RFP.  Work will begin in early May on this project to define specific areas to be considered as potential Competitive Renewable Energy Zones (CREZs) and develop representative wind power profiles for each.

  - A joint Regional Planning Groups (RPG) workshop was held on April 21 to develop generation scenarios to be used for this study.  The primary drivers identified to drive the range of scenarios were natural gas prices, load growth, and environmental regulations.

  - Five-year Study (Pre-Nodal Study Follow-up).

  - Completed ERCOT analysis on projects proposed for completion in 2007 for which TSPs have requested decisions prior to the timeline for completion of the Five-Year Study.  These results will soon be posted.

  - Completed and posted the differences between 2006/2007, 2007/2008, 2008/2009 TPIT vs. SSWG basecase comparisons.

  - Continued working with stakeholders on expansion plan scenarios for wind generation in the 2008 and 2009 cases (the 2007 case is based on wind generation units that have signed Interconnection Agreements).

  - Next phase of this study is to complete the reliability basecases and the work a year at a time through the RPG-level projects in order to determine appropriate timing of projects from pre-nodal analysis.

  - Entergy Study (PUCT Project 32217:  Entergy Gulf Coast Inc.’s Plan for Identifying Applicable Power Region Pursuant to PURA 39.452(F)).

  - ERCOT staff developing scope and timeline based on Commission direction to required follow-up studies.

  - Southwest Power Pool (SPP) Studies.

  - ERCOT staff has synched fuel price forecast assumptions with SPP, and performed initial preliminary fuel forecast analysis.

  - Regional Planning Group Project Reviews.

  - ERCOT received only two comments regarding the Centerpoint Dynamic Reactive project.  The threshold issue under investigation in examining this project is what criteria for dynamic reactive needs should be developed.  ERCOT staff recommends that ROS/DWG need to address this issue.  In addition, ERCOT has initiated a survey to determine frequency of forced outages similar to NERC Category D; however, responses have only been received from CPS, Centerpoint, Austin, and LCRA.

  - TXUED submitted the addition of a second 345/138kV auto at Sandow for RPG review.  Since the initial submission, TXUED has responded to all comments and this project is now undergoing Independent Review by ERCOT staff with a completion date set for July 18, 2006.

  - Two 69kV projects submitted by South Texas Electric Cooperative (STEC) are now in Study Mode with an estimated end date of May 15, 2006.

  - ERCOT staff is currently performing an Independent Review of this AEPTCC/Medina Electric Cooperative (MEC) project for the Uvalde area.  Anticipated completion of this study is May 2006.

4.0	Transmission Services Activities

The following summarizes numerous significant activities associated with the Transmission Services group.

4.1 	Dynamic Analysis and Modeling.

- The RFP for the Combined Cycle Stability Model Development is being finalized by ERCOT staff.  The initial draft was reviewed by System Planning staff and the TAC ROS Dynamics Working Group in April.

- ERCOT staff is currently working to integrate “Wind Farms” into the 2006 summer on-peak stability base case.   However, due to Non-Disclosure Agreement (NDA) clauses in modeling agreements with wind  turbine manufacturer’s, ERCOT staff will distribute Dynamic Data Sets with public-domain models only to DWG members; unless the DWG member provides evidence that their organization holds a NDA with the wind model data owner (usually the wind turbine manufacturer).  At present, the Mitsubishi turbine model requires a NDA for its use.  At present, ERCOT staff is negotiating with Siemens Wind an agreement to use the Siemens wind turbine model without the explicit need of a NDA for DWG activities.

- ERCOT staff has distributed a survey to “Wind Farms” in order to solicit “as-built” voltage and frequency protection data for use in stability analysis studies.  Responses are expected in May.

- ERCOT staff is working to develop stability study scopes to satisfy ERCOT compliance with NERC Standards TPL-001-0, TPL-002-0, TPL-003-0, TPL-004-0 relating to NERC Contingency Categories A, B, C and D.

4.2	Load Forecasting.

- ERCOT staff is continuing work on the 2006 Capacity Demand and Reserve (CDR) Report.  A survey to determine the impact on the CDR due to Private Networks has been developed and distributed. Results are expected back to ERCOT in May.

- ERCOT staff is continuing to expand and refine its analysis of weather volatility limits regarding the long-term demand forecast.  Current efforts are primarily centered around a more detail periodicity from daily to hourly due to weather volatility and sensitivity.

5.0	Upcoming Events/Deadlines (partial list)

May

- Transmission Project Information Tracking (TPIT) workbooks and base case updates due to ERCOT; May 1st.

- Steady state base case RAW data files for base case development due to ERCOT SSWG; May 5th

- NERC Operating Committee, Transmission Issues Subcommittee (TIS) meeting; May 10-11th

- TAC ROS Dynamics Working Group (DWG) meeting; May 30-31

June

- ROS Steady State Working Group Data Set A meeting at ERCOT; June 13-15

- NERC Planning Committee Meeting: June 7-8

# Footnotes

NERC Category D examines contingencies related to “Extreme event resulting in two or more (multiple) elements removed or cascading out of service”.

NERC Category A requires a planning analysis under “No Contingencies”.  NERC Category B is related to “Event resulting in the loss of a single element”.  NERC Category C is related to “Event(s) resulting in the loss of two or more (multiple) elements”.