## Open TX SET Action Items
Date Opened | Action Item | Resolution | Status | Date Last Updated
2006-02-28 | TX SET membership was assigned to review and propose revision changes to TX SET Implementation Guides to support Mass Transition Project and high level design at March Meeting. | Discussed at March TX SET Meeting - 04/26/06 - This is a work in progress | Pending | 2006-04-26
2006-02-28 | TX SET Leadership (Kathy Scott ) will take updated TX SET Procedures Document to RMS for approval. | Approved at RMS on 4/12/06 and will be discussed at TAC in May for their approval | Closed | 2006-04-26
2006-02-28 | TX SET Leadership (Kathy Scott) will develop an RMGRR to incorporate MCT Roles and Responsibilities Document into the Retail Market Guide. | Pending - need to discuss with Sonja Mingo and Glen Wingerd on suggestion of website posting of the MCT Taskforce | Pending | 2006-04-26
2006-02-28 | Revise the 867_04 Implementation Guide to remove invalid example. TX SET discussed example 2 of 5 found on page 19 of this Implementation Guide. | Need and issue created to remove the incorrect or correct the examples on this transaction - Johnny Robertson will draft issue | Pending | 2006-04-26
2006-02-28 | Revise grey boxes in transactions to clarify that only 5 or 9 digit zip codes are allowed all others would be rejected by ERCOT. | Need and issue to clarfiy the graybox for the acceptable data for the ZIP Code - Catherine Meiners will draft issue | Pending | 2006-04-26
2006-02-28 | SIR 10528 – Backdating Transactions – ERCOT will implement validation to reject any transaction received that backdated prior to 01/01/1999. | This action item has been resolved with the implementation of SIR 10528 by ERCOT on April 22, 2006 | Closed | 2006-04-26
2006-02-28 | Multiple DTM~140s on the 867_04 transaction received from TDSP. Bill Reily will bring an example of when TXU ED has provided multiple meter information in the 867_04 to enable TX SET to fully discuss the appropriate transactional process. | Discussion on 4/25/06 at TX SET identified that issue has been resolved | Closed | 2006-04-26
2006-03-06 | TX Leadership to develop language to specify that the Change Control Form is for use by TX SET after the approval of an Issue | Leadership had discussed with Jennifer Fredrick to update the Change Control Form on the web for TX SET Use only, however that information had not been posted at the time of this meeting - Susan Munson will work with Jennifer to get this updated. | Pending | 2006-04-26
2006-03-06 | Market Participants and ERCOT to go back to their shops and determine what they need to implement changes in their systems. Provide feedback at the April 5th meeting. | Market Participants provided the necessary feedback at the April 5, 2006 meeting concerning Mass Transition changes and implementation schedule | Closed | 2006-04-26
2006-03-06 | Each Market Participant has been asked to evaluate cost estimates of what it would cost to implement Mass Transistion Long Term Transactional Solution. Provide feedback at the April 5th meeting. | Market Participants provided the necessary feedback at the April 5, 2006 meeting concerning Mass Transition changes and implementation schedule | Closed | 2006-04-26
2006-05-06 | Ts Cs - POLR Rule Reference 4.3.4 - Is a new reject code necessary to reject off cycle fee. CRs will evaluate need for new reject code prior to TX SET meeting. | Assigned to Rob Bevill | Pending | 2006-05-23
2006-05-06 | Ts Cs - POLR Rule Reference 4.4.3 - Do we need a reject code when a re-bill comes in greater than 150 days? Note: 5 day reject rule applies. | Assigned to Rob Bevill | Pending | 2006-05-23
2006-05-06 | Ts Cs - POLR Rule Reference 4.3.7 - will look at the Implementation Guide for potential transaction flow and grey box changes for the 814_PC process. | Assigned to Johnny Robertson. (Gray box change only.) | Pending | 2006-05-23
2006-05-06 | Ts Cs - POLR Rule Reference 4.4.5 - Review the 820 Implementation guide for conformity with the rule. | Assigned to Kathy Scott, Cary Reed, Bill Reily (regarding clarity between 820/810 pairs) | Pending | 2006-05-23
2006-05-06 | Ts Cs - POLR Rule Reference 4.8.3 - Modify 810_02 existing “05” replacement code to allow for a new provision. | Will look at 867 monthly and final and 810 for "05" replacement code. Assigned to Jennifer Garcia, Diana Rehfeldt | Pending | 2006-05-23

## Closed Action Items
Date Opened | Action Item | Resolution | Status | Date Last Updated

## Parking Lot Items
Date Opened | Parking Lot Item | Resolution | Status | Date Last Updated
2006-02-28 | Update RMGRR to make sure there is a way to drop the Customer Information to the TDSP as well as the CR for updates. | Due to issues and POLR rulemaking has not been settled this may not be an issue for TX SET. Can re-open if needed at a later date when all issues have been resolved. | Closed | 2006-04-26
2006-02-28 | (Chuck Moore) Look at RMGRR Long Term language to see if ERCOT will still send a list of pending transactions to the Gaining CRs. This request is for when the current CR is defaulting the new gaining CR receives a spreadsheet that notifies them of pending transactions to see if the gaining CR has an opportunity to gain (Switch) the Retail Customer earlier preventing them from going to POLR. | ERCOT will investigate if this functionality or process can be added to the Mass Transition requirements document. TX SET Leadership will also add this item to the agenda for May 22/23 meetings to discuss what needs to be added and to document the requirement needs for ERCOT. | Pending | 2006-04-26
2006-02-28 | Possibly look at ERCOT dropping a 814_03 for ESI IDs with pending MVIs that are on day 1, 2, or 3. Might need to look at a priority code and/or code to let the TDSP know that this is a MVI and the lights are not on so that they know it will not be processed as a Switch. | Per TX SET discussion the cost of building this logic would be more than the benefit because of the volume that would apply for this situation. | Closed | 2006-04-26
2006-02-28 | (Kyle Patrick) Need a way for CRs to submit a Switch on customers that are with them as the POLR but have requested Non-POLR service. | This issue may be resolved through the adopted POLR Rule and the selection criteria for POLRs that are within the Rule. | Closed | 2006-04-26
2006-02-28 | Work to consolidate implementation materials for Retail Releases. Work to make sure that information provided concerning releases is consistent across all documentation involved in the project and/or release. | TX SET in conjuction with MCT will work to creating this as our goal | Pending | 2006-04-26