## Slide 1: MO Projects Update
Adam D. Martinez
Mgr, Market Ops Divisional Projects Organization
ERCOT
COPS Meeting
May 23, 2006

## Slide 2: Current MO Project Priority List – Top 22 *
Stats: 3 Closed/Closing; 12 Active (4 Initiation; 0 Planning; 8 Execution); 2 Not Started; 5 Transf/Cancel
Indicates planned or recent change in Phase and/or Budget Range; specifics in red font
PLEASE NOTE: PPL posted to ERCOT.com as of 5/10/06 (http://www.ercot.com/services/comm/projects/index.html) may not include recent updates reflected here
Yellow
Srce | Com | Src Doc | Project | Project No. | Curr Phase | 2006 Priority | 2006 Rank | 2006 Budget Range | Est. Closure
M | MO | SCR740 | Enhancements to SCR727 - Market Access | 50024_01 | Execution | 1.0a | 0.05 | $500k-$1M | Jan-07
M | MO | SCR740 | Enhancements to SCR727 - Market Enhancements | 50024_02 | Initiation | 1.0a | 0.05 | $100k-$500k | Jan-07
M | MO | SCR740 | Enhancements to SCR727 - Market Enhancements | 50024_03 | 50024_02 Merge | 1.0a | 0.05 | $100k-$500k | N/A
M | MO | PRR312 | Enhance ESIID Lookup Function | 50025 | Execution | 1.0a | 0.06 | $100k-$500k | Dec-06
P | MO |  | EDW BI Reporting Tool | 50004 | Closing | 1.0a | 0.15 | <$100k | May-06
E | MO |  | Lodestar Extracts | 40042_06 | Execution | 1.0a | 0.18 | $100k-$500k | Nov-06
M | MO | PRR283 PIP204 | EPS Meter Data | 30026 | Execution | 1.0b | 0.54 | <$100k | Aug-06
E | MO |  | TCR Report Enhancements Phase II | 40015_02 | Execution | 1.0b | 0.59 | <$100k | Nov-06
E | MO |  | SCR 727 Phase II | 40007 | Execution | 1.0b | 0.71 | $100k-$500k | Jan-07
M | MO | PRR548 PRR599 | Settlement Mismatches Inter-QSE Schedules / Notification for Mismatched Inter-QSE Schedules | 50128 | Closing | 1.0b | 0.87 | <$100k | Jun-06
M | MO | PRR613 | Replacemnt Resrve Undr Sched Capacity Delineation | New | SIR Dlvry | 1.0b | 0.87 | N/A | N/A
MO Cut Line (Initial placement based on consolidated ERCOT PPL; MO Allocation = $2.44M) |  |  |  |  |  |  |  |  | 
M | RMS | PRR565 | Calculation of Losses for Settlement (RO x-fer) | 60068_01 | Not Started | 1.1 | 32.6 | <$100k | 2006
M | COPS |  | TML Phase 3 - Wholesale Enhancements | 40103_01 | Initiation | 1.1 | 7 | $500k-$1M | 2007
M | WMS | SCR747 | Removal of Price Administration for Zonal Congestion | 60080_01 | SO CART | 1.1 | 9.25 | <$100k | N/A
E | MO |  | Lodestar 4.0 Upgrade | 40066_04 | Initiation | 1.1 | 12 | $100k-$500k | 2007
M | MO | PRR598 | Extension of Credit Against OOM Start Up | New | Not Started | 1.1 | 12.1 | <$100k | 2006
E | MO |  | DC Tie Automation (Pk2 Only) | 50018_01 | SO CART | 1.1 | 14 | $100k-$500k | N/A
E | MO |  | Maestro Upgrade | 50137 | Execution | 1.1 | 16 | $100k-$500k | Oct-06
MO Capability Range (Line placement varies based on Forecasted Spend for Portfolio) |  |  |  |  |  |  |  |  | 
E | MO |  | MV90 Upgrade Part 2 - Installation of Software | 50033_02 | Closed | 1.1 | 21 | <$100k | Feb-06
M | MO | PRR602 | Ancillary Service Obligation for DC Tie Exports | New | Cancelled | 1.1 | 32.5 | N/A | N/A
E | MO |  | EDW Lodestar Decommission | 50030 | Execution | 1.1 | 44 | $100k-$500k | Feb-07
E | MO |  | REC Program Modifications | 60027_01 | Initiation | 1.2 | 61 | $100k-$500k | 2007

## Slide 3: MO Projects – Additional Detail
Closed/Closing
EDW BI Reporting
Settlement Mismatches Inter-QSE Schedules / Notification for Mismatched Inter-QSE Schedules
MV90 Upgrade, Pt. 2
Not Started
Calculation of Losses for Settlement
Extension of Credit Against OOM Start Up
Active
Enhancements to SCR727 - Market Access
Enhancements to SCR727 - Market Enhancements
Enhance ESIID Lookup Function
Lodestar Extracts
EPS Meter Data
TCR Report Enhancements Phase II
SCR 727 Phase II
TML Phase 3 - Wholesale Enhancements
Lodestar 4.0 Upgrade
Maestro Upgrade
Lodestar Data Archive Decommission
REC Program Modifications
Cancel/Transfer
PR 50024_03 – Enhancements to SCR727
PRR613, Replacement Reserve Under Scheduled Capacity Delineation
PR 60080_01 – Removal of Price Administration for Zonal Congestion
PR 50018_01 – DC Tie Automation (Pk2 Only)
PRR602, Ancillary Service Obligation for DC Tie Exports

## Slide 4: Completed or Near Completion
EDW BI Reporting
  PR 50004; Closed
  2006 Budget Range: <$100k
  PUCT project for implementation of a Business Intelligence (BI) Tool that will enable users to translate business questions into optimized queries. Supports consistent and efficient reporting for the PUCT, ERCOT, and eventually, MPs
Settlement Mismatches Inter-QSE Schedules & Notification for Mismatched Inter-QSE Schedules
  PR 50128; Closing
  2006 Budget Range: <$100k
  Market project to address PRR548 & PRR599
    PRR548: Reduce the quantities of energy “scheduled” by ERCOT into or from the Balancing Energy market during intervals in which Inter-QSE trades do not match. This will reduce ERCOT and Market Participants’ credit exposure to entities which submit mismatched inter-QSE trades
    PRR599: Notice be provided to both QSEs involved in a mismatch in the event that ERCOT remedies a mismatch as prescribed in PRR 548.
MV90 Upgrade, Pt. 2
  PR 50033_02; Closing
  2006 Budget Range: <$100k
  ERCOT project to install and implement the MV-90 software upgrade purchased in 2005. Support of the current product version ends in 2007

## Slide 5: Active
Enhancements to SCR727 - Market Access
  PR 50024_01; Execution
  2006 Budget Range: $500k-$1M
  Market project (SCR 740) to provide Market Participants access to SCR 727 ESIID level data in ERCOT systems via Web Services
Enhancements to SCR727 - Market Enhancements
  PR 50024_02; Initiation (combined with PR 50024_03)
  2006 Budget Range: $100k-$500k
  Additional sub-projects identified by ERCOT to purchase and implement the necessary hardware required by SCR740
Enhance ESIID Lookup Function
  PR 50025; Execution
  2006 Budget Range: $100k-$500k
  Market project (PRR312) to provide additional information for an ESI ID to include Station ID, Power Region, Premise Type, status (active/de-energized/inactive) for an ESI ID. In addition, advise if there is a pending Move In/Move Out for the ESI ID

## Slide 6: Active - continued
Lodestar Extracts (migrate to ODS)
  PR 40042_06; Execution (recently taken off hold)
  2006 Budget Range: $100k-$500k
  ERCOT project to migrate the Generation, Load, Settlements & Billing, and Shadow Pricing extracts from the Data Archive to the ODS (Operational Data Store)
EPS Meter Data
  PR 30026; Execution
  2006 Budget Range: <$100k
  Market project (PRR283/PIP204) to provide Resource ID data to Market Participant owners via extract
TCR Report Enhancements Phase II
  PR 40015_02; Execution
  2006 Budget Range: <$100k
  ERCOT project to deliver enhancements to reporting capabilities within the Transmission Congestion Rights (TCR) application

## Slide 7: Active - continued
SCR 727 Phase II
  PR 40007; Execution
  2006 Budget Range: $100k-$500k
  ERCOT project to transition SCR 727 Extract from the Data Archive to the Lodestar ODS environment
TML Phase 3 - Wholesale Enhancements
  PR 40103_01; Planning
  2006 Budget Range: $500k-$1M
  Market project (COPS) to focus on user experience enhancements of the Texas Market Link for Wholesale Market Participants. The goal is to incorporate additional functionalities and enhanced usability to fill in gaps between the current portal and the needs of QSEs, Transmission Operators and Resources
Lodestar 4.x Upgrade
  PR 40066_04; Initiation
  2006 Budget Range: $100k-$500k
  ERCOT project to maintain efficiency and reliability of the LodeStar application in order to enable ERCOT to meet Energy Aggregation and Billing & Settlements business needs

## Slide 8: Active - continued
Maestro Upgrade
  PR 50137; Execution
  2006 Budget Range: $100k-$500k
  ERCOT project to replace ERCOT’s current batch job scheduling software. The current scheduling software, Maestro, experiences issues outlined below:
    Maestro is currently not supported; major upgrade required
    Maintenance cost expensive due to CPU Pricing Model
    Security Risk – passwords not encrypted
    Preventing upgrade of DBMS and Operating System
    Uses a Proprietary Database
Lodestar Data Archive Decommission
  PR 50030; Planning (recently taken off hold)
  2006 Budget Range: $100k-$500k
  ERCOT project to transition LodeStar reporting to the EDW Lodestar/EMMS ODS
REC Program Modifications
  PR 60027_01; Initiation
  2006 Budget Range: $100k-$500k
  ERCOT project to port Renewal Energy Credit (REC) application from ASP to Java in order to efficiently continue support of this application. This project will now also address changes required by PUCT order

## Slide 9: New or Not Started
Calculation of Losses for Settlement
  Transfer from RO PPL
  PR 60068_01; Not yet started
  2006 Budget Range: <$100k
  Market project to address PRR565
    Modify the way distribution losses are calculated to be based on actual rather than forecasted ERCOT load
Extension of Credit Against OOM Start Up
  No PR assigned yet; Not yet started
  2006 Budget Range: <$100k
  Market project to address PRR598
    If MCPE is greater than Resource Category Generic Minimum Energy Cost, the difference will be credited against Startup Cost. This credit against Startup Cost shall continue until the earlier of: a) the end of the calendar day; or b) the credit has completely covered the startup payment

## Slide 10: Cancelled, Transferred, Non-project Delivery
PR 50024_03 – Enhancements to SCR727
  Cancelled, merged with another project
  Scope addressed HW required to support PR 50024_02. HW now included in scope of the _02 sub
New – PRR613, Replacement Reserve Under Scheduled Capacity Delineation
  Cancelled from MO as capital project; requirements delivered during MO monthly release of system enhancements
PR 60080_01 – Removal of Price Administration for Zonal Congestion
  Cancelled from MO, scope within SO
  ERCOT SCR analysis determined no impact to Settlements & Billing applications
PR 50018_01 – DC Tie Automation (Pk2 Only)
  Cancelled from MO; scope transferred to SO
  LodeStar requirements and changes covered under SO project, PR 50134, DC Tie Automation
New - PRR602, Ancillary Service Obligation for DC Tie Exports
  Cancelled from MO, PRR withdrawn by Market

## Slide 11: 2007 PPL DRAFT ERCOT Analysis – Top 22 *
Srce | Com | Src Doc | Project | Project No. | Curr Phase | DRAFT ERCOT 2007 PPL Impact
M | MO | SCR740 | Enhancements to SCR727 - Market Access | 50024_01 | Execution | Carry-over into 2007 (minimal budget)
M | MO | SCR740 | Enhancements to SCR727 - Market Enhancements | 50024_02 | Initiation | Carry-over into 2007 (minimal budget)
M | MO | SCR740 | Enhancements to SCR727 - Market Enhancements | 50024_03 | Cancelled | N/A – cancel from MO
M | MO | PRR312 | Enhance ESIID Lookup Function | 50025 | Execution | N/A – planned complete in 2006
P | MO |  | EDW BI Reporting Tool | 50004 | Closing | N/A – completes in 2006
E | MO |  | Lodestar Extracts | 40042_06 | Execution | N/A – planned complete in 2006
M | MO | PRR283 PIP204 | EPS Meter Data | 30026 | Execution | N/A – planned complete in 2006
E | MO |  | TCR Report Enhancements Phase II | 40015_02 | Execution | N/A – planned complete in 2006
E | MO |  | SCR 727 Phase II | 40007 | Execution | Carry-over into 2007 (minimal budget)
M | MO | PRR548 PRR599 | Settlement Mismatches Inter-QSE Schedules / Notification for Mismatched Inter-QSE Schedules | 50128 | Closing | N/A – completes in 2006
M | MO | PRR613 | Replacemnt Resrve Undr Sched Capacity Delineation | New | Cancelled | N/A – cancel from MO
MO Cut Line (Initial placement based on consolidated ERCOT PPL; MO Allocation = $2.44M) |  |  |  |  |  | 
M | RMS | PRR565 | Calculation of Losses for Settlement (x-fer from RO) | 60068_01 | Not Started | N/A – planned complete in 2006
M | COPS |  | TML Phase 3 - Wholesale Enhancements | 40103_01 | Initiation | Carry-over into 2007 Need COPS input – possible NODAL impacts
M | WMS | SCR747 | Removal of Price Administration for Zonal Congestion | 60080_01 | Cancelled | N/A – cancel from MO; x-fer to SO
E | MO |  | Lodestar 4.0 Upgrade | 40066_04 | Initiation | Carry-over into 2007
M | MO | PRR598 | Extension of Credit Against OOM Start Up | New | Not Started | N/A – planned complete in 2006
E | MO |  | DC Tie Automation (Pk2 Only) | 50018_01 | SO CART | N/A – cancel from MO; x-fer to SO
E | MO |  | Maestro Upgrade | 50137 | Execution | N/A – planned complete in 2006
MO Capability Range (Line placement varies based on Forecasted Spend for Portfolio) |  |  |  |  |  | 
E | MO |  | MV90 Upgrade Part 2 - Installation of Software | 50033_02 | Closed | N/A – completes in 2006
M | MO | PRR602 | Ancillary Service Obligation for DC Tie Exports | New | Cancelled | N/A – cancel from MO
E | MO |  | EDW Lodestar Decommission | 50030 | Execution | Carry-over into 2007 (minimal budget)
E | MO |  | REC Program Modifications | 60027_01 | Initiation | Carry-over into 2007
7 of the top 22 projects identified as carry-over projects into 2007
PLEASE NOTE: Analysis and 2007 PPL subject to change via additional PUCT, Market, & ERCOT input gathered during May-July 2006

## Slide 12
Adam D. Martinez
Mgr, Market Operations Divisional Projects Organization
ERCOT
(512) 248-3883
amartinez@ercot.com
Questions / Contact Information
Notes: <number>
<footer>
<header>
<date/time>