## How to USE this Workbook
Terms and Conditions Task Force
How to Use this Workbook
The purpose of this spreadsheet is to provide a brief description of the tabs in this workbook. As the issues evolve in the meetings, we will track the history of the Issues List and capture Action Items.
Tab Description | Spreadsheet TAB
Action Items captured in the May 8 and 9 meeting. Tab - 3. Action Items - May 8 & 9 | 3. Action Items
On May 8th and May 9th, the Terms and Conditions Task Force met at the Austin MET center. It was decided a new spreadsheet would be added using the previous speadsheet as the starting point. This is 2. 5-8-2006 & 5-9-2006 Combined. | 2. 5-8-2006 & 5-9-2006 Combined
The TDSPs authored the original Spreadsheet as a list of issues that would require market coordination to implement. The TDSP shared the issues spreadsheet with the CRs who added their reply. This is captured in the tab - 1. Impact TDSP Initial. | 1. Impact TDSP Initial

## 3. Action Items - May 8 & 9
Terms and Conditions Task Force Meeting
Action Items
May 8 & 9, 2006
Action Item Number | Rule Reference | Action Item | Responsibility | Date Due
1 | 4.3.6 | TDSP to provide information for CR review of distinctions to service address field. Example 123 Oak Street TEMP, Houston, TX | TDSPs | No later than May 24, 2006
2 | 4.3.6 | ERCOT will see if the portal is picking up the extended address. Need length for the Portal display. | ERCOT | No later than May 24, 2006
3 | 4.3.9 | CRs to recommend the time of year (month?/quarter?)for Critical Care (CC) annual reevaluation. | CRs | Low priority
4 | 4.3.4 | TX SET - Is a new reject code necessary to reject off cycle fee. CRs will evaluate need for new reject code prior to TX SET meeting. | TX SET | May 22, 2006 Meeting
5 | 4.4.3 | TX SET - Do we need a reject code when a re-bill comes in greater than 150 days? Note: 5 day reject rule applies. | TX SET | May 22, 2006 Meeting
6 | 4.7.2 | TCTF - Comprehensive review and revision of the process for estimation and denial of access that currently exists in the RMG. | TCTF - Bill Reily, Bevill, Robert Rodriguez, Chuck Moore, Kathy Scott, Cary Reed | May 24, 2006
7 | 4.3.7 | TX SET - will look at the Implementation Guide for potential transaction flow and grey box changes for the 814_PC process. | TX SET | 5/22/2006
8 | 4.4.5 | TX SET - Review the 820 Implementation guide for conformity with the rule. | TX SET | May 22, 2006
9 | 4.7.2 | Bill Reily - Convert PowerPoint to Word for RMG. | Bill Reily part of Action Item 6 | No later than 5-24-2006 to list serve
10 | 4.7.2 | TCTF - Document the Long Term process for all of section 4.7.2. TX SET will do the transactional solution. | Bill Reily part of Action Item 6 | 5/31/2006
11 | 4.8.3 | TX SET - Modify 810_02 existing “05” replacement code to allow for a new provision. | TX SET | May 22,2006
12 | 6.1.2.1 | TCTF - Review safety net process. | Suzette Sondag, Blake Gross Chuck Moore, Johnny Robertson, Alan Burke | May 24,2006
13 | 6.1.2.1 | TCTF - Review transaction timelines in Section 15 Protocols. | Zach Collard, Jennifer Garcia, Ann Boren, McCarty | May 22,2006
DRAFT

## 2. 5-8-2006 & 5-9-2006 Combined
| PROJECT NO. 29637 | [6 empty] | TCTF Project Impacts
Consensus TCTF Comments | RULEMAKING TO AMEND PUC SUBST. R. § 25.214 AND PRO-FORMA RETAIL DELIVERY TARIFF |  | TDSP Systems | TDSP Operational | Transactional (TX SET) | TDSP Comments |  | TX SET Change | Retail Market Guide | Protocols | Date | REP Comments
| §25.214 | [5 empty] | Reply to TDSP Comments | [5 empty] | TCTF Note
This document captures the changes requiring market coordination resulting from the Terms and Condition Rule dated April 20, 2006 which is effective May 11, 2006.
See discussion in 6.1.2.1 | 4.3.2.1 | INITIATION OF DELIVERY SYSTEM SERVICE WHERE CONSTRUCTION SERVICES ARE NOT REQUIRED | [6 empty] | ü | ü | 2006-07-15
Verified TDSPs are currently compliant. | 4.3.3 | REQUESTS FOR DISCRETIONARY SERVICES INCLUDING CONSTRUCTION SERVICES (Field Completion Date) |  |  |  | TDSPs currently comply with the Rule | We'd like to confirm that the Date stamp in the 650_02 reflects the field completion date. |  |  |  | 2006-07-15 | No change
Is a new reject code necessary to reject off-cycle fee on Mass Transition. CRs will evaluate need for reject code prior to TX SET | 4.3.4 | CHANGING OF DESIGNATED COMPETITIVE RETAILER (MASS TRANSITION REQUIREMENT) | ü | ü |  | TDSPs will need to modify systems to bill exiting CR rather than gaining CR for mass transitions. See related Chapter 6 changes. |  | ü | ü |  | 2007-07-01 | Only if a new reject code is needed to reject a charge for a special read that is estimated for a reason other than access or mass transition. | Reference 6.1.2.1 Action Item 4 - TX SET
Charge Change - Timing change explicit - Refer to Chapter 6 (TDSP and CR changes) | 4.3.4 | CHANGING OF DESIGNATED COMPETITIVE RETAILER | ü | ü | [6 empty] | 2007-07-01 |  | Reference 6.1.2.1
Multiple ESI Ids/ Addresses is the only change required in this rule - See Action Item 1 & 2 | 4.3.6 | IDENTIFICATION OF THE PREMISES AND SELECTION OF RATE SCHEDULES ( 5. Multiple ESI IDs only) | ü | ü | ü | [5 empty] | 2007-07-01 | No change | Action Item 1 & 2
Consistent application in use of transaction when red lining the guide | 4.3.7 | PROVISION OF DATA BY COMPETITIVE RETAILER TO COMPANY (814_PC) |  |  | ü | All CRs must provide 814_PC's |  | ü |  | ü | 2007-07-01 | 814_PC required by all CRs. May want to clarify required by all in same place the timing is clarified. | Action Item 7 - TX SET should look at transaction flow and gray box changes
TDSPs will use established processes for evaluating the application and reevaluating eligibility for CC customers. | 4.3.9 | CRITICAL CARE/CRITICAL LOAD CUSTOMER DESIGNATION |  | ü |  | TDSPs will use established processes for evaluating the application and reevaluating eligibility for CC customers. |  |  |  |  | 2006-07-15 | No change | Action Item 3
| 4.3.9.1 | Critical Care Residential Status | [6 empty] | ü |  | 2006-07-15 | Establish process for re-evaluating critical care eligibility. Synchronize, standardize.
Applies to 814_12 Date Change See 6.1.2.1 | 4.3.12.1 | MOVE OUT REQUESTS | ü | ü |  | All Move Out (MVO) requests must be received two (2) Business days prior to the date requested. MVOs not received with 2 B days notice, will be scheduled for 2 B days after the request is received. Any request received after 5:00 pm will be considered the next Business day. |  |  | ü | ü | 2006-07-15 | MVOs received 2 business days prior to the requested date must be done on requested date.
See discussion in section 6.1.2.1 Applies to standard reconnects only July 15, 2006 | 4.3.12.2 | DISCONNECTION DUE TO NON-PAYMENT OF COMPETITIVE RETAILER CHARGES; RECONNECTION AFTER DISCONNECTION | [6 empty] | ü |  | 2006-07-15 | Standard Reconnect received by 2pm shall be completed on same day
Disconnect for Non-pay - timing change - fix transaction timing matrix | 4.3.12.2 | DISCONNECTION DUE TO NON-PAYMENT OF COMPETITIVE RETAILER CHARGES; RECONNECTION AFTER DISCONNECTION | [6 empty] | ü | ü | 2007-07-01
Coordination for Clearance of Safety Issues is required and may not be accomplished in 3 days (NO CHANGE) | 4.3.13 | CUSTOMER REQUESTED CLEARANCE |  | ü |  | TDSP will comply with 3 days notice or upon mutual consent where safety issues exist. CRs should provide customer contact information to ensure timely completion. |  |  |  |  | 2006-07-15 | No change
Market Participants need to be in Compliance with ANSI X12 and 5 days on the 824 and bills transmitted no later 3 business day from scheduled meter read date | 4.4.1 | CALCULATION AND TRANSMITTAL OF DELIVERY SERVICE INVOICES | ü | ü |  | TDSPs will not process 824's received after days 5 of the 810 send date. TDSPs will comply with sending the 810 within 3 days of the Scheduled Meter Reading Date (SMRD). TDSPs will develop a request and response process for information requests on billing determinants. | There may be some REP concern that this could leave an item hanging open. REPs would like to discuss implications of receiving no notice/response in this scenario. |  |  |  | 2006-07-15 | Rejects for ANSI X12 must be re-sent within two business days.
Action Item 5 - Reject Code when rebill > 150 days | 4.4.3 | INVOICE CORRECTIONS | ü | ü |  | TDSPs will comply with proposed changes. |  |  |  |  | 2007-07-01 | New Reject Reason for 810 charges billed >150 days after original. | Action Item 5 - Reject Code when rebill > 150 days
Action Item #8 - Texas SET needs to coordinate language between the 820 Implementation Guide and the rule. | 4.4.5 | REMITTANCE OF INVOICED CHARGES | ü | ü | ü | The CRs payment will be considered received on the date company's bank receives the Electronic File Transfer (EFT) or Wire Transfer (WT) and the appropriate remittance advice is received by company in accordance with the requirements specified by Applicable Legal Authority (ALA). (EFT or WT and 820 - Remittance Advice must match) | What is the TX SET change required for this section? | ü | ü | ü | 2006-07-15 | No change
Action Item 6 - | 4.7.2.Manual Work Around | METER READING | ü | ü | ü | Beginning 7/15/06 CenterPoint, TXU ED and TNMP will provide monthly to each CR in it's service area a spreadsheet listing their premises with 2 or more consecutive estimates due to denial of access. The spreadsheet will include the reason for denial. AEP does this automatically via the 810_02 transaction. 7/1/07 this spreadsheet will be replaced with the automated process. |  |  | ü |  | 2006-07-15 | Temporary Manual Process Required.
Action Item #10 - Document the Long Term Process for Denial of Access. (Change the PowerPoint to Word) | 4.7.2.1 | DENIAL OF ACCESS BY RETAIL CUSTOMER | ü | ü | ü | TDSP will use a standard door hanger. TDSPs will propose a change to TX SET with: 1.Reason for estimate (by type) 2.Counter for number of consecutive estimates 3.Yes/No indicator for door hanger. 4.Method for the CR to request reconnect after access issue is resolved | REPs aren't sure about the fourth item, need to talk about the details of this one. | ü | ü |  | 2007-07-01 | Details of long-term process required for 2007. | Action Item 6 Following "DNA", how does CR request RN
Action Item #10- Document the Long Term Process for all section 4.7.2 Texas SET does transactional solution - Process by TCTF (Change the PowerPoint to Word) | 4.7.2.2 | ESTIMATES FOR REASONS OTHER THAN FOR DENIAL OF ACCESS BY RETAIL CUSTOMER | ü | ü | ü | TDSPs will provide the reason for estimate whether access or other. List of common codes will be provided to TX SET. |  | ü | ü |  | 2007-07-01 | No change
TDSP will comply | 4.7.4 | METER TESTING | ü | ü |  | 1.TDSPs will comply with the 10day and 30 day timelines for testing 2. TDSPs will track meter test history by meter 3. TDSPs will report all test result information required by the rule and pass to CR in the 650 comments field 4. TDSPs propose metrics be established to track volume of meter test requests by CR. |  |  |  |  | 2006-07-15 | No change
Action Item 5 - Reject Code when rebill > 150 days same as 4.4.3 note: 5 day reject rule applies rmg7.7.1 | 4.7.5 | INVOICE ADJUSTMENT DUE TO METER INACCURACY (150 day) | ü | ü |  | TDSPs will comply with 150 day limitation rule |  |  | ü |  | 2006-07-15 | No change
TNP and CenterPoint are in compliance. AEP AND TXU ED will comply by 2007 | 4.8.1 | DATA FROM METER READING (web access for all non residential customers) |  | ü |  | AEP and TXU ED will implement a process to accommodate all non residential historical usage on their web portal. | REPs request clarification on this section for all TDSPs. Not sure why AEP and TXU ED are singled out here. |  |  |  | 2007-07-01 | Historical usage requested by LOA must be provided within 3 business days. Don't think change is required?
TDSP will comply | 4.8.1.3 | OUT-OF-CYCLE METER READS | ü | ü |  | 7/15/06 all TDSPs will comply |  |  |  |  | 2006-07-15 | Meter re-reads must be completed within 5 business days of CR request.
TDSP will comply with the 2006 Requirement | 4.8.1.4 | ESTIMATED USAGE (Smoothing) | ü | ü |  | Smoothing will occur anytime the ESI ID has been estimated 2 or more consecutive months. |  |  | ü |  | 2006-07-15 | Company shall provide the reason for estimation. Smoothing required under certain circumstances.
Action Item 11 - TX SET will modify existing 05 code to allow for new provision Section 4.8.3 | 4.8.3 | ADJUSTMENTS TO PREVIOUSLY TRANSMITTED DATA (Replacement) | ü |  | ü | Anytime the TDSP submits a cancel/rebill the 810 & 867_03 will have a replacement code. TX SET needs to redefine the existing "05" code. |  | ü | ü |  | 2007-07-01 | Replacement indicator on 810 and 867. Replacements required within one business day.
Multiple ESI Ids/ Addresses is the only change required in this rule - 5. Multiple ESI Ids | 5.3.5 | SELECTION OF RATE SCHEDULES | ü | ü |  | Same as 4.3.6 |  | ü | ü | ü | 2007-07-01 | For two or more ESI IDs at the same service address, service address must distinguish between them. Gray box TX SET change
5.3.7.4
Timing Change Only | 5.4.6 | RETAIL CUSTOMER'S DUTY REGARDING COMPANY'S FACILITIES ON RETAIL CUSTOMER'S PREMISES (streetlight/security light repair) | ü | ü |  | TDSPs will comply |  |  |  |  | 2006-07-15 | No change
If the request is received less than 2 business days prior to the requested date the Move In (MVI) will be scheduled for the business day that is 2 business days after the date the request is received. This process also applies to safety net and date change requests (814_12).Action Item 12 - Review the Safety Net Process | 6.1.2.1 | STANDARD DISCRETIONARY SERVICES - (Standard Move-In) | ü | ü |  | If the request is received less than 2 business days prior to the requested date the MVI will be scheduled for the business day that is 2 business days after the date the request is received. This process also applies to safety net and date change requests (814_12). |  |  | ü |  | 2006-07-15 | For all Discretionary Services, need to clean up the Retail Market Guide (maybe just refer to Chapter 6).
1.TDSPs will make every attempt to work priority requests received before 5pm the same business day, but will not exceed the close of the next business day. 2. Priority orders received after 5pm will be considered received on the next business day. | 6.1.2.1 | STANDARD DISCRETIONARY SERVICES - (Priority Move-In) | ü | ü |  | 1.TDSPs will make every attempt to work priority requests received before 5pm the same business day, but will not exceed the close of the next business day. 2. Priority orders received after 5pm will be considered received on the next business day. | Was this row highlighted intentionally? What about TDSPs that don't offer priority Move In (MVI)? |  | ü | ü | 2007-07-01 | Review as priority for potential Retail Market Guide (RMG) Revision
If the request is received less than 2 business days prior to the requested date the MVO will be scheduled for the business day that is 2 business days after the date the request is received. This process also applies to date change requests (814_12). | 6.1.2.1 | STANDARD DISCRETIONARY SERVICES - (Move-Out) | ü | ü |  | If the request is received less than 2 business days prior to the requested date the MVO will be scheduled for the business day that is 2 business days after the date the request is received. This process also applies to date change requests (814_12). |  |  | ü | ü | 2006-07-15
Coordination for Clearance of Safety Issues is required and may not be accomplished in 3 days (NO CHANGE) 4.3.13 | 6.1.2.1 | STANDARD DISCRETIONARY SERVICES - (Customer Requested Clearance) | ü | ü |  | TDSPs will comply |  |  |  |  | 2006-07-15 | Review as priority for potential RMG Revision
1.Pending clarification from staff on same day and holiday DNPs. 2.DNP request received less than 2 business days prior to the requested date will be scheduled for the business day that is 2 business days after the request is received. 3.The 3 day completion time frame will require the TDSPs to work DNPs on Fridays. This will require CRs to revisit their DNP processing and may require those that are not presently available on Saturdays to be available for customer calls. | 6.1.2.1 | STANDARD DISCRETIONARY SERVICES - Disconnect for Non-Pay (DNP) | ü | ü |  | 1.Pending clarification from staff on same day and holiday DNPs. 2.DNP request received less than 2 business days prior to the requested date will be scheduled for the business day that is 2 business days after the request is received. 3.The 3 day completion time frame will require the TDSPs to work DNPs on Fridays. This will require CRs that are not presently available on Saturdays to be available for customer calls. | REPs don't necessarily agree that all REPs will need to be available on Saturdays to take calls. For example, a REP could confine DNP requested dates to Mondays of weeks with no holidays. We may also want to discuss the possibility of Unexecuting DNPs on Fridays for certain scenarios. |  | ü |  | 2007-07-01
Standard reconnect requests received by Company prior to 2pm on a business day shall be reconnected that day. Standard reconnect requests received by Company prior to 5pm on a business day shall be reconnected that day if possible, but no later than the close of Company's next field operational day. Standard reconnect requests received by Company after 5pm on a day that is not a business day shall be considered received on the next business day. | 6.1.2.1 | STANDARD DISCRETIONARY SERVICES - Reconnect After DNP (Standard) | ü | ü |  | Standard reconnect requests received by Company prior to 2pm on a business day shall be reconnected that day. Standard reconnect requests received by Company prior to 5pm on a business day shall be reconnected that day if possible, but no later than the close of Company's next field operational day. Standard reconnect requests received by Company after 5pm on a day that is not a business day shall be considered received on the next business day. |  |  | ü |  | 2006-07-15
Same day reconnect requests received by Company prior to 5pm on a business day shall be reconnected no later than the close of Company's field operational day. | 6.1.2.1 | STANDARD DISCRETIONARY SERVICES - Reconnect After DNP (Same Day Reconnect) | ü | ü |  | Same day reconnect requests received by Company prior to 5pm on a business day shall be reconnected no later than the close of Company's field operational day. |  |  | ü |  | 2007-07-01 | Review as priority for potential RMG Revision
TS flag in POLR Drop transaction necessary for fee to departing CR on final bill | 6.1.2.1 | STANDARD DISCRETIONARY SERVICES - (Out Of Cycle Meter Reads) | ü | ü | ü |  |  | ü | ü |  | 2007-07-01 |  | Reference 4.3.4
Draft
Draft

## 1. Impacts TDSP Initial
PROJECT NO. 29637 |  | Impact Estimations
RULEMAKING TO AMEND PUC SUBST. R. § 25.214 AND PRO-FORMA RETAIL DELIVERY TARIFF |  |  | TDSP Systems | TDSP Operational | Transactional (TX SET) | TDSP Comments
§25.214 | [6 empty] | REP Comments | Approved TCTF
4.3.3 | REQUESTS FOR DISCRETIONARY SERVICES INCLUDING CONSTRUCTION SERVICES |  |  |  |  | TDSP's currently comply with the Rule | We'd like to confirm that the Date stamp in the 650_02 refelcts the field completion date.
4.3.4 | CHANGING OF DESIGNATED COMPETITIVE RETAILER |  | ü | ü |  | TDSP's will need to modify systems to bill exiting CR rather than gaining CR for mass transitions. See related Chpt. 6 changes.
4.3.6 | SELECTION OF RATE SCHEDULES |  | ü | ü | ü | See Chpt. 6 issues, For duplicate addresses each TDSP will use existing descriptors and populate on the address field.
4.3.7 | PROVISION OF DATA BY COMPETITIVE RETAILER TO COMPANY |  |  |  | ü | All CR's must provide 814_PC's
4.3.9 | CRITICAL CARE/CRITICAL LOAD CUSTOMER DESIGNATION |  |  | ü |  | TDSPs will use established processes for evaluating the application and reevaluating eligibility for CC customers.
4.3.12.1 | MOVE OUT REQUESTS |  | ü | ü |  | All MVO request must be received two (2) Business days prior to the date requested. MVO's not received with 2 B days notice, will be scheduled for 2 B days after the request is received. Any request received after 5:00 pm will be considered the next Business day.
4.3.13 | CUSTOMER REQUESTED CLEARANCE |  |  | ü |  | TDSP will comply with 3 days notice or upon mutual consent where safety issues exist. CRs should provide customer contact information to ensure timely completion.
4.4.1 | CALCULATION AND TRANSMITTAL OF DELIVERY SERVICE INVOICES |  | ü | ü |  | TDSP's will not process 824's received after days 5 of the 810 send date. TDSPs will comply with sending the 810 within 3 days of the SMRD. TDSPs will develop a request and response process for information requests on billing determinants. | There may be some REP concern that this could leave an item hanging open. REPs would like to discuss implications of receiving no notice/response in this scenario.
4.4.3 | INVOICE CORRECTIONS |  | ü | ü |  | TDSPs will comply with proposed changes.
4.4.5 | REMITTANCE OF INVOICED CHARGES |  | ü | ü | ü | The CRs payment will be considered received on the date company's bank receives the EFT or WT and the appropriate remittance advice is received by company in accordance with the requirements specified by ALA.(EFT or WT and 820 must match) | What is the TX SET change required for this section?
4.7.2 | METER READING *see attached PowerPoint |  | ü | ü | ü | TDSPs will propose a change to TX SET with: 1.Reason for estimate (by type) 2.Counter for number of consecutive estimates 3.Yes/No indicator for door hanger. 4.Method for the CR to request reconnect after access issue is resolved | REPs aren't sure about the fourth item, need to talk about the details of this one.
4.7.2.1 | DENIAL OF ACCESS BY RETAIL CUSTOMER |  | ü | ü | ü | TDSPs will use a standard door hanger.
4.7.2.2 | ESTIMATES FOR REASONS OTHER THAN FOR DENIAL OF ACCESS BY RETAIL CUSTOMER |  | ü | ü | ü | TDSPs will provide the reason for estimate whether access or other. List of common codes will be provided to TX SET.
4.7.2.Manual | METER READING |  | ü | ü | ü | Beginning 7/15/06 CenterPoint, TXU ED and TNMP will provide monthly to each CR in it's service area a spreadsheet listing their premises with 2 or more consecutive estimates due to denial of access. The spreadsheet will include the reason for denial. AEP does this automatically via the 810_02 transaction. 7/1/07 this spreadsheet will be replaced with the automated process.
4.7.4 | METER TESTING |  | ü | ü |  | 1.TDSPs will comply with the 10day and 30 day timelines for testing 2. TDSPs will track meter test history by customer 3. TDSPs will report all test result information required by the rule and pass to CR in the 650 comments field 4. TDSPs propose metrics be established to track volume of meter test requests by CR.
4.7.5 | INVOICE ADJUSTMENT DUE TO METER INACCURACY |  | ü | ü |  | TDSPs will comply with 150 day limitation rule
4.8.1 | DATA FROM METER READING |  |  | ü |  | AEP and TXU ED will implement a process to accommodate all non residential historical usage on their web portal. | REPs request clarification on this section for all TDSPs. Not sure why AEP and TXU ED are singled out here.
4.8.1.3 | OUT-OF-CYCLE METER READS |  | ü | ü |  | 7/15/06 all TDSPs will comply
4.8.1.4 | ESTIMATED USAGE (smoothing) |  | ü | ü |  | Smoothing will occur anytime the ESI ID has been estimated 2 or more consecutive months.
4.8.3 | ADJUSTMENTS TO PREVIOUSLY TRANSMITTED DATA |  | ü |  | ü | Anytime the TDSP submits a cancel/rebill the 810 & 867_03 will have a replacement code. TX SET needs to redefine the existing "05" code.
5.3.5 | SELECTION OF RATE SCHEDULES |  | ü | ü |  | Same as 4.3.6
5.4.6 | RETAIL CUSTOMER'S DUTY REGARDING COMPANY'S FACILITIES ON RETAIL CUSTOMER'S PREMISES (streetlight/security light repair) |  | ü | ü |  | TDSPs will comply
6.1.2.1 | STANDARD DISCRETIONARY SERVICES - Standard Move-In |  | ü | ü |  | If the request is received less than 2 business days prior to the requested date the MVI will be scheduled for the business day that is 2 business days after the date the request is received. This process also applies to safety net and date change requests (814_12).
6.1.2.1 | STANDARD DISCRETIONARY SERVICES - Priority Move-In |  | ü | ü |  | 1.TDSPs will make every attempt to work priority requests received before 5pm the same business day, but will not exceed the close of the next business day. 2. Priority orders received after 5pm will be considered received on the next business day. | Was this row highlighted intentionally? What about TDSPs that don't offer priority MVI?
6.1.2.1 | STANDARD DISCRETIONARY SERVICES - Move-Out |  | ü | ü |  | If the request is received less than 2 business days prior to the requested date the MVO will be scheduled for the business day that is 2 business days after the date the request is received. This process also applies to date change requests (814_12).
6.1.2.1 | STANDARD DISCRETIONARY SERVICES - Customer Requested Clearance |  | ü | ü |  | TDSPs will comply
6.1.2.1 | STANDARD DISCRETIONARY SERVICES - Disconnect for Non-Pay (DNP) |  | ü | ü |  | 1.Pending clarification from staff on same day and holiday DNPs. 2.DNP request received less than 2 business days prior to the requested date will be scheduled for the business day that is 2 business days after the request is received. 3.The 3 day completion time frame will require the TDSPs to work DNPs on Fridays. This will require CRs that are not presently available on Saturdays to be available for customer calls. | REPs don't necessarily agree that all REPs will need to be available on Saturdays to take calls. For example, a REP could confine DNP requested dates to Mondays of weeks with no holidays. We may also want to discuss the possibility of Unexecuting DNPs on Fridays for certain scenarios.
6.1.2.1 | STANDARD DISCRETIONARY SERVICES - Reconnect After DNP (Standard) |  | ü | ü |  | Standard reconnect requests received by Company prior to 2pm on a business day shall be reconnected that day. Standard reconnect requests received by Company prior to 5pm on a business day shall be reconnected that day if possible, but no later than the close of Company's next field operational day. Standard reconnect requests received by Company after 5pm on a day that is not a business day shall be considered received on the next business day.
6.1.2.1 | STANDARD DISCRETIONARY SERVICES - Reconnect After DNP (Same Day Reconnect) |  | ü | ü |  | Same day reconnect requests received by Company prior to 5pm on a business day shall be reconnected no later than the close of Company's field operational day.
Draft