Terms and Conditions Task Force

Timeline for Implementation

Version 2

| TCTF agreement on issues matrix | May 9 2006 |
| --- | --- |
| TCTF agreement on TX SET changes | June 1 2006 |
| TCTF develop Protocol/RMG revisions | June 2006 |
| TX SET requirements agreed | July 2006 TX SET meeting |
| Tariff stipulated implementation on with the exceptions specifically stated TDSPs to implement standard MVI, MVO, standard reconnect, meter re-reads and spreadsheets identifying inaccessible meters | July 15 2006 |
| TX SET change requests complete, final guidelines posted | September 1 2006 |
| Protocol Changes and Retail Market Guide changes for submission | September 1 2006 |
| MP/ERCOT Detailed design begins | September 1 2006 |
| MP/ERCOT Build/Development begins | October 20 2006 |
| MP/ERCOT Build/Development complete | March 20 2007 |
| MP/ERCOT UAT activities begin | March 20 2007 - estimate |
| MP/ERCOT should be complete with all internal changes and UAT testing and all known error/defects resolved | April 28 2007 |
| Market Connectivity testing begins | April 28 2007 – (kick off) – through May 12 2007 – to be verified |
| Market Testing begins Flight 0507 | May 15 2007 – to be verified |
| Market Testing ends – production connectivity for new CRs | June 23 2007 |
| Market shutdown for transactions | June 28, 29, 30 2007 |
| Cut-over Implementation date for items exempt from July 15, 2006 Mass Transition needs to be considered for cross impacts | June 30 - July 1 2007 |
| Consensus 5-8-2006 |  |