## Slide 1: Terms & Conditions Task Force
RMS Update
June 14, 2006

## Slide 2: Terms & Conditions Task Force
TCTF Significant Events…
  March 14th
    Role and Responsibility, Scope and Purpose
  May 8th and 9th
    Time line, Issues Matrix and Action Items
  May 31st and June 1st
    TCTF Protocol Team – Transaction Timing
    Safety Net Team - RMGRR
    Estimation/Denial of Access
  June 12th and June 13th
    Agreement of Protocol Changes
    Progress on Estimation and Safety Net

## Slide 3: Terms & Conditions Task Force
Implementation Timeline
TCTF agreement on issues matrix May 9 2006
TCTF agreement on TX SET changes June 1 2006
TCTF develop Protocol/RMG revisions June 2006
TX SET requirements agreed July 2006
Tariff stipulated implementation July 15 2006
TX SET change requests complete Sept 1 2006
Protocol and RMGRR submitted Sept 1 2006
MP/ERCOT Detailed design begins Sept 1 2006
MP/ERCOT Build/Development begins Oct 20 2006
MP/ERCOT Build/Develop complete March 20 2007
MP/ERCOT UAT activities begin March 20 2007
MP/ERCOT UAT complete April 28 2007
Market Connectivity testing begins April 28 2007
Market Testing begins Flight 0507 May 15 2007
Market Testing ends June 23 2007
Cut-over Implementation June 30 - July 1 2007

## Slide 4: Terms & Conditions Task Force
Issue Resolution
Each section of the rule was closely analyzed for Market Impact
Required system or process change?
Require a TX SET Change?
Require a Protocol or Retail Market Guide Change?
Identified Action Items
Developed Teams to resolve/recommend resolution

## Slide 5: Terms & Conditions Task Force
TCTF Significant Events…
  March 14th
    Role and Responsibility, Scope and Purpose
  May 8th and 9th
    Time line, Issues Matrix and Action Items
  May 31st and June 1st
    TCTF Protocol Team – Transaction Timing
    TCTF Safety Net Team - RMGRR
    TCTF Estimation/Denial of Access
  June 12th and June 13th
    Agreement of Protocol Changes
    Progress on Estimation and Safety Net

## Slide 6: Terms & Conditions Task Force
TCTF Significant Events…
  March 14th
    Role and Responsibility, Scope and Purpose
  May 8th and 9th
    Time line, Issues Matrix and Action Items
  May 31st and June 1st
    TCTF Protocol Team – Transaction Timing
    Safety Net Team - RMGRR
    Estimation/Denial of Access
  June 12th and June 13th
    Agreement of Protocol Changes
    Progress on Estimation and Safety Net

## Slide 7: Terms & Conditions Task Force
Wrapping It Up…
Identify any Remaining Implementation Issues
Resolve all Outstanding Action Items
Complete Texas SET Business Requirements
Develop Protocol Changes
Recommend Retail Market Guide Modifications
Implement TX SET 3.0