| SCR Number | 748 | PRR Title | Website Enhancements for ERCOT Outage Notifications |
| --- | --- | --- | --- |
| Impact Analysis Date |  | 06/06/2006 |  |
| Cost/Budgetary Impact |  | $250,000 - $500,000 In addition, there is a potential cost for ongoing maintenance which will be confirmed during project planning. |  |
| Estimated Project Time Requirements* *Unless otherwise indicated, project time requirements begin upon project initiation. |  | Implementation of this SCR will take 6 - 9 months from project initiation, assuming no resource constraints. Following is a breakdown of the estimated project timeline: - Business process development (1 month) - Application development (3 - 4 months) - Integration testing (1 - 2 months) - Deployment (1 - 2 months) |  |
| ERCOT Staffing Impacts (across all areas) |  | There will be a temporary impact to existing ERCOT staff for development of the functionality proposed by this SCR in the following groups: - Web and Data Services - Enterprise Architecture - Retail Client Services - Wholesale Client Services - Commercial Operations - Console Operations - Release Management There is an ERCOT staff impact in the following groups: Commercial Operations (1 FTE) and Console Operations (2 FTEs). |  |
| ERCOT Computer System Impacts |  | This SCR describes systems changes as the addition of functionality on the ERCOT website(s) for: - Calendar of dates/times for planned outages affecting retail - Unplanned Outage Notice with web message capability - Log of outages Business processes to support communications to the market on ERCOT system events have not yet been confirmed between ERCOT and the market. For the purpose of this Impact Analysis, assumptions (listed below) have been made regarding the business requirements of this SCR. These assumptions and other requirements are to be confirmed or corrected as part of the project planning process. Any modification of assumptions or requirements during the project planning process will be reflected in the estimates of project time, cost, etc. - In Scope: - Calendar of dates/times for planned outages affecting retail – scope includes the following systems: - NAESB Proxy Servers - TCH - Electronic Data Interchange (EDI) PaperFree - Enterprise Application Integration (EAI) - Customer Registration Database (Siebel) - Texas Market Link (TML) including reporting capabilities - MarkeTrak - Enterprise Data Warehouse (EDW) - Settlements and Billing Services (Lodestar) - ERCOT email servers - Unplanned Outage Notice with web message capability – scope includes the following systems: - NAESB Proxy Servers - TCH - Electronic Data Interchange (EDI) PaperFree - Enterprise Application Integration (EAI) - Customer Registration Database (Siebel) - Texas Market Link (TML) including reporting capabilities - MarkeTrak - Enterprise Data Warehouse (EDW) - Settlements and Billing Services (Lodestar) - ERCOT email servers Notification could be specific to retail processing/systems initially or could include both retail and wholesale eventually. - Log of outages There will be only one (1) log of outages. This one (1) log could include retail initially, and wholesale eventually. Delivery mechanism of the log is to be determined during project planning. Service/application information could be presented on Texas Market Link (TML). - Out of Scope: services/systems not specifically stated above as in scope. - Security aspects: - A cross-reference of names of commercial off-the-shelf applications to business process services/applications would be refined by ERCOT and posted on TML. - For both the Calendar of dates/times for planned outages affecting retail and the Unplanned Outage Notice with web message capability: - Service/application information could be presented on www.ercot.com with no information that can be considered confidential or restricted. - Confidential or restricted information includes: - Technical information about the ERCOT network, applications, IP addresses, server names, and other infrastructure details. - Names of commercial off-the-shelf applications. - Log of outages Delivery mechanism of the log is to be determined during project planning. Service/application information could be presented on Texas Market Link (TML) with limited confidential information. - Cannot include technical information about the ERCOT network, applications, IP addresses, server names, and other infrastructure details. - Processes proposed by this SCR will be triggered once ERCOT staff has determined that an unplanned outage is in progress. - This SCR will not modify availability of technical or business analysis during ERCOT non-business hours. - Following determination that an unplanned outage is in progress, the types of notification for the Unplanned Outage Notice with web message capability will be: - Status notification: - Initial notification (identification that service is not available, but technical or business analysis not yet available) to be sent as soon as it is determined that an unplanned outage is in progress. - Notification regarding end of outage (service is restored).to be sent as soon as it is determined that an outage has been corrected. - Business follow-up on significant events (outages over 24 hours) - Follow-up notification, multiple updates depending on the duration of the outage (progress reports and reporting of impacts to other systems), would be updated on the next business day. - Summary of lessons learned and any mitigation action taken by ERCOT. - While source data is assumed to exist in the current suite of applications, data gathering and delivery mechanism required by this SCR must be developed, tested, and deployed. - Delivery of information to the website will not be completely automated. Some ERCOT staff effort will be required for quality assurance of data prior to notification posting. - Notifications posted on the website and corresponding email notifications will have identical wording. Any difference in wording could increase the volume of calls to Service Desk. - Source of data for notification posting will primarily be from two sources: - Service Desk - for tracking of unplanned outages - Release Management - for a calendar of planned outages Given these assumptions, implementation of this SCR would impact the following system/process areas: - ERCOT Service Desk - Release Management Portal - TML - ERCOT.com - Application interfaces between the above systems |  |
| ERCOT Business Function Impacts |  | Business processes to support communications to the market on ERCOT system events have not yet been confirmed between ERCOT and the market. Given the assumptions above, implementation of this SCR would impact the following business process areas: - Commercial Operations - Console Operations - Release Management - Retail Client Services - Wholesale Client Services |  |
| Grid Operations & Practices Impacts |  | No additional operations required. |  |

Alternatives for a More Efficient Implementation (include explanation of impacts)

NA

Evaluation of Interim Solutions (e.g., manual workarounds)

Notification process for outages that is currently in place includes information sent to Market Participants by the ERCOT Client Services group using listserves.

Feasibility of Implementation

Resource availability Project work for SCR748 has the potential to impact resources on the following projects: - PR-40103 – TML Phase 3 Wholesale Enhancements - PR-60077 – ERCOT.com Secured Area Enhancements - PR-60006 – ERCOT Outage Evaluation & Resolution - PR-60050 – Texas Set 3.0 / PR-40038 – Mass Customer Transition / PR-60008 – Terms and Conditions Requirements - PR-60013 – Enhance Digital Certificate Program - Texas Nodal Market Impact to other projects - Technical dependency with 002COPMGRR to coordinate the implementation of 002COPMGRR’s 1) system notifications on www.ercot.com and 2) the log of outages. - There is an opportunity to leverage the synergy between 002COPMGRR and SCR748. At this time, both SCR748 and 002COPMGRR are pending approval. Assuming both revision requests are approved, the opportunity to combine the SCR748 and 002COPMGRR efforts can be reviewed.

Comments

The SCR also needs to be coordinated with COPMGRR002, an effort currently underway by the COPS Communications Working Group to improve and standardize the communication process to the market on ERCOT system events including the timing of notifications.