## RO
RO 2007 Project Prioritization - PUCT, Market and ERCOT Projects
Main Sort | Source | Committee | Prog Area | Source Doc | Project | Project No. | Current Status | Project Manager | Expected Completion | 2007 Priority | 2007 Rank | 2006 Priority | 2006 Rank | 2007 Budget Range | Nodal Impact | Nodal Impact Comments | Priority Approval | 2005 Priority | 2005 Rank | CBA Score | Net Benefit | 2006 Budget Range | 2006 Running Range | Summary Description | Benefit Summary | 2007 PPL PR/IA Complete | 2007 PPL T&C Complete | 2007 PPL CBA Complete | 2007 PPL Documentation Action Item / Notes
1120 | Market | RMS | RO | PRR660 | Mass Customer Transition | 40038_01 | Initiation | Munson | 2007 | 0 - Carryover | 1 | 1.2 | 54 |  |  |  |  | 3.3 | 132 | 16 | 3100000 | $1M-$3M | $46M-$48M | Certain circumstances may arise during the course of business in the Texas retail electric market that may necessitate the transition of ESI IDs from one CR to another or one TDSP to another in quantities and on a time frame that is not completely supported by standard market transactions or business processes. For a detailed outline of the business process and responsibility of all Entities involved in the transition, refer to the approved RMS Retail Customer Transition procedures documented in the Retail Market Guide. | Estimated savings of $100k per year per TDSP and $100k per year per POLR CR. | N | N | N | Need Market input
1090 | ERCOT | RO | RO |  | EDW Siebel Transition | 50059_01 | Planning | Ray | 2007 | 0 - Carryover | 2 | 1.1 | 26 | <$100k |  |  |  | 2.1 | 72.5 | 23 | 448938 | $500k-$1M | $36M-$38M | Transition of Siebel reporting from Data Archive to Enterprise Data Warehouse | Fewer ad hoc data requests (4 hours per workday), less production support of data archive (4 hours per workday), improved daily research of Siebel service order changes (8 hours per workday) | Y | Y | Y | Complete
1130 | ERCOT | RO | RO |  | ESI ID Account Table Split | 60015_01 | Not Yet Started | Haynes | 2007 | 0 - Carryover | 3 | 1.1 | 23 | $100k-$500k | [5 empty] | 18 | 891464 | $100k-$500k | $36M-$38M | Normalize type of data associated to business objects. Multiple business objects are using the same tables which are growing large causing performance and scalability issues. | Increased efficiences in development and integration time as well as end user interaction (approximately 12 hours per day) | Y | Y | Y | Complete
1140 | ERCOT | RO | RO |  | EDW TCH (Transaction Clearinghouse) Transition | 50060_01 | Planning | Ray | 2007 | 0 - Carryover | 4 | 1.1 | 27 | <$100k |  |  |  | 2.1 | 72 | 23 | 743338 | $100k-$500k | $38M-$40M | Transition of TCH reporting from Data Archive to Enterprise Data Warehouse | Fewer ad hoc data requests (4 hours per workday), less production support of data archive (4 hours per workday), improved daily research of Siebel service order changes (8 hours per workday) | Y | Y | Y | Complete
| ERCOT | RO | RO |  | ETS (ESIID Tracking System) Transition to EDW | 50088_01 | Not Yet Started |  | 2007 | 0 - Carryover | 5 | 1.1 | 29 | $500k-$1M |  |  |  | 2.3 | 106 | 21 | 1240143 | $500k-$1M | $38M-$40M | Transition of ETS reporting from Data Archive to Enterprise Data Warehouse | Improved reporting and analysis efficiency (7 hours per workday); Improved development efficiencies (16 hours per workday) | Y | Y | Y | Complete
1150 | ERCOT | RO | RO |  | EDW EAI Transition (inc. PaperFree & NAESB) | 50061_01 | Not Yet Started |  | 2007 | 2 - High | 6 | 1.1 | 28 |  |  |  |  | 2.1 | 72 | 23 | 743338 | $100k-$500k | $38M-$40M | Transition of EAI reporting from Data Archive to Enterprise Data Warehouse | Fewer ad hoc data requests (4 hours per workday), less production support of data archive (4 hours per workday), improved daily research of Siebel service order changes (8 hours per workday) | Y | Y | Y | Complete
| ERCOT |  | RO |  | EIS Siebel to L* Data Comparison | New | New |  | New | 2 - High | 7 | N/A | N/A | $100k-$500k | [5 empty] | 17 | 390000 |  |  |  |  | Y | Y | Y | S. Egger to follow-up on CBA
| Market | ERCOT | RO |  | MarkeTrak Enhancements (Workflow & Reporting) | New | New |  | New | 2 - High | 8 | N/A | N/A | $500k-$1M | [5 empty] | 16 | 740000 |  |  |  |  | Y | Y | Y | Complete
2360 | Market | RMS | RO | RMGRR26 | TDSP to TDSP Transition Process | New | Not Yet Started |  | TBD | 2 - High | 9 | 3.1 | 139.5 |  |  |  | TAC 11/3/2005 |  |  | 14 | 1400000 | $1M-$3M | $70M-$80M | Certain circumstances may arise during the course of business in the Texas retail electric market that may necessitate the transition of ESI IDs from one CR to another or one TDSP to another in quantities and on a time frame that is not completely supported by standard market transactions or business processes. For a detailed outline of the business process and responsibility of all Entities involved in the transition, refer to the approved RMS Retail Customer Transition procedures documented in the Retail Market Guide. | Estimated savings of $100k per year per TDSP and $100k per year per POLR CR. | N | N | N | Need Market input
| ERCOT |  | RO |  | Exception Reporting / Monitoring Enhancements | New | New |  | New | 2 - High | 10 | N/A | N/A | $100k-$500k | [5 empty] | 9 | 400000 |  |  |  |  | Y | Y | Y | S. Egger to follow-up on CBA
| ERCOT |  | RO |  | Systematic Exception Reprocessing Functionality | New | New |  | New | 2 - High | 11 | N/A | N/A | $500k-$1M | [5 empty] | 8 | 40000 |  |  |  |  | Y | Y | Y | Need T&C doc in file folder
1500 | ERCOT |  | RO |  | Transition of Production Reporting to EIS - Retail | New | New |  | New | 2 - High | 12 | N/A | N/A | $100k-$500k | [5 empty] | 21 | 80000 |  |  |  |  | Y | Y | Y | Complete
1760 | ERCOT | RO | RO |  | Integration of Commercial Operations Data in EIS (formerly known as Web services that integrate L* and Siebel data for MPs) | 60028_01 | Not Yet Started |  | 2007 | 2 - High | 13 | 1.2 | 62 | $100k-$500k | [5 empty] | 18 | 246591 | $100k-$500k | $50M-$52M | Provide enhanced access to both Siebel and Lodestar data via web services. | Market benefit: fewer D2D and DEV FasTrak issues (8 hours per workday for 25 CRs) | Y | Y | Y | Complete
1790 | ERCOT | RO | RO |  | 867 inbound map rewrite | 60042_01 | Not Yet Started |  | TBD | 3 - High / Medium | 14 | 1.3 | 89 | $100k-$500k | [5 empty] | 11 | 7793706 | $100k-$500k | $58M-$60M | Re-Write of Inbound 867 maps to Increase Efficiency, Reliability and Stability of ERCOT transaction data processing |  | Y | Y | Y | Complete
2190 | Market | RMS | RO |  | Retail Enhancements to TML - Ph 4 | 50058_01 | Not Yet Started |  | TBD | 3 - High / Medium | 15 | 2.2 | 126 |  |  |  |  | 2.1 | 70 | 16 | -960000 | $500k-$1M | $70M-$80M |  |  | N | N | N | Need Market input
2140 | ERCOT | RO | RO |  | 814 inbound XML rewrite (impacts input from portal only) | 60043_01 | Not Yet Started |  | TBD | 3 - High / Medium | 16 | 1.3 | 92 | $100k-$500k | [5 empty] | 13 | 444532 | $100k-$500k | $58M-$60M | Re-Write of Inbound 814 XML maps to Increase Efficiency, Reliability and Stability of ERCOT transaction data processing. |  | Y | Y | Y | Complete
| ERCOT | RO | RO |  | EDI Transaction logging | 60062_01 | Not Yet Started |  | TBD | 3 - High / Medium | 17 | 2.2 | 128 | $100k-$500k | [5 empty] | 14 | 74851 | $100k-$500k | $70M-$80M | Change the Paper Free application system to log all ANSI records to TRLOG and to log all TXSET records to a new table which will better support current and future business needs. |  | Y | Y | Y | Complete
| ERCOT |  | RO |  | 997 records logged to ETS (or ETS Replacement) | New | New |  | New | 3 - High / Medium | 18 | N/A | N/A | $100k-$500k | [5 empty] | 11 | 90000 |  |  |  |  | Y | Y | Y | Complete
2260 | Market | RMS | RO | SCR742 | Automated Retail Transaction Verification | 60064_01 | Not Yet Started |  | TBD | 3 - High / Medium | 19 | 2.3 | 132 |  |  |  | BoD 8/19/2005 | 1.3 | 56.5 | 13 | 3400000 | $500k-$1M | $70M-$80M | Build interface to existing Market Certification environment This option involves building automation and an integrated user interface to the existing market certification environment. |  | N | N | N | Need Market input
1560 | ERCOT |  | RO |  | MID reporting enhancements | New | New |  | New | 3 - High / Medium | 20 | N/A | N/A | [7 empty] | 0 |  |  |  |  | Y | N | N | T&C needs input from Chase, Grantham, Stanley
2060 | ERCOT | RO | RO |  | Commercial Apps - Calendar Consolidation | 60033_01 | Not Yet Started |  | TBD | 3 - High / Medium | 21 | 1.2 | 69 | $100k-$500k |  | - |  |  |  | 23 | 740000 | $100k-$500k | $52M-$54M | Develop single business calendar for use by all retail applications | Reduced rework for both market and ERCOT by eliminating possibility of out of sync conditions between multiple business calendars (50 hours per year of data repair activity for CRs and TDSPs) | Y | Y | Y | Complete
2080 | ERCOT | RO | RO |  | Name to DUNS conversion | 60059_01 | Not Yet Started |  | TBD | 4 - Medium | 22 | 2.1 | 120 | $100k-$500k | [5 empty] | 14 | 14148 | $100k-$500k | $60M-$70M | Change the Paper Free application system to utilize DUNS numbers as opposed to Market Participant company names. |  | Y | Y | Y | Complete
2200 | ERCOT | RO | RO |  | MP configuration Table | 60060_01 | Not Yet Started |  | TBD | 4 - Medium | 23 | 2.1 | 122 | $100k-$500k | [5 empty] | 18 | -325 | $100k-$500k | $60M-$70M | Remove all of the MPDB.conf files in the MB/PF systems and consolidate all of the configurations into a single table. The complexity of adding new MP to the system must be reduced in order to remove the number of errors that are encountered when adding / modifying MP information. |  | Y | Y | Y | Complete
2090 | ERCOT/MKT | RO | RO |  | Create Retail XML Transaction Format to MPs - set the national standard | 60065_01 | Not Yet Started |  | TBD | 9 - Parking Lot |  | 2.3 | 134 | [7 empty] | 0 | $100k-$500k | $70M-$80M |  |  | N/A | N/A | N/A | No docs needed for Parking Lot items
950 | PUCT | RMS | RO | ??? | Performance Measures Reporting Requirements (changes to Project 24462) | 60007_01 | Not Yet Started |  | TBD | 9 - Parking Lot |  | 1.1 | 9 | [6 empty] | 18 | -1000000 | $1M | $16M-$18M | Expected project needed to enhance reporting systems as a result of T&Cs requirements effecting PUCT Performance Measures Project 24462 | TBD | N | N | N | Need Market input
1910 | Market | RMS | RO | SCR745 | ERCOT Outage Evaluation and Resolution (TDTWG)--Phase III | 60006_02 | Not Yet Started |  | TBD | 9 - Parking Lot |  | 1.2 | 58.5 |  |  |  | BoD 12/13/05 |  |  | 24 | 25200000 | $1M-$3M | $48M-$50M | Identify market facing servers without redundancy. Implement new code and hardware when possible to eliminate single points of failure. This will include clustering market facing servers and implementing code which will be able to switch from one system to the other without an outage. This project may be addressed in SCR-745 | Savings based on cost estimates of data cleanup due to outages: 4 large incidents per year at $25k each; 20 small incidents per year at $5k each. | N | N | N | Need Market input
2120 | Market | RMS | RO | SCR737 | Estimated Meter Read Data | 50091_01 | Not Yet Started | Follow up w/Mkt Rules | TBD | 9 - Parking Lot |  | 1.3 | 86 |  |  |  | TAC 9/9/2004 | 3.1 | 111 | 7 | 500000 | $100-$500k | $58M-$60M | Create a calendar month, summary report to be presented at RMS that will provide Market Participants with estimated meter reading information broken-down by TDSP territory and indicating customer class. This report will also indicate the degree to which meter reads occur consecutively across two or more months and the degree to which estimates may straddle Move-Ins and Move-In/Forced Outs. |  | N | N | N | Need Market input
920 | ERCOT | RO | RO |  | SOA Extend Footprint | 60010_01 | Not Yet Started |  | Never | DELETE | N/A | 1.1 | 13 | [6 empty] | 21 | 3226908 | $1M-$3M | $26M-$28M | This project will continue the strategic implementation, approved by the BoD, of Service Oriented Architecture (SOA) using TIBCO technology. It includes: o Continued replacement of integration points within ERCOT with TIBCO technology. o Implementation of new business processes to address replacement of outdated automated and/or manual business processes. | Internal ERCOT savings due to manual process reduction and reduction in project manual processes; reduction of licensing in software products replaced by TIBCO | N/A | N/A | N/A | Not expected to carry into 2007
2530 | ERCOT | RO | RO |  | Enhance Digital Certificate Program | 60013_01 | X-fer | N/A | x-fer to IO | DELETE | N/A | 1.1 | 17 | [6 empty] | 15 | 4074838 | $100k-$500k | $32M-$34M | ERCOT is implementing a 2005 project, VeriSign Upgrade Project (PR 40107), that is upgrading ERCOT’s digital certificate technology from the vendor’s Lite to the Enterprise version. This 2006 project is a follow-up that will take advantage of features/enhancements in the Enterprise version not included in the scope of the 2005 project. | Estimated savings: 6 hours of maintenance per digital certificate per year | N/A | N/A | N/A | Removed from list for 2007
2220 | Market | RMS | RO | PRR565 | Calculation of Losses for Settlement | 60068_01 | X-fer | N/A | x-fer to MO | DELETE | N/A | 1.1 | 32.6 |  |  |  | TAC 9/8/2005 |  |  |  |  | <$100k | $42M-$44M |  |  | N/A | N/A | N/A | Removed from list for 2007
1530 | ERCOT | RO | RO |  | Enhancements to Retail Test Website | 60031_01 | Not Yet Started |  | Never | DELETE | N/A | 1.2 | 65 | [6 empty] | 12 | 499743 | $100k-$500k | $50M-$52M | This project will provide increased efficiency and agility to the testing of Retail Market Participants. It also provides additional reporting and produces existing reporting in a more expeditious manner. | Market benefit: For each day that is reduced in the length of a market test flight, each MP could reduce their expenditure no the flight by 1/2 FTE for that day | N/A | N/A | N/A | Removed from list for 2007
1730 | ERCOT | RO | RO |  | SIR enhancements - RO | 60041_01 | Not Yet Started |  | Never | DELETE | N/A | 1.2 | 85 | [6 empty] | 17 | 69333 | $500k-$1M | $58M-$60M | To implement RO-SIR enhancements using internal ERCOT resources | Dependent on nature of SIR enhancements | N/A | N/A | N/A | Removed from list for 2007
1830 | ERCOT | RO | RO |  | Enhancements to ERCOT.com (enhancements not included in PR-40106) | 60046_01 | Not Yet Started |  | Never | DELETE | N/A | 1.3 | 96 | [6 empty] | 18 | 950476 | $100k-$500k | $60M-$70M |  |  | N/A | N/A | N/A | Removed from list for 2007
1940 | ERCOT | RO | RO |  | Web based ERCOT 101 training | 60051_01 | Not Yet Started |  | Never | DELETE | N/A | 2.1 | 107 | [7 empty] | 0 | $500k-$1M | $60M-$70M |  |  | N/A | N/A | N/A | Removed from list for 2007
1990 | ERCOT | RO | RO |  | L* Retail POC (Proof of Concept) | 60052_01 | Not Yet Started |  | Never | DELETE | N/A | 2.1 | 112 | [6 empty] | 15 | -602009 | $500k-$1M | $60M-$70M |  |  | N/A | N/A | N/A | Removed from list for 2007
2010 | ERCOT | RO | RO |  | MP Automation of Manual Cancels | 60053_01 | Not Yet Started |  | Never | DELETE | N/A | 2.1 | 114 | [7 empty] | 0 | <$100k | $60M-$70M |  |  | N/A | N/A | N/A | Removed from list for 2007
2030 | ERCOT | RO | RO |  | Siebel GUI-Based Data Validation Improvements | 60056_01 | Not Yet Started |  | Never | DELETE | N/A | 2.1 | 117 | [7 empty] | 0 | <$100k | $60M-$70M |  |  | N/A | N/A | N/A | Removed from list for 2007
820 | ERCOT | RO | RO |  | Publish / subscribe self services / communications | 60061_01 | Not Yet Started |  | Never | DELETE | N/A | 2.1 | 123 | [7 empty] | 0 | $500k-$1M | $70M-$80M |  |  | N/A | N/A | N/A | Removed from list for 2007
110 | ERCOT | RO | RO |  | Unified Member Account Management View | 60067_01 | Not Yet Started |  | Never | DELETE | N/A | 2.3 | 136 | [7 empty] | 0 | $100k-$500k | $70M-$80M |  |  | N/A | N/A | N/A | Removed from list for 2007
160 | ERCOT | RO | RO |  | Automate Internal Surveys | 60069_01 | Not Yet Started |  | Never | DELETE | N/A | 3.1 | 141 | [6 empty] | n/a | n/a (3.x priority) |  | $70M-$80M |  |  | N/A | N/A | N/A | Removed from list for 2007
170 | ERCOT | RO | RO |  | Outage notification system & storage facility (centralized) | 60071_01 | Not Yet Started |  | Never | DELETE | N/A | 3.1 | 145 | [6 empty] | n/a | n/a (3.x priority) |  | $70M-$80M |  |  | N/A | N/A | N/A | Removed from list for 2007
2280 | Market | RMS | RO | PRR241 | UFE Analysis | 30022_01 | X-fer | N/A | x-fer to MO | DELETE | N/A | 3.2 | 147 |  |  |  | BoD 6/19/2001 | 3.2 | 122 | n/a | n/a (3.x priority) |  | $70M-$80M | 1) Revises the beginning date for UFE analysis in Section 11.5.1 to January 2002. 2) Modifies the language in 11.5.2.1 to accommodate a December 1, 2001 implementation timeline. 3) Adds language in 11.5.2.1 to require TDSPs to leave "old control area" boundary meters in place until UFE analysis zones are defined. Definition of zones to take place after June 1, 2001 but supporting December 1, 2001 deadline. |  | N/A | N/A | N/A | Removed from list for 2007
2320 | Market | RMS | RO | PRR385 | DLC Implementation | - | X-fer | N/A | x-fer to MO | DELETE | N/A | 3.3 | 150 |  |  |  | BOD 5/20/2003 |  |  | n/a | n/a (3.x priority) |  | $70M-$80M | This PRR will allow the DLC programs to be appropriately profiled and ERCOT systems to properly process DLC programs. |  | N/A | N/A | N/A | Removed from list for 2007
2510 | Market | RMS | RO | PRR478 | Use of Lagged Dynamic Samples for New Load Profiles | 40056_01 | X-fer | N/A | x-fer to MO | DELETE | N/A | 3.3 | 151 |  |  |  | BOD 02/17/2004 | 2.2 | 85 | n/a | n/a (3.x priority) |  | $70M-$80M | This is a change to the method for creating Load Profiles allowing for the use of lagged dynamic samples for new profiles adopted subsequent to market open. |  | N/A | N/A | N/A | Removed from list for 2007
180 | ERCOT | RO | RO |  | Market Meeting Electronic Voting | 60072_01 | Not Yet Started |  | Never | DELETE | N/A | 3.3 | 165 | [6 empty] | n/a | n/a (3.x priority) |  | $70M-$80M |  |  | N/A | N/A | N/A | Removed from list for 2007
185 | ERCOT | RO | RO |  | Administration of Enrollment Notifications | 60074_01 | Not Yet Started |  | Never | DELETE | N/A | 3.3 | 167 | [6 empty] | n/a | n/a (3.x priority) |  | $70M-$80M |  |  | N/A | N/A | N/A | Removed from list for 2007
1205 | Market | RMS | RO | ??? | Terms and Conditions requirements, not limited to Texas SET changes | 60008_01 | Not Yet Started |  | TBD | DELETE |  | 1.1 | 10 | [6 empty] | 17 | -500000 | $500k | $18M-$20M | To implement Public Utility Regulations as they relate to the establishment of non-discriminatory terms and conditions of retail delivery service, including delivery service to a Retail Customers provided by a transmission and distribution utility (TDU). Certain transactions and system processes must be created and others modified to accomplish the regulatory requirements. | TBD | N | N | N | Need Market input
1740 | Market | COPS | RO | SCR743 | Settlement Disputes Extract (QSE Dispute Extract) | 60022_01 | Not Yet Started | N/A | x-fer to MO | DELETE |  | 1.2 | 55 |  |  |  | BoD 9/20/2005 | 1.2 | 35.8 | 19 | 660000 | <$100k | $46M-$48M | Provide QSEs detailed information regarding all submitted settlement disputes. The current method of looking up disputes via the ERCOT Texas Market Link Portal has several limitations, including manually reviewing Dispute ID’s one at a time. | Estimated savings of 8 hours per year for 50 QSEs due to improved dispute tracking | N | N | N | Need Market input
2180 | Market | RMS | RO |  | Texas Set 2.2 | 60050_01 | Not Yet Started |  | TBD | DELETE |  | 2.1 | 105 | [6 empty] | 15 | 3862239 | $500k-$1M | $60M-$70M | This is a place holder for new TxSet version 2.2 for 2006 |  | N | N | N | Need Market input
2340 | Market | RMS | RO | SCR734 | CSA Report for CRs | 50057_01 | Not Yet Started | Follow up w/Mkt Rules | Put in RMG | DELETE |  | 2.3 | 133 |  |  |  | TAC 9/28/2005 | 2.1 | 69 | 8 | 200000 | $100k-$500k | $70M-$80M | Provide CR’s with an on-demand extract capability to retrieve CSA (Continuous Service Agreement) data for their DUNS via the ERCOT Portal |  | N | N | N | Need Market input Reclassify as ERCOT?
2370 | Market | RMS | RO | SCR736 | TML ESIID TXN Portal Flag | 50100_01 | Not Yet Started | Include with TML P4 | TBD | DELETE |  | 3.2 | 148 |  |  |  | TAC 9/9/2004 | 3.2 | 123 | n/a | n/a (3.x priority) |  | $70M-$80M | Append a data Flag of “P” to the Transaction Type number to indicate when a displayed transaction was generated and transmitted through the Texas Market Link portal by Market Participants, rather than being generated by Market Participant’s system and transmitted in the Market via GISB. |  | N | N | N | Need Market input
1030 | Market | RO | RO | SCR738 | Enhancement to FasTrak Tools | 50007_01 | Execution | Segovia | 2006 | N/A | N/A | 1 | 0.03 |  |  |  | TAC 9/9/2004 | 1.1 | 9 | 20 | 18300000 | $1M-$3M | $2M-$4M | FasTrak is the retail transaction issue resolution tool. The system currently in place does not include the capability to track issues by variables such as ESI ID or TDSP, and does not allow determination of issue aging. In addition, the tool cannot be queried and interfacing with the tool is somewhat cumbersome. The FasTrak tool needs to be made more user friendly and enhanced with features that will allow issues to be better tracked and manipulated by Market Participants for purposes of better managing the retail transaction issue resolution process. | Significant direct cost savings and time efficiencies for CRs and TDSPs. CBA estimates varying amounts of savings depending on size of market participant. | N/A | N/A | N/A | Not expected to carry into 2007
980 | ERCOT | RO | RO |  | Service Oriented Architecture (formerly EAI Upgrade/Replacement - PR40066-06) | 50121 | Execution | Prince | 2006 | N/A | N/A | 1 | 0.08 |  |  |  |  | 1.1 | 17 | 21 | 3244060 |  | $4M-$6M | The Service Oriented Architecture (SOA) project is comprised of a series of sub-projects designed to implement a service-oriented architecture – a collection of services on a network that communicate with one another, making it easier to integrate applications. The goals of SOA include the following: o Replace SeeBeyond EAI technology with TIBCO EAI technology; o Deploy Service Oriented Architecture (SOA) methodology/framework; o Deploy sufficient TIBCO licensing footprint to support ERCOT’s future integration needs through 2007. | Expected efficiency gain of 32% on current application interface development time. Reduced need for data center expansion due to consolidation of application interface activities in a common architecture. | N/A | N/A | N/A | Not expected to carry into 2007
1410 | ERCOT | RO | RO |  | Endpoint Services - Phase I | 50121_06 | Closing | Thomas | 2006 | N/A | N/A | 1 | 0.08 |  |  |  |  | 1.1 | 17 | 21 | 3244060 | $100k-$500k | $4M-$6M |  |  | N/A | N/A | N/A | Not expected to carry into 2007
1430 | ERCOT | RO | RO |  | Retail Business Processes | 50121_07 | Execution | Prince | 2006 | N/A | N/A | 1 | 0.08 |  |  |  |  | 1.1 | 17 | 21 | 3244060 | $1M-$3M | $4M-$6M |  |  | N/A | N/A | N/A | Not expected to carry into 2007
1470 | ERCOT | RO | RO |  | Endpoint Services - Phase II | 50121_08 | Execution | Prince | 2006 | N/A | N/A | 1 | 0.08 |  |  |  |  | 1.1 | 17 | 21 | 3244060 | <$100k | $4M-$6M |  |  | N/A | N/A | N/A | Not expected to carry into 2007
40 | ERCOT | RO | RO |  | TX SET 2.1 | 40034_01 | Closing | Chudgar | 2006 | N/A | N/A | 1 | 0.09 |  |  |  |  | 1.1 | 6 | 15 | -4800000 | <$100k | $4M-$6M | To implement changes to retail transactions as identified by TX SET in support of the RMS directed Task Forces, DNP, TITF, and 810/867/824 Workgroup for the Texas Electric Retail Market… 1. Support the MOU/EC entrance, 2. Disconnect for Non-Pay process, 3. Communication of additional billing determinants to the ERCOT's Electric Retail Market | Enhancements to systems to accommodate MOU/EC participants into the Retail Electric Market; enhancements to billing determinants for better customer service by the CR | N/A | N/A | N/A | Not expected to carry into 2007
910 | ERCOT | RO | RO |  | 2005 SIR Enhancements (ETS/DA/DW/TS/CARR/Portal) | 50026_01 | Execution | Haynes | 2006 | N/A | N/A | 1 | 0.89 |  |  |  |  | 1.2 | 35 |  |  | $100k-$500k | $10M-$12M |  |  | N/A | N/A | N/A | Former place-holder. To Be Replaced by Other Projects if needed in 2007
1115 | Market | RMS | RO | SCR745 | ERCOT Outage Evaluation and Resolution (TDTWG)--Phases I and II | 60006_01 | Planning | Thomas | 2006 | N/A | N/A | 1.1 | 8 |  |  |  | BoD 12/13/05 |  |  | 24 | 25200000 | $1M-$3M | $16M-$18M | Identify market facing servers without redundancy. Implement new code and hardware when possible to eliminate single points of failure. This will include clustering market facing servers and implementing code which will be able to switch from one system to the other without an outage. This project may be addressed in SCR-745 | Savings based on cost estimates of data cleanup due to outages: 4 large incidents per year at $25k each; 20 small incidents per year at $5k each. | N/A | N/A | N/A | Not expected to carry into 2007
2345 | ERCOT | MO | RO |  | ERCOT.com Secured Area | 60077_01 | Planning | Haynes | 2006 | N/A | N/A | 1.1 | 25.5 |  |  |  |  | 2.1 | 72.5 |  |  | $100k-$500k | $36M-$38M |  |  | N/A | N/A | N/A | Not expected to carry into 2007