| COPMGRRNumber | 002 | COPMGRR Title | Section 4, Unplanned Outage Communication Process |
| --- | --- | --- | --- |
| Impact Analysis Date |  | 06/20/2006 |  |
| Cost/Budgetary Impact |  | $250,000 - $500,000 In addition, there is a potential cost for ongoing maintenance which will be confirmed during project planning. |  |
| Estimated Project Time Requirements* *Unless otherwise indicated, project time requirements begin upon project initiation. |  | Implementation of this COPMGRR will take 5 – 8 months from project initiation, assuming no resource constraints. Following is a breakdown of the estimated project timeline: - Business requirements (1 month) - Application development (2 - 3 months) - Integration testing (1 - 2 months) - Deployment (1 - 2 months) |  |
| ERCOT Staffing Impacts (across all areas) |  | There will be a temporary impact to existing ERCOT staff for development of the processes proposed by this COPMGRR in the following groups: - Web and Data Services - Enterprise Architecture - Retail Client Services - Wholesale Client Services - Commercial Operations - Console Operations Ongoing support cannot be absorbed by current staff. There is an ERCOT staff impact in the following groups: Commercial Operations (1 FTE) and Console Operations (2 FTEs). |  |
| ERCOT Computer System Impacts |  | The 002COPMGRR proposes a documented and standardized communication process around unplanned outage events or interruption in any of the market services it provides to Market Participants, and the needed escalation process to stakeholder subcommittees. This impact analysis outlines system changes to support the communication process, including: - Unplanned Outage Notice with web message capability - E-mail notification identical to the web message - Log of outages and posting of the log Business processes to support communications to the market on ERCOT system events have not yet been confirmed between ERCOT and the market. For the purpose of this Impact Analysis, assumptions (listed below) have been made regarding the business requirements of this COPMGRR. These assumptions and other requirements are to be confirmed or corrected as part of the project planning process. Any modification of assumptions or requirements during the project planning process will be reflected in the estimates of project time, cost, etc.: - In Scope: All Services and Systems listed in the cross-reference of service to notice template in CCWG Recommendation Report for this COPMGRR. This includes both retail and wholesale services. - Out of Scope: services/systems not specifically stated above as in scope. - Log of outages: There will be only one log of outages. This one log is the same log to be implemented by SCR748. (The CCWG Recommendation Report references a 24x7 and a Business Day log to be posted to a webpage.) - Security aspects: - A cross-reference of names of commercial off-the-shelf applications to business process service/application would be refined by ERCOT and posted on TML. - Notifications could include service/application information with no information that can be considered confidential or restricted. Confidential or restricted information includes: - Technical information about the ERCOT network, applications, IP addresses, server names, and other infrastructure details. - Names of commercial off-the-shelf applications. - Log of outages: Delivery mechanism of the log is to be determined during project planning. Service/application information could be presented on Texas Market Link (TML) with limited confidential information. The information cannot include technical information about the ERCOT network, applications, IP addresses, server names, and other infrastructure details. - Processes proposed by this COPMGRR will be triggered once ERCOT staff has determined that an unplanned outage is in progress. - This COPMGRR will not modify availability of technical or business analysis during ERCOT non-business hours. - Following determination that an unplanned outage is in progress, the types of notification for the Unplanned Outage Notice with web message capability will be: - Status notification: - Initial notification (identification that service is not available, but technical or business analysis not yet available) to be sent as soon as a determination that an unplanned outage is in progress has been made - Notification regarding end of outage (service is restored); to be sent as soon as it is determined that the outage has been corrected. - Both initial and end of outage notifications could be posted on www.ercot.com, with corresponding e-mail notification sent to a defined distribution list developed by ERCOT Client Services. - Business Follow-up on significant events (outages over 24 hours) - Follow-up notification, multiple updates depending on the duration of the outage (progress reports and reporting of impacts to other systems), would be updated on the next business day; and - Summary of lessons learned and any mitigation action taken by ERCOT, if any, within one week following the end of an unplanned outage. - Delivery of information will not be completely automated. Some ERCOT staff effort will be required for quality assurance of data prior to notification posting. - Notifications posted on the website and corresponding email notifications will have identical wording. Any difference in wording could increase the volume of calls to Service Desk. - Source of addressees for notification posting will be from Client Services – for defined list of both initial and end of outage notifications for each business process service/application in scope. Given these assumptions, implementation of this COPMGRR would impact the following system/process areas: - ERCOT Service Desk - TML - ERCOT.com - Application interfaces between the above systems |  |
| ERCOT Business Function Impacts |  | Given the assumptions above, implementation of this COPMGRR would impact the following business process areas: - Commercial Operations - Console Operations - Retail Client Services - Wholesale Client Services |  |
| Grid Operations & Practices Impacts |  | No additional operations required. |  |

Alternatives for a More Efficient Implementation (include explanation of impacts)

NA

Evaluation of Interim Solutions (e.g., manual workarounds)

Notification process for outages that is currently in place includes information sent to Market Participants by the ERCOT Client Services group using listserves.

Feasibility of Implementation

Resource availability Project work for COPMGRR002 has the potential to impact resources on the following projects: - SCR748, Website Enhancements for ERCOT Outage Notifications - Texas Nodal Market Impact to other projects - Technical dependency with SCR748 to coordinate the implementation of 002COPMGRR’s system notifications on www.ercot.com and the log of outages. - There is an opportunity to leverage the synergy between 002COPMGRR and SCR748. At this time, both SCR748 and 002COPMGRR are pending approval. Assuming both revision requests are approved, the opportunity to combine the SCR748 and 002COPMGRR efforts can be reviewed.

Comments

The COPMGRR also needs to be coordinated with SCR748.