## Goals for 2006
DSWG Goals for 2006
Item # | DSWG Goal | Deliverable | Target Date | Primary Owner | Team Members | Status
1 | Identify a permanent solution for negative LaaR bidding | List of solution alternatives identified, comparative analysis completed, and PRR's introduced | End of 2nd Quarter | Mary Anne Brelinsky | Steve Krein | ☑
2 | Develop a description of demand side opportunities for the Nodal Market Design | HTML document that has been peer reviewed and posted to the ERCOT website | End of 4th Quarter | George Arnold | Jay Zarnikau | PUC to initiate a Rule Making Project that will further define rules for load participation in Nodal Market Design
3 | Develop a Price Responsive Load Participation Program for all customer segments | Program concept and preliminary analysis completed. Present to WMS for market feedback an next steps | End of 4rd Quarter | Malcolm Smith | Jay Zarnikau, Dan Austin, George Arnold | In Progress
4 | Submit comments from an Ad Hoc Group from the DSWG on Proposed Rules for Resource Adequacy and Automated Metering | Comments to Proposed Rules filed with the PUCT | End of 1st Quarter | Jay Zarnikau | Malcolm Smith | ☑
5 | Compare demand response resource programs being run in other ISO markets | Report Completed and Posted to ERCOT Website | End of 3rd Quarter | Steve Isser | Steve Krein, Jay Zarnikau | Steve I. will replace Fred Y as leader. Preliminary data being collected.
6 | Identify by market segment: a. customer ability to respond to prices b. barriers to participation c. proposed solutions to remove those barriers | Market assessment and basis for ERCOT's reporting requirements under the PUCT Proposed Rule 25.505. | End of 4th Quarter | Steve Krein | All | Not started, pending release of new PUCT Rule on Resource Adequacy.
7 | Identify demand side program opportunities to solve a once in ten year loss of load type event | Present analysis and recommendations to WMS | End of 1st Quarter | Steve Krein | All | ☑
8 | Update the current description of demand side opportunities on the ERCOT website and include status update for Replacement Reserve | HTML document that has been peer reviewed and posted to the ERCOT website | End of 2nd Quarter | Mary Anne Brelinsky | Steve Krein | ☑