## IO
2007 Project Prioritization - PUCT, Market and ERCOT Projects
Main Sort | Source | Committee | Prog Area | Source Doc | Project | Project No. | Status | Project Manager | 2007 Priority | 2007 Rank | 2006 Priority | 2006 Rank | 2007 Budget Range | 2007 Running Range | Nodal Impact | Nodal Impact Comments | Priority Approval | 2005 Priority | 2005 Rank | CBA Score | Net Benefit | Summary Description | Benefit Summary
967 | ERCOT | IO | IO |  | EDW EMMS Decommission | 50031 | Initiation | McLain/Wilkinson | 0 - Carryover | 0.1 | 1.1 | 11.7 |  | <$2M | Resource Impact | required to free up system / infrastructure resources to meet nodal demands. Unable to support new EMMS with existing version of Oracle. |  | 1.2 | 39 | 29 | 81234 | Transition reporting to the EDW Lodestar/EMMS ODS. | Reduction of support costs of over 50% (10 hours per day to 4 hours per day)
880 | PUCT | IO | IO |  | EIS Conformed Data Warehouse Foundations | 60004_01 | Initiation | McLain/Wilkinson | 0 - Carryover | 0.2 | 1.1 | 5 |  | <$2M | None |  |  |  |  | 29 | 48620154 | Roll out the architecture and framework for the next generation data warehouse environment. This project is in direct support of Section 17 of the Protocols and is a required element to directly support the PUCT and the Market. | Market cost savings equates to 2 hours of savings per day per participant, through optimized access to data, additional data access, and analytical processes to be rolled out at a later time through data marts
890 | PUCT | IO | IO |  | EIS CDW Data Marts | 60005_01 | On Hold Possibly be Absorbed into 50088 and Cancelled -or- Moved to RO/MO |  | 0 - Carryover | 0.3 | 1.1 | 6 | $500k-$1M | <$2M | None |  |  |  |  | 25 | 24350470 | Roll out first wave of data marts in the next generation data warehouse environment. | Market cost savings equates to 1 hour of savings per day per participant, through optimized access to data, additional data access, and analytical processes to be rolled out at a later time through data marts
2330 | ERCOT | IO | IO |  | Enhance Digital Certificate Program | 60013_01 | Start June/July |  | 0 - Carryover | 0.4 | 1.1a | 17 |  | <$2M | None |  |  | 2.2 | 95 | 15 | 4074838
| ERCOT | IO | IO |  | Enterprise Service Management | 60055_01 | Initiation | Wilkinson | 0 - Carryover | 0.5 | 1.1 | 25.7 | $500k-$1M | <$2M | None |  |  |  |  | 16 | 0
| ERCOT | IO | IO |  | Cisco NAC Appliances | New | Not Yet Started |  | 1 - Critical | 1 |  |  | $100k-$500k | <$2M | None | allow remote connectivity to enable mobile workforce |  |  |  | 20 | -300000 | (includes (4) appliances and software) This will allow ERCOT to check AV, Alteris, patch-level, and other criteria prior to access to ERCOT systems. This will enable ERCOT to be certain that only ERCOT authorized computing devices have the ability to access the Network. This will allow for corporate users to connect to any network port at any ERCOT facility.
| ERCOT | IO | IO |  | Citrix Rebuild | New | Not Yet Started |  | 1 - Critical | 2 |  |  | $500k-$1M | $2M-$4M | None | allow remote connectivity to enable mobile workforce |  |  |  | 18 | 790000
1850 | ERCOT | IO | IO |  | Switch Consolidation | 60047_01 | Not Yet Started |  | 1 - Critical | 3 | 1.3 | 98 | $100k-$500k | $2M-$4M | Resource Impact | required to free up system / infrastructure resources to meet nodal demands |  |  |  | 16 | -200000 | The Network Group currently maintains several hubs and switches that can be consolidated in to a single chassis switch. Provisioning will call for two in Austin and two in Taylor. Most of these devices are obsolete and end-of-life.
| ERCOT | IO | IO |  | Storage Upgrade | New | Not Yet Started |  | 1 - Critical | 4 |  |  | $500k-$1M | $2M-$4M | None | required to free up system / infrastructure resources to meet nodal demands |  |  |  | 23 | 8400000
1580 | ERCOT | IO | IO |  | Tools and Strategy for Information Lifecycle Management | 60035_01 | Not Yet Started |  | 1 - Critical | 5 | 1.2 | 71 | >$5M | $10M-$12M | Resource Impact | required to free up system / infrastructure resources to meet nodal demands |  |  |  | 19 | 2763458 | Develop strategy for Information lifecycle management to manage data in production databases. This will include Tier 2 Storage w/San Switches.
1010 | ERCOT | IO | IO |  | TCC Data Center Virtualization | 60011_01 | Not Yet Started |  | 1 - Critical | 6 | 1.1 | 15 | $1M-$3M | $12M-$14M | Resource Impact | required to free up system / infrastructure resources to meet nodal demands |  |  |  | 21 | 5800000 | There is a need to expand the Taylor Data Center in order to maintain the necessary redundant capacities and provide for continued increases in storage requirements. | Addressing power and cooling limitations will allow ERCOT to continue to effectively support ongoing operations and additional capital projecte requirements
| ERCOT | IO | IO |  | Virtual Tape Backup | New | Not Yet Started |  | 1 - Critical | 7 |  |  | $1M-$3M | $14M-$16M | None | required to free up system / infrastructure resources to meet nodal demands |  |  |  | 26 | 110000000
| ERCOT | IO | IO |  | Deskside Standardization | New | Not Yet Started |  | 2 - High | 8 |  |  | $500k-$1M | $14M-$16M | None |  |  |  |  | 23 | 1100000
Estimated Resource Capability = $16,000,000
2040 | ERCOT | IO | IO |  | Console Operations Area | 60057_01 | Not Yet Started |  | 2 - High | 9 | 2.1 | 118 | $1M-$3M | $16M-$18M | None |  |  |  |  | 25 | -443271 | Provide a permanent and suitable location for Console Operations. The build-out will provide a 1500 sq.ft. location in the hardened area of TCC adjoining the Data Center. The objective is to design and construct a work area with the proper communcation infrastructure and audio visual capabilities needed for this environment.
| ERCOT | IO | IO |  | UNIX Hardware EOL | New | Not Yet Started |  | 2 - High | 10 |  |  | >$5M | $32M-$34M | None |  |  |  |  | 14 | 13000000
| ERCOT | IO | IO |  | Software Standardization (non-Nodal) | New | Not Yet Started |  | 2 - High | 11 |  |  | $100k-$500k | $34M-$36M | None |  |  |  |  | 16 | 100000000 | Reduce the number of technologies supported in ERCOT’s production web environment and register the updated applications in a configuration management database (CMDB) | ERCOT’s web platform has a large number of technology components and versions. Supporting such a diverse environment is expensive to both the operations and development teams and it affects the quality of the solutions ERCOT delivers. We have reached a point where the cost of supporting and operating ERCOT’s web environment has become unreasonable.
| ERCOT | IO | IO |  | WAN GTM | New | Not Yet Started |  | 2 - High | 12 |  |  | $100k-$500k | $34M-$36M | None |  |  |  |  | 12 | 430000 | (includes (4) Big-IP 3400s w/ max memory) Enhance high availability and Disaster Recovery for WAN facing services. This will allow us to load balance WAN services such as MOS, MOSTML, TML, etc… between Austin and Taylor. This will reduce the amount of physical hardware required to create a redundant environment. Also, this will dramatically reduce the amount of time required for failover.
| ERCOT | IO | IO |  | Tellabs Digital Cross-Connect System Replacement | New | Not Yet Started |  | 2 - High | 13 |  | 15 | $500k-$1M | $34M-$36M | None |  |  |  |  | 15 | -600000 | Hardware for ERCOT’s current Tellabs systems have been manufacturer discontinued. This replacement is required to continue reliable operation and support of System Operations voice, RTU and data communications on the ERCOT WAN.
2310 | ERCOT | IO | IO |  | TML Port to Unix | 50062_01 | Not Yet Started |  | 2 - High | 14 | 3.1 | 144 | $100k-$500k | $34M-$36M | None |  |  | 2.1 | 73 | 16 | 6348545 | Windows and Jrun environment has proven problematic. Jrun will end of life next year (complete product), and Windows for DMZ applications is being decommissioned.
| ERCOT | IO | IO |  | DB High Availability / Recovery | New | Not Yet Started |  | 2 - High | 15 |  |  | $500k-$1M | $36M-$38M | None |  |  |  |  | 24 | 8400000
| ERCOT | IO | IO |  | LDAP Implementation | New | Not Yet Started |  | 3 - High / Medium | 16 |  |  | $500k-$1M | $36M-$38M | None |  |  |  |  | 18 | 540000
| ERCOT | IO | IO |  | DR Test | New | Not Yet Started |  | 3 - High / Medium | 17 |  |  | $500k-$1M | $36M-$38M | None |  |  |  |  | 17 | 1600000000 | Prove, through a successful executed test, that ERCOT can recover it’s core IT capabilities in the event that we are unable to operate our systems out of the Taylor Data Center. | It is critical, given the amount of change to our IT infrastructure, that we perform and successfully complete a DR tests in 2007 to validate ERCOT’s ability to recover it’s IT systems in the event we are not able operate these core systems from the Taylor Data Center.
| ERCOT | IO | IO |  | ERCOT Private OC-3 Microwave System Retirement | New | Not Yet Started |  | 3 - High / Medium | 18 |  |  | <$100k | $36M-$38M | None | [5 empty] | 0 | ERCOT’s existing OC-3 Microwave System will be retired provided that an alternative, comparably priced redundant infrastructure is attainable.
| ERCOT | IO | IO |  | Spectel Hotline System Replacement | New | Not Yet Started |  | 3 - High / Medium | 19 |  |  | $500k-$1M | $38M-$40M | None | [5 empty] | 0 | ERCOT’s existing Hotline system is 5 years old and is operating on Windows NT. Upgrading and expansion is costly, the system should be replaced with improved technologies providing better functionality and features.
| ERCOT | IO | IO |  | Email PST Consolidation | New | Not Yet Started |  | 4 - Medium | 20 |  |  | <$100k | $38M-$40M | None | [5 empty] | 0
1255 | ERCOT | IO | IO |  | Firewall Modules Between Internal Subnets | 60019_01 | Not Yet Started |  | 4 - Medium | 21 | 1.1 | 38 | $100k-$500k | >$40M | None |  |  |  |  | 28 | -132651 | Separation of CORP Servers from Workstation Envrionment. This will provide for a more secure and segmented environment. | Improve ERCOT's reliability performance; security; accuracy, timeliness and transparency of transactions/settlements related to date received from, managed and delivered to the market; and supports the baseline architecture that delivers current services.
870 | PUCT | IO | IO |  | EIS BI Foundations III | 60001_01 | To be Moved to SO |  | 9 - Parking Lot |  | 1.1 | 2 | [7 empty] | 25 | -195455 | Enable consistent and efficient reporting for the PUCT, ERCOT, and, eventually, MPs. This project will roll out a third set of Business Intelligence (BI) components per the PUCT's requests. | Improve ERCOT's reliability performance; cyber security; efficiency; and accuracy, timeliness and transparency of transactions/settlements related to date received from, managed and delivered to the market.
1020 | Market | ROS | IO | SCR744 | Outage Scheduler View Only Access (to be included in Enhance Digitial Cert project) | 60012_01 | To be Moved to SO |  | N/A |  | 1.1 | 17 |  |  |  |  | BoD 9/22/05 | 1.1 | 38 | 15 | 4074838
968 | ERCOT | IO | IO |  | Austin Test Environment | 40070 | Execution | McLain | N/A |  | 1.1 | 11.8 | [5 empty] | 1.1 | 5.5 |  | 0 | The ability to run concurrent application tests, using equipment that will match more closely the production environment. Create a production functional equivalent for integration, regression, and negative testing, and for User Acceptance testing, break-fix, and volume testing.
490 | PUCT | IO | IO |  | EDW Business Intelligence Foundation Phase 2 | 50001 | Planning | Jirasek | N/A |  | 1.0b | 0.64 | [5 empty] | 1.1 | 1
969 | ERCOT | IO | IO |  | Disk Based Recovery | 50027 | Execution | McLain | N/A |  | 1.1 | 11.9 | [5 empty] | 1.2 | 36 | 20 | -437582 | Remove the overhead and performance impact of backups on production systems to increase performance and meet the needs of current growth | Increased efficiency in performing data restores and refreshing test environments. Savings in tape cartridges ($120k per year). Eliminates risk of unrecoverable data due to tape error.
270 | ERCOT | IO | IO |  | Altiris DC Implementation | 50028 | Closing | Wilkinson | N/A |  | 1.0a | 0.16 | [5 empty] | 1.2 | 37 | 20 | 8321 | Implement Altiris monitoring software in the Data Center Environment. Be able to run reports on all systems against a known good configuration. Enable comparison of two systems to one another to analyze differences between the systems for troubleshooting purposes. | Implement audit recommendations were made to improve network security and safety.
650 | ERCOT | IO | IO |  | TCC II Completion | 50049 | Closing | Stewart-Booker | N/A |  | 1.0b | 0.76 | [5 empty] | 1.1 | 16.5
610 | ERCOT | IO | IO |  | SBC Network Replacement | 50078 | Execution | Stewart-Booker | N/A |  | 1.0b | 0.72 | [5 empty] | 1.1 | 13.5 | 26 | 300000 | vThis project replaces the SBC telecommunications infrastructure between Austin and Taylor that is used for SAN DR replication and network communications. The project significantly reduces ERCOT's long term O&M costs for these services. The replacement network will be comprised of AT&T and Alpheus fiber plus Cisco electronics.
100 | ERCOT | IO | IO |  | Production Storage | 50125 | Closing | McLain | N/A |  | 1.0a | 0.07 | [5 empty] | 1.1 | 10.7 | 23 | 4630932 | Addition and optimization of data storage to meet ongoing demands | Establish Homogeneous storage infrastructure; Reduce storage management overhead; Improve continuity of storage related to business continuity (DR); Improve reporting accuracy and timeliness;Reduce the O&M overhhaed for storage reporting
770 | ERCOT | IO | IO |  | EMMS Development Environment Upgrade | 50138 | Closing | Wilkinson | N/A |  | 1.0b | 0.86 | [5 empty] | 1.1 | 31.92
510 | ERCOT | IO | IO |  | ACC Data Center Power & Cooling | 50145 | Closing | Stewart-Booker | N/A |  | 1.0b | 0.65 | [5 empty] | 1.1 | 5.7 |  |  | Extend the Cooling capacity in the Austin Datacenter. This project included the installation of 2-30ton units and the supporting controls to manage the expanded cooling capabilities.
966 | ERCOT | IO | IO |  | Windows Domain Restructuring | 50147 | Execution | Wilkinson | N/A |  | 1.1 | 11.6 | [5 empty] | 1.2 | 43.1 | 21 | 122841 | Restructure Windows forest under ercot.com domain as an implementation of best practices. This project should result in one Windows Domain with proper trusted relationships among the environments. | Improve ERCOT's reliability performance. Proper infrastucture design is necessary for all projects and effects implementation and management of all systems.
1980 | ERCOT | IO | IO |  | System Engineering Metrics | 50077_01 | Will be Cancelled |  | N/A |  | 2.1 | 111 | [5 empty] | 2.2 | 90 | 14 | -131183 | Ensure delivery of key service metrics, ensure growth and capital efforts are adequately forecasted, and stimulate continuous improvement for data center capacity management.
2330 | ERCOT | IO | IO |  | MET Center Remediation | 50082_01 | Will be Cancelled |  | N/A |  | 3.1 | 146 | [5 empty] | 2.2 | 95 | n/a | n/a (3.x priority) | To remediate potential drainage problems and reduce/eliminate water migration underneath the foundation of the MET Center facility.
970 | ERCOT | IO | IO |  | 2006 Minor Capital | 60009_01 | Execution | N/A | N/A |  | 1.1 | 12 | [8 empty] | 0 | Capital purchases over the course of the year: new desktop and laptop systems, SAN switch upgrades, voice recording system for Outage Coordinators, add'l Mercury Interactive licenses, etc. | Continued maintenance activites in support of ERCOT's infrastructure
965 | ERCOT | IO | IO |  | SAN Switch Expansion | 60011_02 | Closing | Wilkinson | N/A |  | 1.1 | 11.5 | [7 empty] | 19 | 20000 | Introduce new EMC Connectrix to mitigate the lack of SAN ports and the inability to provision more SAN-attached hardware.
1630 | ERCOT | IO | IO |  | Exchange 2003 Implementation | 60036_01 | Closing |  | N/A |  | 1.2 | 76 | [7 empty] | 22 | 29345 | Upgrade Email system to latest version and avoid sunsetting and need for emergency migration later. Exchange 2003 is also necessary for upgrading new software products with a dependancy on Exchange.
1680 | ERCOT | IO | IO |  | IT Systems Map | 60037_01 | Will be Cancelled |  | N/A |  | 1.2 | 80 | [7 empty] | 19 | 1269302 | Create a map of the ERCOT DC environment including all servers in all environments, node to node, applications, Ips, System Model, RAM, Processor, HBA, FA Path and all other important information. Some of this effort may be completed in the Austin iTest project.
1700 | ERCOT | IO | IO |  | Network Response | 60038_01 | Will be Cancelled |  | N/A |  | 1.2 | 82 | [7 empty] | 27 | -120323 | Reduce the amount of time required to disable infected hosts on the ERCOT Corporate network.
| ERCOT |  |  |  | Alcatel MDR8000 SNMP Upgrade | 60048_01 | Will be Cancelled |  | N/A |  | 1.3 | 102 | [7 empty] | 16 | -55022
2010 | ERCOT | IO | IO |  | TCC Modular Storage/Additional Office Space | 60054_01 | Will be Cancelled |  | N/A |  | 2.1 | 115 | [7 empty] | 22 | -708911 | When TCC2 is completed, ERCOT will not have any storage space available on-site for critical computer equipment. A modular storage/office building will give ERCOT additional office space if needed and an on-site, secure environmentally controlled storage area for equipment.
2300 | ERCOT | IO | IO |  | PowderHorn Tape Library Redundancy | 60070_01 | Will be Cancelled |  | N/A |  | 3.1 | 143 | [7 empty] | 14 | -191098 | Provide redundant power for the Tape backup library. | The existing tape library is not power redundant and losses of power to the unit will halt functionality of backup and restore operations.