## MO
MO 2007 Project Prioritization - PUCT, Market and ERCOT Projects
Main Sort | Source | Committee | Prog Area | Source Doc | Project | Project No. | Current Status | Project Manager | Expected Completion | 2007 Priority | 2007 Rank | 2006 Priority | 2006 Rank | 2007 Budget Range | 2007 Running Range | Nodal Impact | Nodal Impact Comments | Priority Approval | 2005 Priority | 2005 Rank | CBA Score | Net Benefit | Summary Description | Benefit Summary
70 | Market | MO | MO | SCR740 | Enhancements to SCR727 - Market Access | 50024_01 | Execution | Ray | 2007 | 0 - Carryover | 0.1 | 1 | 0.05 | <$100k | <$1M |  |  | TAC 9/9/2004 | 1.2 | 33 | 15 | 3500000 | Subproject to provide market access to SCR727 data
80 | Market | MO | MO | SCR740 | Enhancements to SCR727 - Market Enhancements | 50024_02 | Initiation | Ray | 2007 | 0 - Carryover | 0.2 | 1 | 0.05 | <$100k | <$1M |  |  | TAC 9/9/2004 | 1.2 | 33 | 15 | 3500000 | Subproject to provide market-requested enhancements to SCR727 data extract
600 | ERCOT | MO | MO |  | SCR 727 Phase II | 40007_01 | Execution | Haynes | 2007 | 0 - Carryover | 0.3 | 1 | 0.71 | <$100k | <$1M |  |  |  | 1.1 | 13
900 | Market | COPS | MO |  | TML Phase 3 - Wholesale Enhancements | 40103_01 | Hold | Haynes | 2007 | 0 - Carryover | 0.4 | 1.1 | 7 | $100k-$500k | <$1M |  |  |  | 1.3 | 54 | 18 | 11145103 | The scope of Phase 3 will focus on user experience enhancement of the new portal platform for ERCOT Wholesale Market Participants. The goal is to incorporate additional functionalities and enhanced usability for QSEs, Transmission Operators and Resources. | 50 impacted QSE's, 3 hours per calendar day savings in scheduling, 1 hour per workday in settlement mismatch analysis
971 | ERCOT | MO | MO |  | Lodestar 4.x Upgrade | 40066_04 | Initiation | Ray | 2007 | 0 - Carryover | 0.5 | 1.1 | 12 | $100k-$500k | <$1M |  |  |  | 1.1 | 23 | 19 | 26444 | Maintain efficiency, and reliability of the LodeStar application to enable ERCOT to meet Energy Aggregation and Billing & Settlements business needs | Nightly processing speed improvement; improved data editing capabilities (0.5 hours per workday); enhanced querying capability for users (0.5 hours per workday)
1310 | ERCOT | MO | MO |  | EIS L* Transition to ODS ( formerly EDW Lodestar Data Archive Transition to EDW) | 50030_01 | Execution | Ray | 2007 | 0 - Carryover | 0.6 | 1.1 | 44 | <$100k | <$1M |  |  |  | 1.2 | 39 | 29 | 67868 | Transition reporting to the EDW Lodestar/EMMS ODS. | Reduction of support costs of over 50% (10 hours per day to 4 hours per day)
1490 | PUCT/ ERCOT | MO | MO |  | REC Program Modifications | 60027_01 | Planning | Haynes | 2007 | 0 - Carryover | 0.7 | 1.2 | 61 | <$100k | <$1M | [5 empty] | 19 | -389860 | The REC program has been in operation for almost 4 years, and the technology roadmap has deviated from Microsoft tools. Currently, the REC program is written in ASP. In order to efficiently continue support of this application, it will need to be ported to Java in line with ERCOT's technology roadmap. | Enhance ability to make changes and enhancements to the REC program software; better align with long-term IT strategic direction.
975 | Market | MO | MO | PRR598 | Extension of Credit Against OOM Start Up (** COPS Review Requested) | New | New |  | New | 1 - Critical | 1 | 1.1 | 12.1 | <$100k | <$1M |  |  | BoD 11/15/2005 |  |  | 13 | -50000 | Maintain efficiency, and reliability of the LodeStar application to enable ERCOT to meet Energy Aggregation and Billing & Settlements business needs | Nightly processing speed improvement; improved data editing capabilities (0.5 hours per workday); enhanced querying capability for users (0.5 hours per workday)
| Market |  | MO | PRR661 | SCE Performance Enforcement Criteria | New | Not Yet Started |  |  | 2 - High | 1.4 |  |  | <$100k | <$1M | [5 empty] | 20 | -476000 |  | Primary benefits are non-quantifiable
| Market |  | MO | PRR666 | Modification of RPRS Under-Scheduled Capacity Charge Calculation | New | Still in Stakeholder Process |  |  | 2 - High | 1.5 |  |  | TBD | [6 empty] | 16 | -300000 |  | Reduced cost to procure RPRS for capacity sufficiency
| Market |  | MO | PRR667 | RPRS Uplift Charge and Under-Scheduled Charge Correction | New | Still in Stakeholder Process |  |  | 2 - High | 1.6 |  |  | TBD | [6 empty] | 16 | -300000 |  | Reduced cost to procure RPRS for capacity sufficiency. Eliminate cost charged to parties that had no impact on the volume of RPRS being procured by ERCOT.
| Market | COPS | MO | PRR565 | Calculation of Losses for Settlement | 60068_01 | Not Yet Started |  | 2007 | 2 - High | 2 | 1.1 | 32.6 | <$100k | $1M-$2M
| Market | COPS | MO | SCR743 | QSE Dispute Extract | New | New |  | New | 2 - High | 3 | N/A | N/A | <$100k | $1M-$2M
| ERCOT | MO | MO |  | Siebel to L* 5 - Rewrite | New | New |  | New | 2 - High | 4 | N/A | N/A | $100k-$500k | $1M-$2M | [5 empty] | 19 | 210000
| ERCOT | MO | MO |  | Transition of Production Reporting to EIS - Wholesale | New | New |  | New | 2 - High | 5 | N/A | N/A | $100k-$500k | $1M-$2M | [5 empty] | 16 | -50000
1520 | ERCOT | MO | MO |  | Lodestar Web Services | 60030_01 | Not Yet Started |  | 2007 | 2 - High | 6 | 1.2 | 64 | $100k-$500k | $1M-$2M | [5 empty] | 21 | 250000 | Provide enhanced access to Lodestar data via web services. | Market benefit: Create efficiencies in information retrieval (0.5 hours per workday savings for QSEs, CRs and Resources)
| ERCOT | MO | MO |  | Upgrade to Load Profiling SW | New | New |  | New | 2 - High | 7 | N/A | N/A | $100k-$500k | $1M-$2M | [5 empty] | 14 | -200000
2440 | Market | WMS | MO | PRR426 | URC for Uncontrollable Resources(** WMS Review Requested) | 40057_01 | Not Yet Started |  | 2007 | 3 - High / Medium | 8 | 3.3 | 158 | <$100k | >$2M |  |  | BOD 2/17/2004 | 3.3 | 133 |  |  | Defines an Uncontrollable Renewable Resource and allows wind resource to elect to use their Renewable Production Potential in lieu of their schedule as the basis for URC charges and OOME Down payments.
Estimated Resource Capability = $2,058,000
1320 | ERCOT | MO | MO |  | EIS Reporting Tool II | 60021_01 | Not Yet Started |  | 2007 | 9 - Parking Lot | N/A | 1.1 | 46 | $100k-$500k | >$2M | [5 empty] | 24 | 2358819.0704 | Enable consistent and efficient reporting for the PUCT, ERCOT, and MPs. Implementation of the reporting tool will enable users translate business questions into optimized queries. This project rolls out reporting functionality and additional licensing from the framework project 50004. | Market benefit: Create efficiencies in information retrieval (1 hour per workday savings for all Market Participants)
1440 | Market | COPS | MO | PRR577 | TDSP Load Extract | 50150_01 | Not Yet Started |  | TBD | 9 - Parking Lot | N/A | 1.2 | 56 | <$100k | >$2M |  |  | BoD 7/19/2005 | 1.3 | 57.5 | 17 | 47000 | To receive aggregated TDSP Load data from ERCOT for the purposes of accurately identifying TDSP system peaks required for FERC filings. | Possible fines associated with non-compliance = $100k. This number is estimated, and based on the assumption FERC may fine the TDSP for non-compliance considering the TDSP can not produce the data accurately.
2350 | Market | COPS | MO |  | TCR Synchronization of Credit Payment with Settlement Invoices | 30103_01 | Not Yet Started |  | TBD | 9 - Parking Lot | N/A | 3.3 | 149 |  |  | Func. Replaced By Nodal | Shoud be addressed by Nodal efforts |  | 3.3 | 136 | n/a | n/a (3.x priority)
| Market | COPS | MO | PRR385 | DLC Implementation | - | Not Yet Started |  | TBD | 9 - Parking Lot | N/A | 3.3 | 150
| Market | COPS | MO | PRR478 | Use of Lagged Dynamic Samples for New Load Profiles | 40056_01 | Not Yet Started |  | TBD | 9 - Parking Lot | N/A | 3.3 | 150
90 | Market | MO | MO | SCR740 | Enhancements to SCR727 - Market Enhancements | 50024_03 | Not Yet Started |  | 2006 | DELETE | N/A | 1 | 0.05 |  |  |  |  | 15 | 3500000 | $100k-$500k | $2M-$4M
| Market | MO | MO | PRR613 | Replacement Reserve Under Scheduled Capacity Delineation | - | Cancel |  | 2006 | DELETE | N/A | 1 | 0.87 |  |  |  |  | BoD 10/18/05 | 1.2 | 34.4 | 15 | 400000
1001 | Market | WMS | MO | SCR747 | Removal of Price Administration for Zonal Congestion | 60080_01 | Cancel |  | X-fer to SO | DELETE | N/A | 1.1 | 9.25 | [5 empty] | 13 | -20000 | <$100k | $16M-$18M
1015 | ERCOT | MO | MO |  | DC Tie Automation (Pk2 Only) | 50018_01 | X-fer |  | X-fer to SO | DELETE | N/A | 1.1 | 14 | [5 empty] | 1.1 | 29 | 19 | 25041 | This project will implement the EAA and CRC DC Tie accounting tasks that are currently being performed manually for settlement. It is recommended to work this project with the Package 1 component although some automation may be achieved without it. | Automation of various manual aspects of DC Tie accounting (approximately 750 hours per year [1/3 FTE])
1460 | Market | MO | MO | PRR602 | Ancillary Service Obligation for DC Tie Exports | - | Cancel |  | Never | DELETE | N/A | 1.1 | 32.5 |  |  |  |  | PRS 10/27/2005 (Withdrawn) |  |  | 12 | 1600000
1720 | Market | COPS | MO |  | Extract/Report Enhancements | 60025_01 | Not Yet Started |  | Never | DELETE | N/A | 1.2 | 58 | [7 empty] | 10 | 0 | To implement enhancements recognized as necessary with implementation of web services (SCR740). Estimate: 4 small changes at $50k each; 1 large change at $300k | Changes will only be considered if they have a positive net benefit
1950 | ERCOT | MO | MO |  | SIR Enhancement Projects - 3 Releases | 60040_01 | Not Yet Started |  | Never | DELETE | N/A | 1.2 | 84 | [7 empty] | 15 | -210000 | To resolve System Investigation Requests to continue to improve system performance and remove manual workarounds that currently exist in the ERCOT Production environment. | Dependent on nature of SIR enhancements
290 | ERCOT | MO | MO |  | Uninstructed Deviation Calc for Uncontrollable Renewable Resource | 50115_01 | Not Yet Started |  | Never | DELETE | N/A | 2.1 | 108 | [5 empty] | 3.3 | 145 | 15 | 38178 | The Settlement system shall automate receiving and calculating URC charges based on imported RPP data cuts. Also, OOME down shall be calculated using RPP data in lieu of Resource Plan data for units opt for RPP. This project will automate the manual processes currently performed by ERCOT Settlements team (Option A on the Impact Analysis)
260 | Market | MO | MO | PRR312 | Enhance ESIID Lookup Function | 50025_01 | Execution | Haynes | 2006 | N/A | N/A | 1 | 0.06 |  |  |  |  | BOD 5/21/2002 | 1.2 | 34 | 14 | 725000 | Provide additional information for an ESI ID to include Station ID, Power Region, Premise Type, status (active/de-energized/inactive) for an ESI ID. In addition, advise if there is a pending Move In/Move Out for the ESI ID. | 1 hour time savings per week per CR due to increased efficiencies
380 | PUCT | MO | MO |  | EDW BI Reporting Tool | 50004_01 | Closing | Ray | 2006 | N/A | N/A | 1 | 0.15 | [5 empty] | 1.1 | 4 | 24 | 15276127 | Enable consistent and efficient reporting for the PUCT, ERCOT, and eventually, MPs. Implementation of the BI Tool will enable users to translate business questions into optimized queries. | Framework project that will provide additional secured access to information by the PUCT and the Market.
81 | ERCOT | MO | MO |  | Lodestar Extracts | 40042_06 | Execution | Ray | 2006 | N/A | N/A | 1 | 0.18 | [5 empty] | 1 | 0.24 | 25 | 1013815 | To migrate the Generation, Load, Settlements & Billing, and Shadow Pricing extracts from the Data Archive to the ODS (Operational Data Store). | Market benefit: 10 minutes of savings per day per Market Participant due to optimized data access.
440 | Market | MO | MO | PRR283 PIP204 | EPS Meter Data | 30026_01 | Execution | Troxtell | 2006 | N/A | N/A | 1 | 0.54 |  |  |  |  | BOD 1/15/2002 | 1 | 0.13
780 | ERCOT | MO | MO |  | TCR Report Enhancements Phase II | 40015_02 | Execution | Ray | 2006 | N/A | N/A | 1 | 0.59 | [5 empty] | 1 | 0.35
790 | Market | MO | MO | PRR548 | Settlement Mismatches Inter-QSE Schedules | 50128_01 | Closing | Haynes | 2006 | N/A | N/A | 1 | 0.87 |  |  |  |  | BoD 02/16/2005 | 1.2 | 34.4
800 | Market | MO | MO | PRR599 | Notification for Mismatched Inter-QSE Schedules | 50128_01 | Closing | Haynes | 2006 | N/A | N/A | 1 | 0.87 |  |  |  |  | BoD 10/18/05 | 1.2 | 34.4 | 15 | 400000
1080 | ERCOT | MO | MO |  | Maestro Upgrade | 50137_01 | Execution | Haynes | 2006 | N/A | N/A | 1.1 | 16 | [5 empty] | 1.1 | 31.7 | 22 | 380296 | This project will replace ERCOT’s current batch job scheduling software. The current scheduling software, Maestro, experiences issues outlined below: • Maestro is currently not supported – Major upgrade required • Maintenance cost expensive due to CPU Pricing Model • Security Risk – passwords not encrypted • Preventing upgrade of DBMS and Operating System • Uses a Proprietary Database | Increased efficiencies in script creation, testing and maintenance (6 hours per day); Change migration efficiency; Improved job scheduling capabilities
1200 | ERCOT | MO | MO |  | MV90 Upgrade Part 2 - Installation of Software | 50033_02 | Closing | Thomas | 2006 | N/A | N/A | 1.1 | 21 | [5 empty] | 1.1 | 31.5 | 14 | 46011 | This project will install and implement the MV-90 software upgrade that was purchased in 2005. Support of the current product version ends in 2007. | Automation of manual tasks (1 hour per workday); Allow TDSPs to select new meter types for deployment as EPS meters