## CO
2007 Project Prioritization - PUCT, Market and ERCOT Projects
Main Sort | Source | Committee | Prog Area | Source Doc | Project | Project No. | Status | Project Manager | 2007 Priority | 2007 Rank | 2007 Budget Range | 2007 Running Range | Expected Complete | 2006 Priority | 2006 Rank | Nodal Impact | Nodal Impact Comments | Priority Approval | 2005 Priority | 2005 Rank | CBA Score | Net Benefit | Summary Description | Benefit Summary
1055 | ERCOT | CO | CO |  | Identity & Access Management | 60075_01 | Planning | Booker | 0 - Carryover | 0.1 | $500k-$1M | <$1M | 2007 | 1.1 | 19.5 | [7 empty] | Automate and provide ability to generate SAS70, NERC and 17799 complaince reports
1280 | ERCOT | CO | CO |  | Lawson 8.1 Upgrade | 60020_01 | Not Started |  | 0 - Carryover | 0.2 | $100k-$500k | <$1M | 2007 | 1.1 | 40 | [5 empty] | 19 | 177090 | Upgrade Lawson Application Suite and Environment to version 8.1 | Internal ERCOT benefit: increased efficiencies in various areas and reduced cost and risk in maintaining unsupported software
2230 | ERCOT | CO | CO |  | Physical Security Project #1 | 50103_01 | Not Started |  | 1 - Critical | 1 | <$100k | $1M-$2M | 2007 | 2.3 | 137 |  |  |  | 3.2 | 126 | 15 | -311784
| ERCOT | CO | CO |  | Corporate Document Management | New | Not Started |  | 1 - Critical | 2 | $100k-$500k | $1M-$2M | [8 empty] | 15 | 255263 | HR, Finance, Procurement, Security
| ERCOT | CO | CO |  | Cyber-Security Project #1 | New | New |  | 2 - Critical | 3 | $100k-$500k | $1M-$2M | 2007 | [7 empty] | 25 | 5400508.416
2210 | ERCOT | CO | CO |  | Lawson Expense Management | 60066_01 | Not Started |  | 1 - Critical | 4 | <$100k | $1M-$2M | 2007 | 2.3 | 135 | [5 empty] | 14 | -55641 | Implement Lawson Expense mangement in order to track expenses online.
| ERCOT | CO | CO |  | Physical Security Project #2 | New | New |  | 1 - Critical | 5 | $100k-$500k | $1M-$2M | 2007 | [7 empty] | 20 | -237577
| ERCOT | CO | CO |  | Physical Security Project #3 | New | New |  | 1 - Critical | 6 | $100k-$500k | $1M-$2M | 2007 | [7 empty] | 25 | -131310
| ERCOT | CO | CO |  | Lawson Security | New | New |  | 1 - Critical | 7 | <$100k | $1M-$2M | 2007 | [7 empty] | 14 | 232488.4487 | Lawson has restructured the application security within the suite of applications. The security is no longer deductive where a user is given access to everything and the security administrator must strip away any access that is not required. Instead, the new version allows for additive privileges and provides real role based security. The current version requires one security class per user. This results in many unmanageable classes. The role based model is much more flexible and maintainable.
| ERCOT | CO | CO |  | Identity & Access Management (IAM) Integration | New | New |  | 1 - Critical | 8 | <$100k | $1M-$2M | 2007 | [7 empty] | 9 | -37596.049 | To fully utilize the Identity and Access Management project, ERCOT will need to integrate the tool with Lawson HR, the contract management database as well as other applications such as Altiris and Aperture Vista.
2520 | ERCOT | CO | CO |  | Lawson eRecruiting | 60073_01 | Not Started |  | 1 - Critical | 9 | <$100k | $2M-$3M | 2007 | 3.3 | 166 | [5 empty] | 17 | 159978.2695 | Implement Lawson eRecruiting module. ERCOT owns the license to support this functionality.
| ERCOT | CO | CO |  | Absence Management | New | New |  | 1 - Critical | 10 | <$100k | $2M-$3M | 2007 | [7 empty] | 11 | -69280.75 | Replace the existing Time Accrual component in Lawson with Absence Management
| ERCOT | CO | CO |  | Aperture Vista 500 Upgrade | New | New |  | 1 - Critical | 11 | <$100k | $2M-$3M | 2007 | [7 empty] | 10 | -54987.8434 | Upgrade Aperture Vista to the latest platform
| ERCOT | CO | CO |  | Physical Security Project #4 | New | New |  | 1 - Critical | 12 | <$100k | $2M-$3M | 2007 | [7 empty] | 25 | -93812
| ERCOT | CO | CO |  | Open Enrollment | New | New |  | 1 - Critical | 13 | <$100k | $2M-$3M | 2007 | [7 empty] | 11 | 10031.0261 | Enable Open Enrollment via Lawson Employee Self Service
| ERCOT | CO | CO |  | Flexible Port Security | New | New |  | 2 - High | 14 | $100k-$500k | $2M-$3M | 2007 | [7 empty] | 20 | 666330 | Develop systems and methodologies to allow ERCOT employees to connect to any network port within the network perimeter and be granted access to the resources they are authorized. Additionally, explore the technology that will allow guests to connect and be automatically routed to the Guest Network.
1820 | ERCOT | CO | CO |  | Benefits Data Transmission | 60045_01 | Not Started |  | 2 - High | 15 |  | $2M-$3M | 2007 | 1.3 | 95 | [5 empty] | 12 | -62055 | ERCOT currently submits data to our benefits provider manually by extracting the data from Lawson to an Excel spreadsheet and emailing the data. Lawson support edi transmission of data. This would completely automate the process eliminating any potentia
1570 | ERCOT | CO | CO |  | Business Function Automation Time Mgt Integration | 60034_01 | Not Started |  | 2 - High | 16 | $100k-$500k | $2M-$3M | 2007 | 1.2 | 70 | [5 empty] | 8 | 6648961 | Integrate Identity and Access Management functions with key enterprise infrastructure applications. Improves SAS70 compliance. | ERCOT benefit: 10 minutes of time savings per ERCOT employee per day
1780 | ERCOT | CO | CO |  | Budgeting Tool | 40029_01 | Not Started |  | 2 - High | 17 | <$100k | $2M-$3M |  | 1.3 | 91 |  |  |  | 2.1 | 74 | 16 | 45656.7731 | Evaluate, select, and implement an automated budgeting tool that offers interconnectivity to the Lawson Accounting system.
| ERCOT | CO | CO |  | Process Flows - HR | New | New |  | 2 - High | 18 | <$100k | $2M-$3M | 2007 | [7 empty] | 17 | 188462 | Automate and provide auditable checkpoints for the hiring and termination of ERCOT employees
| ERCOT | CO | CO |  | Requisition Self Service | New | New |  | 2 - High | 19 | <$100k | $2M-$3M | 2007 | [7 empty] | 17 | 125108 | Allow employees and managers to begin the process of requesting software, hardware and/or services via an on line form. Support the procurement process with workflow appropriate workflow so that users can see the status of these requisitions
1510 | ERCOT | CO | CO |  | Enterprise Document Management | 60029_01 | Not Started |  | 2 - High | 20 | $100k-$500k | $3M-$4M | 2007 | 1.2 | 63 | [5 empty] | 15 | 5684672 | Provide a document management system to be used across the enterprise for policies, procedures, department documentation, etc. | Internal ERCOT benefit: 10 min. time savings per employee per workday
| ERCOT | CO | CO |  | Cyber-Security Project #2 | New | New |  | 2 - High | 21 | $100k-$500k | $3M-$4M | 2007 | [7 empty] | 20 | 158753.1949
| ERCOT | CO | CO |  | Cyber-Security Project #3 | New | New |  | 2 - High | 22 | $100k-$500k | $3M-$4M | 2007 | [7 empty] | 25 | 2058450
| ERCOT | CO | CO |  | TCC2 Security Facilities Buildout | New | New |  | 2 - High | 23 | $500k-$1M | $4M-$5M | 2007 | [7 empty] | 27 | 852387.7196 | Security needs to vacate current space to make room for IT.
| ERCOT | CO | CO |  | TCC2 HR Buildout | New | New |  | 2 - High | 24 | $500k-$1M | $4M-$5M | 2007 | [8 empty] | 0
| ERCOT | CO | CO |  | Corporate Development Environment | New | New |  | 2 - High | 25 | $100k-$500k | $5M-$6M | 2007 | [7 empty] | 19 | 555579 | Allow the corporate development environment to expand so that the resources are available to the development team so that Corporate Applications is able to follow the ERCOT standard Software Development Lifecycle.
| ERCOT | CO | CO |  | Corporate i-Test Environment | New | New |  | 2 - High | 26 | $100k-$500k | $5M-$6M | 2007 | [7 empty] | 19 | 555579 | Allow the corporate test environment to expand so that the resources are available to ERCOT so that Corporate Applications is able to follow the ERCOT Software Development LifeCycle.
| ERCOT | CO | CO |  | Intranet Re-Arch | New | New |  | 2 - High | 27 | $100k-$500k | $5M-$6M | 2007 | [7 empty] | 15 | 31352 | Retiring Cold Fusion
| ERCOT | CO | CO |  | Report Writer | New | New |  | 2 - High | 28 | <$100k | $5M-$6M | 2007 | [7 empty] | 16 | 259559 | Provide enhanced reporting for ERCOT's standard applications. Allow end users reporting self service.
| ERCOT | CO | CO |  | Vendor Contract Mgt - Phase 2 | New | New |  | 2 - High | 29 | <$100k | $5M-$6M | 2007 | [7 empty] | 19 | 21548 | The project will automate and link Hummingbird's contract approval process with the contract and vendor database.
Estimated Resource Capability = $5,750,000
2050 | ERCOT | CO | CO |  | Project Portfolio Management System | 60058_01 | Not Started |  | 2 - High | 30 | $500k-$1M | >$6M | 2007 | 2.1 | 119 | [5 empty] | 13 | -644026 | Provide additional portfolio analysis features to existing project scheduling tool that allows for tracking and reporting on project portfolio health, performance, budgets, costs and issues.
| ERCOT | CO | CO |  | Patrol path and 3 wheel vehicle for Taylor | New | New |  | 3 - High / Medium | 31 | $100k-$500k | >$6M | TBD | [7 empty] | 24 | -162355
1480 | ERCOT | CO | CO |  | Continuous Monitoring Software | 60026_01 | Not Started |  | 9 - Parking Lot |  |  |  |  | 1.2 | 59 | [5 empty] | 15 | -194924 | Provide automated capabilities to review and interrogate data from ERCOT's key business systems to help ensure there are no fraudulent transactions being processed throughout the organization. | Intangible benefit: Provide improved assurance that fraud is not being perpetrated throughout the organization
1535 | ERCOT | CO | CO |  | NERC Tracking Database | 60032_01 |  | F/U w/ Grimm | 9 - Parking Lot |  |  |  |  | 1.2 | 66 | [5 empty] | 21 | -44482 | Track NERC recommendations, Compliance audit issues, mitigation plans, investigations and correspondence to market participants. | Creates a common data repository for various issues that are currently tracked separately
300 | ERCOT | CO | CO |  | Intrusion Detection/Intrusion Protection (IDS/IPS) | 50132 | Closing | Pena | N/A |  |  |  | 2Q2006 | 1.0a | 0.19 |  |  |  | 1.1 | 5.3 | 23 | -925451 | Implement Network Intrusion Detection and Intrusion Protection Systems into the ERCOT network at the perimeter and internal network layers. | Allows ERCOT to appropriately respond to E&Y audit findings; improves monitoring capability of data transported across the network, allowing for the identification of attack or malware activity
310 | ERCOT | CO | CO |  | Collateral Calculation | 50017 | Execution | Booker | N/A |  |  |  | 3Q2006 | 1.0a | 0.2 |  |  |  | 1.1 | 28 | 17 | 26954 | Automate much of the "data gathering" piece of credit monitoring that is currently done manually using Excel spreadsheets. | Significant intangible benefits plus time savings in Credit group due to automation of collateral calculations
320 | ERCOT | CO | CO |  | Lawson SIR - Time Tracking | 50015_01 | Closed | Pena | N/A |  |  |  | Complete | 1.0a | 0.21 |  |  |  | 1.1 | 26 | 18 | 63910 | Replace manual Excel time tracking with online Lawson entry system for ERCOT employee time reporting | Internal ERCOT benefit: increased efficiencies in Finance department and improved ease of time entry for ERCOT employees
961 | ERCOT | CO | CO |  | IT Incident Reporting | 50152 | Closed | Booker | N/A |  |  |  | Complete | 1.1 | 11.1 | [5 empty] | 21 | 102197 | Implement an automated IT Incident Reporting to address inaccuracies and deficiencies of existing reports, provide greater auditing and issue tracking functionality, and better information to aid in decision making on issues that occur within the production environment
962 | ERCOT | CO | CO |  | Log and Event Management | 50140 | Execution | Pena | N/A |  |  |  | 3Q2006 | 1.1 | 11.2 |  |  |  | 1.1 | 5.6 | 27 | -655320 | Through the use of robust technology, identify, correlate and investigate possible incidents where systems were attacked directly (popularly know has hacking) or indirectly (worms, viruses and denial of service). Allow a single console system to permit the investigation of Intrusion Detection, Operating System, Application logs for event detection and analysis. | Manual monitoring of logs is impossible without either a software solution or a large number of analysts. A software solution is recommended.
963 | ERCOT | CO | CO |  | Secure E-mail | 50141 | Execution | Pena | N/A |  |  |  | 3Q2006 | 1.1 | 11.3 |  |  |  | 1.1 | 5.4 | 19 | -166446 | Provide the ability to encrypt email that may contain confidential or restricted information. | Response to an audit finding that suggests certain enhancements relating to e-mail security.
964 | ERCOT | CO | CO |  | Document Management | 50123 | Execution | Thomas | N/A |  |  |  | 4Q2006 | 1.1 | 11.4 |  |  |  | 1.1 | 19 | 24 | 8370569 | To implement a document management system and roll out to one or more ERCOT departments in addition to the current HR, Legal, and Finance implementation. | Improved efficiency in document handling within ERCOT
1054 | ERCOT | CO | CO |  | Proxy Server | 60076_01 | Execution | Pena | N/A |  |  |  | 4Q2006 | 1.1 | 19.4
1057 | ERCOT | CO | CO |  | Security Camera Enhancements | 50106_01 | Execution | Pena | N/A |  |  |  | 3Q2006 | 1.1 | 19.6 |  |  |  | 3.2 | 129 | 26 | -234135 | To enhance visibility of the Austin/Taylor data centers, the EMMS test lab, and the Blue building.
1060 | ERCOT | CO | CO |  | Risk Management (incl Security Auditing and Monitoring SW) | 60014_01 | Planning | Pena | N/A |  |  |  | 4Q2006 | 1.1 | 20 | [5 empty] | 27 | -349170 | To acquire software for the purpose of identifying vulnerabilities within the network, operating systems and applications. Provide automated, real time capabiliteis to audit and monitor compliance with ERCOT's security infrastructure, policies, and procedures. | Improve ERCOT's ability to identify vulnerabilities associated with the network, internet-facing applications and other cyber-critical applications
1085 | ERCOT | CO | CO |  | Vendor and Contract Management | 50111_01 | Execution | Thomas | N/A |  |  |  | 3Q2006 | 1.1 | 22 |  |  |  | 3.3 | 142 | 21 | -254403 | Provide database which provides tracking and reporting regarding all vendors and vendor contracts,.to help enforce company policies, procedures, and financial reporting. Regulatory support to include: Sarbanes-Oxley, Corporate Contract Management Procedures. | Resolves an audit finding and increases internal controls; provides more efficient reporting capabilities; increases reliability of information about vendors and vendor contracts
1110 | ERCOT | CO | CO |  | Host Intrusion Detection System | 60016_01 | Planning | Pena | N/A |  |  |  | 4Q2006 | 1.1 | 25 | [5 empty] | 26 | -298222 | Implementation of a system for reporting attacks against individual servers thereby increasing the granularity of incident monitoring and investigation. | Event correlation gives ERCOT the ability to identify incidents at a very early stage and mitigate damages; increased productivity of Security Operations group
1111 | ERCOT | CO | CO |  | Lawson SIR - Process Flow | 50015_02 | Planning | Wilkinson | N/A |  |  |  | 4Q2006 | 1.1 | 25 |  |  |  | 1.1 | 26 | 19 | 145389 | Implement Lawson Process Flow to enable workflow processing within Lawson. 1) Automation of requisition approval process; 2) Email notifications to approvers when a requisition is awaiting their approval; 3) Peform the financial control of allowing only certain users to approve GL entries over a specific amount | Reduction in manual effort tracking purchase orders
1550 | ERCOT | CO | CO |  | Computer Aided Facilities Mgmt | 50149 | Closed | Troxtell | N/A |  |  |  | Complete | 1.2 | 68 |  |  |  | 1.2 | 43.65 | 22 | 24100 | This project supports: • Long-range and annual facility planning • Facility financial forecasting • Real estate acquisition and/or disposal • Work specifications, installation and space management • Architectural and engineering planning and design • New construction management and build-out • Maintenance and operations management • Telecommunications integration, security and general administrative services • Floor plans • Building and property information • Space characteristics and usage • Employee and occupancy data • Workplace assets (furniture and equipment) • Business continuity and safety information • LAN and telecom information | Enhance asset management reporting; automate key business processes (6 hours per workday)