## Issues Completed
1 | Checklist/Tracking Tool | Susan Munson | Assigned to | Due Date | Complete | Comments
| Discuss at December 2003 | summary list of scripts for each relationship to be displayed on the checklist | J Teel |  | Close due to being covered under Project PR40019 | Table this item. 4/7/04 notes - 1)Need to bucket the checklist items so that someone can summarize by relationship - CR 1 / TDSP 1 - here are the 15 scripts that are being done with that relationship Refer back to a script - link on the script ID to open 09/23/04 update - No website enhancements will be ready for 0105 either. Project put in place instead, where Testing will now have responsibility instead of having to go through Developers. Choice was either same old process & struggle every flight, or get it right & have control. 01/20/05 - issue is addressed within project PR40019. 3/24/05 - PR40019 - updates to testing website. Not included in ercot.com project. Moving out of planning phase into execution phase on Wed 03/30. Money issue. Have a timeline and 0705 is the target.
|  | Add script step relationship logic whereby MP's can't check off entries when req'd predecessor script step has not been checked | S Munson |  | Close due to being covered under Project PR40019 | 07/15/04 - In Review. Will not be ready for 0504 nor 0904 - future enhancement. 01/20/05 - issue is addressed within project PR40019.
|  | Extra text on checklist - reduce amount of text |  |  | Complete | In Demo phase. Will see in the next set of enhancements.
|  | support checklist items with concurrent CR's and between TDSP and CR's |  |  | Complete | In Demo phase. Will see in the next set of enhancements.
|  | Add dropdown list for the exception/comment. |  |  | Complete | In Demo phase. Will see in the next set of enhancements.
|  | Create new field for ESI ID |  |  | Complete | In Demo phase. Will see in the next set of enhancements.
|  | Clean up Frame tables to prevent checklist entries with NO actions |  |  | Complete | In Production
|  | Change checklist to allow the "Update Checklist" button to be visiable at any point on the page |  |  | Complete | In Demo phase. Will see in the next set of enhancements.
|  | Add logic to highlight receiving party in a different color from the intitating party. |  |  | Complete | In Demo phase. Will see in the next set of enhancements.
|  | Addd receiving party symbolic on page header next to initiating symbol |  |  | REMOVE | Have been advised this is not of concern any longer.
|  | Remove FA checkboxs. | Susan Munson |  | Complete | In Production
2 | Communication/Education | Sharon Polliard - Documentation subteam | Assigned to | Due Date | Complete | Comments
|  | Market Orientation - improve communication lines (jen to look at notes) | Kristi and Sherri |  | Complete | Revamped with 0504. Will help with 0904. Feedback rcvd from 0504 was that it was very good & very helpful. Previously was discussions that were useless to them between technical & business users.
|  | More details of testing process for market participants | Sharon Polliard |  | Complete | look at TMTP in May/June TTPT 4/7/04 - feedback - the presentations were more focused, the skit was good, best one we've had, targeted to both technical and business side of the business, wasn't overwhelming, longer meeting, but we didn't have
|  | Lessons Learned | Karen Bergman |  | Complete | Talk with Glen about a market meeting 1/2 day for MCT, 1/2 day for testing. 07/15/04 - going in notice from TTPT.
|  | Better Prepared documentation for new market participants - document created and easy to find | Sharon Polliard |  | Complete | A lot has been adding to ercot.com instead of appearing on etod. Look at TMTP in May/June TTPT New MP said it was helpful documentation/clear
|  | Update web pages indicating the correct way to get added or removed to the List Serves (not just TTPT) | ERCOT |  | Complete | Updated under all Committee & Subcommittee links. 22 in total.
|  | Testing email for questions that is monitored and responded to by test team | Sherri Slagowski |  | Complete | TTPT voted (03/03/04) that a separate inbox is not needed. General questions could be sent to TTPT list, added to TTPT agendas, to the Flight Admin or their Account Manager.
|  | testing minutes and general testing data on ERCOT website instead of ETOD (like TX SET) | Sherri Slagowski |  | Complete | Find out from J Teel why this was requested. Per TTPT meeting discussion (01/07/04), do not feel this is wise. Link in Key Documents to ETOD should suffice.---Just meant the mtg minutes
|  | Lessons Learned | Karen Bergman |  | Complete | Talk with Glen about a market meeting 1/2 day for MCT, 1/2 day for testing. NOTES: 07/15/04 - going in notice from TTPT.
|  | Survey - hand it out during the meeting | Sherri Slagowski |  | Complete | E-mailed survey for Flight 0504 and only received two responses back. Survey was distributed during Flight 0904 Market Orientation meeting.
|  | Market Orientation Material | Sherri Slagowski & TTPT |  | Complete | Review Orientation Material for Flight 0105 during October TTPT meeting
| Retail Testing Web Site |  | Assigned to | Due Date | Complete | Comments
|  | Correct links that do not work | Suzette Wilburn |  | Complete | Testing Demo as time permits.
|  | review security on Retail Testing Website site - some things should be accessible by anyone | Suzette Wilburn |  | Closed based on Comments | 4/7/04 notes - send list to Susan 01/20/05 - follow up with Suzette on status. Any items outstanding? File Cabinet is secured the way it should be. FAQs no longer require login, nor do Contacts.
|  | Update TSW testing portion of website | Susan Munson |  | Close due to being covered under Project PR40019 | Part of the MIMO changes 4/7/04 - grammatical errors will be fixed next time business section of the CR / CR in the market - testing a new relationship Contacts - so you see Flight test vs. Production - add Production Contacts to TSW ? Then keep the list 01/20/05 - issue is addressed within project PR40019.
|  | Audit trail needed on TSW |  |  | Close due to being covered under Project PR40019 | Deferred to after 0504. 07/15/04 - Still WIP 01/20/05 - PR40019 will provide a better audit trail.
| Test Flight |  | Assigned to | Due Date | Complete | Comments
|  | To Do list for what needs to be updated before a flight. | Flight Admin |  | Complete | KB thought this is what pre-flight timeline is for. More for orientation changes to the format of Flight 0504 & orientation have resolved this.
|  | improve communication of testing relationships and minimize changes in testing relationships | Flight Admin |  | Complete - 6/11/04 | More for new MPs to educate on the amt of work - add to orientation. Will have a lessons learned from Flight 0504 that will be incorporated into the next Flight Test
|  | Make sure ETOD scripts and ETOD files are updated before Frame 1 | Flight Admin |  | Complete - 06/11/04 | No ETOD in 0504. TTPT will create agenda item for future meeting to define requirements for an application that provides the same type of service as ETOD
|  | SR file updates (maybe part of a Frame 0 step) | script subteam |  | Complete - 06/11/04 | Communicated with TDSP expectations. New files for 0504. After 0504, script subteam - do we need to keep this script? 4/7 notes - need new files from the TDSP - are people using them? There has been discussion that people are using them
|  | Transition from testing to production. | Sherri Slagowski |  | Complete | Transition from testing to production. EDI via FTP verbiage. Jamie Lavas has information & has discussed with Jennifer Teel. This still seems to cause issues & is not real smooth.
3 | Scripts | Jennifer Teel | Assigned to | Due Date | Complete | Comments
|  | New Format for scripts | Script Subteam |  | Complete
|  | Method of updating scripts easier | Jen and Brian S |  | Complete | Currently have the ability to change scripts, but not upload new ones. Take the spreadsheets being developed & upload directly. If changes are necessary, GUI to be used to update & can be done in TTPT writing requirements now. MIMO can be loaded directly in - not manually. 4/7/04 - the work done for MIMO flight 0504 completed this item.
|  | Ability to update scripts in TTPT or script subteam | Jen and Brian S |  | Complete | Currently have the ability to change scripts, but not upload new ones. Take the spreadsheets being developed & upload directly. If changes are necessary, GUI to be used to update & can be done in TTPT writing requirements now. MIMO can be loaded directly in - not manually. 4/7/04 - concerns about version control if we had the ability to change in a meeting. Closing the item.
|  | provide counts of required sent and received and actual sent and received on scripts | J Teel |  | DELETE - because of the new format of the calls | keep this tabled item - the calls are going to change the format the market summary page is still there Bring up at the June TTPT meeting
|  | Documentation on how to use checklist and what is required to be done on checklist |  |  | 01/20/05 - Check List Help screens were updated in the fall. Will now distribute during testing orientation as a handout. | Documentation for take home. Help screen on checklist needs to be updated (Not priority for 0504-future enhancement). Web Conference 5/7. 07/15/04 - In Review. Future checklist enhancement. Some will be done in Mkt Orientation.
|  | FAQ's updated more frequently | Julie Ballentine |  | COMPLETE | 1) Clean up of old and there is production items listed within (FasTrak?) 2) Is there a way to show the date of the item has been updated need to have a team assigned to review? 3) Should we put a counter on the items to show how often the site is acces. 07/15/04 Tabling till August TTPT mtg.
|  | Clean out file Cabinet | Suzette Wilburn |  | COMPLETE | In Progress - 07/15/04
|  | Archive old data | Suzette Wilburn |  | COMPLETE | In Progress - 07/15/04

## Doc Changes
date added | person submitting | person assigned | issue | document affected | notes | status | resolution
2006-04-18 | B Pidcock |  | Emphasis on PGP Keys | Mkt Orientation | review April TTPT notes for further details
2006-04-18 | G Wingerd |  | Update Approved Flight Schedules to include Black out periods during testing time frames | Approved Flight Schedules | Work with Glen on formatting of adding addtl lines or color coding due to formatting issues.
2006-06-01 | S Slagowski |  | Add to Approved Flight Schedule for 2006 & 2007 the verbiage for when TWs are locked & unlocked.
2006-06-01 | S Slagowski |  | Add to Approved Flight Schedule for 2006 the black out periods for last 2 flights.
2006-06-01 | S Slagowski |  | Add 3 new scenarios to Retail Testing Matrix to use as testing guideline |  | to CR, to TDSP, to MOU/EC TDSP
2006-06-01 |  | Doc SubTeam | DUNS + 4 verbiage update | TMTP
2006-07-13 |  | Doc SubTeam | Update Random Testing Document within File Cabinet of RTW | Random Testing | Non Established scenarios for TDSP/CR. Need documentation update regarding notification to Market Participants when an MP makes changes for a Flight Test that would affect ofther MPs. Whatever changes are determined by Script SubTeam, update TMTP & Market Orientation material
2006-07-13 |  | Farrah Litton | 2007 Approved Flight Schedule - update verbiage, put into Word doc & get posted to ERCOT.com & RTW
2006-07-13 |  | Sherri Slagowski | Update Excel Future Flight Schedule verbiage to match Approved Flight Schedule verbiage
2006-07-13 | Roger Tenenbown | Script SubTeam | update scripts for NAESB logs to be sent only when requested for issue research. | Flight Scripts
2006-07-13 |  | Brian Pidcock | update Market Orientation material re NAESB logs - that info is available for research | Market Orientation PowerPoint
2006-07-13 |  | Sherri Slagowski | Update Connectivity Contact to appear on Contacts page of RTW
2006-07-13 |  | Chuck Moore | let RMS know deadline for MCT Documentation and timeline for adjusting 0407 Flight Schedule |  |  | Completed - 07/13/06 | Chuck sent email to Shannon Bowling & Blake Gross
2006-07-13 |  | Sherri Slagowski | Gaining/Losing CRs for MarkeTrak testing. |  | Updated matrix needs to be sent advising who Gaining & Losing CR is for GUI scripts.

## Doc Changes Completed
date added | person submitting | issue | document affected | notes | status | resolution
2004-08-15 | S. Polliard | Documentation subteam will review the White Paper before the next TTPT to ensure that it is kept updated per the new Flights | white paper | 01/20/05 - review for updates on Version 2.1 04/27/05 - White paper to be reviewed during 06/02/05 Script Sub Team 06/09/05 - compare to TMTP and possibly add info from this document to the TMTP next time it is reviewed by Documentation sub-team | Marla working on as of 09/12/05. Red line to participants by 09/19/05. 10/05/05 - 3 calls were attempted. Discussed during 10/05/05 TTPT mtg. Should White Paper be incorporated into TMTP? Group decision to have still available as an attachment until TMTP updated and incorporated. 11/16/05 - white paper incorporated into TMTP during today's mtg. Awaiting RMS approval. WIll keep as separate document until approved by RMS. Now that White Paper & TMTP Doc combined together, this item complete. Updated TMTP V1.4 approved by RMS in February 15, 2006.
2004-04-01 | Chuck Moore | Direct Energy requests that the TMTP be modified so that a REP doesn't need to go through all E2E testing if their service provider has already tested. | TMTP | also see DISCUSSION recorded in Apr TTPT minutes | Completed - Addressed in matrix | Issue will be addessed in new testing guidelines matrix
2004-04-01 | Sharon Polliard | Do any of you think the TMTP should be amended to have clarification that a change in a TPs already qualified business function status (ie, CSA, SO option, Outage option etc) is considered a non-emergency back end system change and should be tested durin | TMTP | be sure to include the Certification process impacts | Completed - Addressed in matrix | Issue will be addessed in new testing guidelines matrix
2004-04-01 | Sharon Polliard | Then, is the Back-end System Change Checklist even needed? Testing and implementation plans are already a natural part of testing and implementation of the test flight changes. | TMTP - page 12 | This checklist was included in the TMTP as a guideline for MPs because TTPT can't govern what goes on behind the black curtain of the MP's gateway. | Completed - The TMTP will need to be reviewed again in the future to see what is needed and what is not. Also to make it more relevant. Not sure when direction will be recvd to make those updates in the future. | Issue will be addessed in new testing guidelines matrix
2004-04-01 | Jennifer Teel | For Example, becoming CSA certified involves testing CSA01 with only ERCOT. CSA01 involves a CR sending an 814_18, receiving an 814_19 and receiving an 814_22 and sending an 814_23. The transaction samples could satisfy the sending transactions. Also | TMTP | Customer is at risk if no 814_22 loaded: for new construction, first time as CSA, and no energy on MVO | Completed - Only a CR new to mkt will test that script with ERCOT. Leave CSA script as is. This would test the 814_22. Has been handled by script sub-team. | Script subteam to determine if CSA script is adequate to test the process
2004-04-01 | Jennifer Teel | Another example, a certified and production CR wants to add an additional DUNS number (same EDI, same backend system) - this usually involves connectivity, penny test, transaction samples - possibilility of RA001 or SJ351. Does this need to wait? Can we | TMTP | Be sure to include the Certification process impacts. Address the different components and combinations involved. Same EDI, same backend, different banks, different Data base, differetn translator, etc | Completed - Addressed in matrix | Issue will be addessed in new testing guidelines matrix
2004-04-19 | APR TTPT meeting | Scripts sub-team and Documenation sub-team are to correlate work on creating a matrix that spells out different scenarios requiring testing or retesting and list the specific testing requirements. This could be referenced from the TMTP instead of contain | TMTP | Matrix is not meant to replace all the text sections in the TMTP document. The existing text is meant as a guideline. The matrix is meant to support and clarify the text with specific information. The documenation Sub Team will draft the matrix and sp | WIP - Documenation sub team is meeting the afternoon of May 5 to begin draft of Testing Requirements Matrix | Create a separate matrix that will be referenced from the TMTP doc 01/20/05 - COMPLETE. Appearing in Appendix of TTPT (possibly Appendix F)
2004-04-19 | Sharon Polliard | I am thinking that the TMTP should have a link directly from the Key Documents link of the ERCOT/ RMS/ TTPT site. The only thing there now is the white paper and the address for the testing website. I know you can get it from the testing website but that is too indirect. It is a key document of the TTPT and it should be under that link. | TMTP | add a link to the TMTP under Key Documents of the ERCOT/ RMS / TTPT site | COMPLETE | Suzette put request in. Link should be added by Fri Apr 23.
2004-04-21 | Sharon Polliard | Put a space in the footer between the version and the page number. Currently displaying TMTP V1.22 OF 36 | TMTP | Sherri will have updated. Submitted request to have etod updated as well as TTPT site under Key Docs. | COMPLETE 07/09/04 | SIR 8867 submitted on 05/20/04.
2004-05-05 | J Teel | Pretest Activities. PowerPoint is hard to read. Possibly go back to Word document. Would prefer to see each flight as being a single sheet. | etod.ercot.com & TTPT web page on ercot.com | ERCOT to take action item to create the Word document. Will keep presentation version for RMS. However, Word doc will be used for posting. | COMPLETE 07/09/04 | S Slagowski - SIR 8978 created for etod update. Test Flights are now in Word doc and each flight listed as a single sheet. Completed TTPT website update with new document.
2005-01-20 | J. Teel | Create TTPT Procedures |  | Sharon & Jenn have created first draft | Completing in 03/24/05 meeting. Either approving or re-working. | To be posted by next TTPT meeting in June 2005.
Dec, 2004 | TTPT | Create Transaction Sample Library |  | J. Ballantine to take first stab at creating draft library document. Then start building off of TX SET guideline examples and create new as required | COMPLETE | presented to TTPT during 01/20/05 mtg
2005-03-24 | S. Polliard | Banking information not communicated clearly enough to new MPs | TMTP or Retail Market Testing Orientation material |  | COMPLETE | Added additional verbiage in Retail Testing Orientation as of May 2005 TTPT meeting.
2005-07-06 | G Wingerd | Blurb added to Market Orientation re PGP and GPG | Market Orientation | Assigned G Wingerd. Connectivity Testing would be the place to put it. Review the orientation material before the next flight. | COMPLETE | Added to 1005 orientation material 8/9/05.
2005-07-06 | J Teel | Move 2006 Flight Schedules into Word document for RMS presentation/ approval | ercot.com & Retail Testing Website | Also send out to TTPT for distribution | COMPLETE | moved into Word doc for RMS presentation 07/14/05. Sent to TTPT distribution list same day as well.
2005-07-06 | J Teel | Blurb for ad-hoc testing involving ERCOT & CR | TMTP | Assigned G Wingerd. Doc sub team call to handle the action items. Still open through doc sub team 8/9/05. J Teel will get something organized in the next week or two. | COMPLETE | Completed - during TTPT mtg 09/12/05
2005-12-05 | S Slagowski | FAQs | RTW | Need to add Lesson's Learned and update FAQs with new ERCOT weblinks. | COMPLETE | New additions approved by TTPT on 04/18/06. Ready to load on RTW.
2006-01-09 | J Teel | 1) Update Flight Schedule for 2007 to include verbaige for ERCOT maintenance period. 2) Change orientation meetings from Wednesdays to Tuesdays to account for RMS schedules. 3) Look at adding one day to CR review of test bed | Approved Flight Schedules | Review June TTPT meeting for 2007 Flight Schedules. Will be good time to give to RMS. | COMPLETE | Completed - 06/01/06
2006-06-01 | S Slagowski |  | white paper | Remove White Paper from ERCOT.com | Since TMTP revised; no white paper anymore. White paper info included in TMTP now. | Completed - 06/01/06

## Mtg Issues
person submitting | date added | issue | assigned to | notes | status | resolution
J Teel | 2005-07-06 | TTPT Procedures Post under key documents on ERCOT website after TAC approval. Also remove team charter. |  | TAC did approve RMGRR 024 effective August 1; so the Retail Market Guide for August does reflect the verbiage change. It is not the complete TTPT Procedures though. However, the same verbiage is to appear in Protocol Section 23. PRR597 (which is the same verbiage added to the Retail Market Guide) is not due to be approved by TAC until 09/01/05. This would be the complete TTPT Working Group Procedures that would mirror the TX SET Working Group Procedures. | Pending 09/01/05 approval by TAC for PRR597. 10/03/05 - verbiage resubmitted under new PRR as language was not consistent with RMG. J Teel will submit to protrevrequest@ercot.com. 11/16/05 - J Teel rcvd new form from S Mingo. J Teel will submit in the near future. 02/22/06 - hold on this now. According to February RMS meeting, they are looking to update all the WG procedures. Kyle to get a better read from Shannon on this.
S Munson | 2005-10-05 | ACKs on TW | doc subteam | List of checkboxes. Will put on doc subteams plate as low priority to review/possibly combine checklist items. Streamline all checklist items. In line for Flight 0406. | 02/22/06 - no action taken at this time. Email to be sent to doc subteam - no need for mtg on issue. | Was this done? Check with Glen.
L Damen | 2006-04-18 | Get with Glen to document two exception cases for missed Flight orientations in the past. | S Slagowski | July 13, August 23, October 10, November 16

## Mtg Issues Completed
person submitting | date added | issue | assigned to | notes | status | resolution
J Teel | 2004-06-17 | Present the top 10 FAQ's at TTPT in June. Also a note that TTPT needs to define what the FAQ section should be. | J. Ballantine | 07/15/04 - Julie can bring to August TTPT mtg. 08/11/04 - Discussion took place re FAQs. Will send with the August TTPT minutes. A 2-4 hour session to be held to discuss at Sept TTPT. | Complete
J Teel | 2004-06-17 | Talk with TDTWG about a NAESB 1.6 lessons learned | Johnny | 07/15/04 - Johnny spk w/D McKeever. Hold off on lessons learned till after V2.0. August is earliest expected date to address - possibly Sept. | Complete | Sharon to distribute with TTPT minutes
J Teel | 2004-06-17 | Keep TTPT updated on status of minutes being posted on website | Karen Bergman | Posting of minutes will redirect you to the Testing website, which the minutes are posted. | Complete | http://www.ercot.com/Participants/Committees/TexasRetailTesting%20.htm.
| 2004-09-23 | Definition of Sub-LSE | S. Slagowski | Sherri check definition of sub-LSE. | Complete | No such terminology not to use it. Additional Duns for Certified Rep to be used.
| 2004-09-23 | ETOD meeting | J. Ballantine | Julie re-schedule a meeting on ETOD before end of year. | Complete | Meeting re-scheduled for 11/18/04
| 2004-09-23 | FAQs and New e-mail | G. Wingerd | Create an email distribution that will have ERCOT test team and ERCOT Client Relations representatives for questions and general email. This distribution email address will replace the ERCOT references in the FAQs. This was to be set up for 'Intent to Test' e-mails. | Complete | Glen Wingerd, Susan Munson, Kristi Hobbs, and Sherri Slagowski set on distribution list. RetailMarketTesting@ercot.com
| 2004-09-23 | FAQs | J. Ballantine | Julie will send out a new revised redline for review and feedback. We will review only the feedback at the next meeting and take a vote to adopt at the next meeting | Complete | Posted FAQs to ETOD and ercot.com
| 2004-09-23 | FAQs | S. Slagowski, C. Rohrer, and J. Ballantine | Sherri, Carrie, and Julie to work on creating a 'Going to Production Checklist' FAQ. Bring to TTPT for review next month. | Complete | Material created to be distributed in the Retail Testing Orientation. ERCOT, PUCT, and TDSPs each have a separate checklist.
J Teel | 2004-09-23 | Market Orientation Material for Flight 0105 | S. Slagowski | Sherri and ERCOT review orientation material for Flight 0105. Send out note to TTPT to review on website and bring back feedback to Oct. meeting. Will review slides at Oct meeting. | Complete | E-mail sent to TTPT 09/24/04
| 2004-09-23 | Documentation needs updating | S. Slagowski | Sherri to get with J. Lavas and J. Teel. ERCOT's cut-over documentation from testing to production still refers to FTP. | COMPLETE
| 2004-09-23 | TCW info posted to website | S. Slagowski and J. Teel | Sherri and Jennifer to contact TDTWG to get production TCW information posted on website | COMPLETE
| 2004-09-23 | Testing Matrix | G. Wingerd | Glen make tab on Testing Requirements Matrix that has definitions of all drop down box options | COMPLETE
| 2004-09-23 | TMTP Guide | Doc SubTeam | Documentation sub-team to add section numbering to TMTP document. | COMPLETE
| 2004-09-23 | TMTP Guide | Doc SubTeam | Documentation sub-team to add contingency provider section to TMTP document option | COMPLETE
| 2004-09-23 | FAQs | J. Ballantine | See list of additional To Do's under FAQs | COMPLETE
| 2004-09-23 | FAQs | J. Ballantine | Julie to go through FAQs and take out specific links to a form page and just go to the web page that refers to the specific document. The person can then click on the link to the document from that page. This will allow for the document name to change without having to change the link in the document. | COMPLETE
| 2004-09-23 | FAQs - TDSP links | TDSPs | TDSPs to verify that the link to their company's FAQs is correctly identified. | COMPLETE
J. Teel | 2005-01-18 | SCR for automated testing system | J Ballantine | ready in draft form. To review during 01/20/05 TTPT mtg. | COMPLETE | SCR742 submitted March 2005.
J Teel & J Ballantine | 2005-04-27 | Update TTPT contacts on Retail Testing Website | S. Munson |  | COMPLETE | S Munson updated TTPT contacts.
B. Pidcock | 2005-04-27 | Daily Flight Progress Comparison | G Wingerd | Post on Retail Testing Website Daily Agenda to see delta gap. | COMPLETE | Completed starting the day after April's TTPT mtg.
J Teel | 2005-04-27 | Send at least 2 wks prior to TTPT Flight 0405 Lessons Learned | G Wingerd |  | COMPLETE | Reviewed during TTPT mtg 06/09/05
J Teel | 2005-04-27 | Check with each TDSP if they have updates to their Checklist - Testing to Production for Market Orientation | C Rohrer & S Slagowski | Updates to be provided to S Slagowski by 5/18/05 | COMPLETE | Received one for NEC for the first time. CNP updated thiers. Both included in orientation material.
J Teel | 2005-04-27 | Remove IDR Test Data under TTPT page of ercot.com | S. Slagowski | Remove entirely from site | COMPLETE | Removed from website 05/20/05
J Ballantine | 2005-04-27 | Fix the "All" Filter on Texas Retail Testing Website for TSW page & Contacts page to show only valid TSWs and contacts | G Wingerd & S Munson | J Ballantine requested due date of 05/15/05 | COMPLETE | Completed the day after April's TTPT mtg.
S. Polliard | 2005-04-27 | Flight Progress Comparison charts & graphs | G Wingerd | May be able to post in the File Cabinet weekly (3 charts) until PR40019 completed. Add | Will put on the list & ask for prioritization at next TTPT Mtg 10/05 To be posted on website. Item captured on Enhancements list. Tentatively slotted for implementation January 2006. | Assigned a release date for RTW. Considered Complete during TTPT meeting 11/16/05.
J Teel | 2005-06-09 | Create a CBA for SCR 742 | G Wingerd, J Teel, & J Ballantine |  | COMPLETE
J Robertson | 2005-06-09 | Ask TX SET about processing order of Disconnects & Reconnects | J Robertson & J Teel (Script subteam) | Discussed at TX SET. Update to be provided from Kyle or TX SET meetings. Jen will bring to next TTPT mtg. | COMPLETE | Per J Robertson 09/12 - none of the TDSPs currently have priority processing for disconnects & re-connects as far as sequencing.
S. Polliard | 2005-07-06 | Elect new TTPT Vice Chair for S Polliard; elect new Documentation Sub Team chair | J Teel | Sharon resigning 10/28/05. Send nominations to S Munson by August mtg? Operate TTPT with one vice chair for two months? | COMPLETE - 09/12 | Vice Chair - decided against it - will wait for 2006 nominations. J Teel will be seeking assistance in November for notes of TTPT. Marla Hanley volunteered for Doc Sub Team Chair.
J Teel | 2005-07-06 | Market Orientation material for Flight 1005 | S. Slagowski | ways to change up orientation. Get volunteers for presentations? Ways to have TDSPs present? Have TTPT members present? | COMPLETE - | Brian Pidcock to speak on behalf of TDSPs for orientation 1005.
J Teel | 2005-07-06 | Orientation ideas compiled and bring up at next TTPT meeting. | S. Slagowski | due to full agendas, will address at future TTPT meeting. 10/05/05 - Ideas discussed during 10/05 TTPT meeting. | COMPLETE
J Teel | 2005-08-09 | Testing to Production updates from TDSPs. | S. Slagowski | Send email to remind any updates need to be received. | COMPLETE | 2005-08-16
J Teel | 2005-08-09 | Documentation sub team call to take place | M Hanley | Meeting scheduled for no later than week of 09/18. | COMPLETE
| 2004-09-23 | Documentation sub team to review White Paper |  | Review at next version release 2.1 Marla working on as of 09/12/05. Red line to participants by 09/19/05. | 01/09/06 - COMPLETE | COMPLETE - 02/22/06 Going to vote - incorporated changes with TMTP.
J Teel | 2005-10-05 | NAESB EDM | TTPT members | Should the two new encryption software version & SSL certificate authority be mandatory or optional? Action item for everyone to go back to their companies & find out for next TTPT meeting. | Completed 11/16/05 | 11/16/05 - determined fields will be kept mandatory at this point. Mixed opinion whether it is needed or not. If one MP needs it, will keep. EC Power expressed need.
J Teel | 2005-11-16 | Change Flight Orientation Date on Approved Flight Schedule | S Slagowski |  | Completed 11/17/05 | Changed on 'old' ercot.com under TTPT Key Documents and Texas Retail Testing sites. Changed on Retail Testing Website. Changed on 'new' ercot.com.
J Teel | 2005-11-16 | Retail Testing Website - link retail orientation mtg info under the Notices | G Wingerd |  | Completed 11/17/05 | notice applied to RTW
J Teel | 2005-09-12 | Clean up the Testing Matrix & File Cabinet for new script names & STK29 & add CON51 & CON56 to a banking change | G Wingerd |  | 11/16/05 - company abbreviation name updated. STK29 not incorporated yet. 01/09/06 - working on | Completed - 02/22/06
G Wingerd | 2005-11-16 | Add to the FAQ simulated dates as they relate to PGP creation | G Wingerd |  | COMPLETE | Completed - 02/22/06
C Moore | 2006-02-22 | Let Brittney know meeting dates for future TTPT meetings & to remove March meeting. | S Slagowski |  | COMPLETE | Brittney cancelled 03/22 meeting. Added 04/18 meeting & 06/01 meeting.
S Slagowski | 2006-02-22 | Have FAQ list on ercot.com point to RTW (same shared doc). | S Slagowski |  | COMPLETE | Completed - 04/25/06
S Slagowski | 2006-06-01 | Get TTPT Dates updated on ercot.com under TTPT page. | S Slagowski | add 06/01/06, 06/19/06 (scripts), 07/13/06, 08/23/06 dates | COMPLETE | Completed - 06/02/06
S Slagowski | 2006-06-01 | Book next two TTPT meetings with B Albracht. | S Slagowski | 07/13/06 & 08/23/06 meetings booked & reserved with Brittney | COMPLETE | Completed - 06/02/06
B Pidcock | 2006-06-01 | Flight Administrator title not on Contacts page of RTW. FA term doesn’t scream out after market orientation… even though orientation refers to that title over & over. | S Slagowski | Update Contact Type on Contacts tab of RTW to reflect title Flight Administrator | COMPLETE | Completed - 06/09/06

## Top 10 TTPT
Date Added | TTPT Accomplishments | Notes | Completed
2005-06-09 | Flight 0105
2005-06-09 | Flight 0405
2005-06-09 | Random Testing Pilot | run in both 0105 & 0405 Flights
2005-06-09 | SCR742 | Automated Testing; submitted and approved
2005-06-09 | Script Development & Testing Methodology for V2.1 Testing | Flight 1005
2005-10-05 | Flight 0705
2005-10-05 | Enhanced Retail Testing Website (RTW) | Project PR40019; roll out of the new system
2005-10-05 | TMTP Updates by Documentation SubTeam
2005-10-05 | TTPT Procedures created and placed in Protocols & RMG | Protocols updated
2005-10-05 | PIVAR - Post Implementation Verification and Reporting | Initial analysis complete; criteria established
2005-10-05 | Flight Metric Chart - Statistic Graphs posted on Retail Testing Website | comparison of current flight from previous flight
2005-10-05 | Flight Planning for 2006
2005-10-05 | Transaction Sample Library
2006-01-09 | Flight 1005
2006-01-09 | Retail Testing Website Enhancements | Ongoing monthly releases for updates to the RTW
2006-01-09 | Implemented Ad Hoc testing for service provider changes; banking change, and additional DUNS | Implemented February 2005
2006-02-23 | Moved TTPT meetings to every 6 weeks (2 wks prior to orientation - 1 time during Flight). Cut out 4 meetings per year (33%)

## 2006 Goals
Date Added | 2006 Goals | Notes | Completed
2006-01-09 | FasTrak Testing
2006-01-09 | Conduct 4 scheduled Flights as planned
2006-01-09 | Continue to enhance Retail Testing Website
2006-01-09 | Flight Planning for 2007
2006-01-09 | TMTP updates
2006-01-09 | Conduct Flight Orientation and continue to improve and modify as required to support testing
2006-01-09 | Support of TX SET Version upgrade if required or RMS requested market testing
2006-01-09 | TTPT Procedures and Protocols updates
2006-01-09 | Update SCR742 documentation for 2007 Prioritization