## Slide 1: MO Projects Update 2006 PPL Status & Budget Update 2007 PPL Update
Adam D. Martinez
Mgr, Market Ops Divisional Projects Organization
ERCOT
COPS Meeting
July 25, 2006

## Slide 2: 2006 PPL Status and Budget Update
Current Stats: 3 Closed 0 Initiation 5 Planning 4 Execution 3 Not Started 3 Deferred/Combined/Cancelled
PLEASE NOTE: Changes since last COPS update noted in red font. PPL posted to ERCOT.com (http://www.ercot.com/services/comm/projects/index.html) may not
reflect recent changes noted here
Srce | Project | Project No. | Current Phase | 2006 Priority | 2006 Rank | 2006 Budget Range | 2006 Running Range
M | Enhancements to SCR727 - Market Access | 50024_01 | Execution; 2007 PPL Impact | 1.0a | 0.05 | $500k-$1M | $500K-$1M
M | Enhancements to SCR727 - Market Enhancements | 50024_02 | Planning; 2007 PPL Impact | 1.0a | 0.05 | $100k-$500k | $1M-$3M
M | Enhance ESIID Lookup Function | 50025 | Execution | 1.0a | 0.06 | $100k-$500k | $1M-$3M
P | EDW BI Reporting Tool | 50004 | Closed | 1.0a | 0.15 | <$100k | $1M-$3M
E | Lodestar Extracts | 40042_06 | Execution | 1.0a | 0.18 | $100k-$500k | $1M-$3M
M | EPS Meter Data | 30026 | Execution | 1.0b | 0.54 | <$100k | $1M-$3M
E | TCR Report Enhancements Phase II | 40015_02 | Execution | 1.0b | 0.59 | <$100k | $1M-$3M
E | SCR 727 Phase II | 40007 | Execution; 2007 PPL Impact | 1.0b | 0.71 | $100k-$500k | $1M-$3M
M | Settlement Mismatches Inter-QSE Schedules / Notification for Mismatched Inter-QSE Schedules | 50128 | Closed | 1.0b | 0.87 | <$100k | $1M-$3M
MO Cut Line (Initial placement based on consolidated ERCOT PPL; MO Allocation = $2.44M) |  |  |  |  |  |  | 
M | Calculation of Losses for Settlement | 60068_01 | Not Started; 2007 PPL Impact | 1.1 | 32.6 | <$100k  $0 | 
M | TML Phase 3 - Wholesale Enhancements | 40103_01 | On Hold (Planning); 2007 PPL Impact | 1.1 | 7 | $100k-$500K | $1M-$3M
E | Lodestar 4.0 Upgrade | 40066_04 | Planning; 2007 PPL Impact | 1.1 | 12 | $100k-$500k | $1M-$3M
M | Extension of Credit Against OOM Start Up | New | Not Started; 2007 PPL Impact | 1.1 | 12.1 | <$100k  $0 | 
E | Maestro Upgrade | 50137 | Execution | 1.1 | 16 | $100k-$500k | $3M-$5M
MO Capability Range (Line placement varies based on Forecasted Spend for Portfolio) |  |  |  |  |  |  | 
E | MV90 Upgrade Part 2 - Installation of Software | 50033_02 | Closed | 1.1 | 21 | <$100k | $3M-$5M
E | EDW Lodestar Decommission | 50030 | Execution; 2007 PPL Impact | 1.1 | 44 | $100k-$500k | $3M-$5M
E | REC Program Modifications | 60027_01 | Planning; 2007 PPL Impact | 1.2 | 61 | $100k-$500k | $3M-$5M

## Slide 3: 2007 PPL Update
Source | Source Doc | Project | Project No. | Current Status | 2007 Priority | 2007 Rank | 2007 Budget Range | 2007 Running Range
Market | SCR740 | Enhancements to SCR727 - Mkt Access | 50024_01 | Execution | 0 - Carryover | 0.1 | <$100k | <$1M
Market | SCR740 | Enhancements to SCR727 – Mkt Enhcmts | 50024_02 | Initiation | 0 - Carryover | 0.2 | <$100k | <$1M
ERCOT |  | SCR 727 Phase II | 40007_01 | Execution | 0 - Carryover | 0.3 | <$100k | <$1M
Market |  | TML Phase 3 - Wholesale Enhancements | 40103_01 | Hold | 0 - Carryover | 0.4 | $100k-$500k | <$1M
ERCOT |  | Lodestar 4.x Upgrade | 40066_04 | Initiation | 0 - Carryover | 0.5 | $100k-$500k | <$1M
ERCOT |  | EIS L* Transition to ODS (formerly EDW Lodestar Data Archive Transition to EDW) | 50030_01 | Execution | 0 - Carryover | 0.6 | <$100k | <$1M
PUCT/ ERCOT |  | REC Program Modifications | 60027_01 | Planning | 0 - Carryover | 0.7 | <$100k | <$1M
Market | PRR598 | Extension of Credit Against OOM Start Up (** COPS Review Requested) | New | New | 1 - Critical | 1 | <$100k | <$1M
Market | PRR661 | SCE Performance Enforcement Criteria | New | Not Yet Started | 2 - High | 1.4 | <$100k | <$1M
Market | PRR666 | Modification of RPRS Under-Scheduled Capacity Charge Calculation | New | Still in Stakeholder Process | 2 - High | 1.5 | TBD | 
Market | PRR667 | RPRS Uplift Charge and Under-Scheduled Charge Correction | New | Still in Stakeholder Process | 2 - High | 1.6 | TBD | 
Market | PRR565 | Calculation of Losses for Settlement | 60068_01 | Not Yet Started | 2 - High | 2 | <$100k | $1M-$2M
Market | SCR743 | QSE Dispute Extract | New | New | 2 - High | 3 | <$100k | $1M-$2M
ERCOT |  | Siebel to L* 5 - Rewrite | New | New | 2 - High | 4 | $100k-$500k | $1M-$2M
ERCOT |  | Transition of Production Reporting to EIS - Wholesale | New | New | 2 - High | 5 | $100k-$500k | $1M-$2M
ERCOT |  | Lodestar Web Services | 60030_01 | Not Yet Started | 2 - High | 6 | $100k-$500k | $1M-$2M
ERCOT |  | Upgrade to Load Profiling SW | New | New | 2 - High | 7 | $100k-$500k | $1M-$2M
Market | PRR426 | URC for Uncontrollable Resources (** WMS Review Requested) | 40057_01 | Not Yet Started | 3 - High / Medium | 8 | <$100k | >$2M
Estimated Resource Capability = $2,058,000 |  |  |  |  |  |  |  | 

## Slide 4: Posting of Project Information
Link: http://www.ercot.com/services/comm/projects/project_list.html
Proposed process
  PMO will work with MORO & SO DPOs to address posting of project-related documents to the web
  DPOs to seek input from Market
  Develop process and guidelines for ongoing updates
    Suggest posting of subset of standard documents/deliverables
    Posting of final versions only
    Legal and/or Security review required

## Slide 5: Standard Projects Deliverables
Impact Analysis
Project Request
Project Charter
Project Schedule
Time / Cost Estimate
Cost Benefit Analysis
Business Requirements
Conceptual System Design
Detailed Design
Environmental Design
Test Plan Template
Test Scripts
Training Documents
Migration Plan

## Slide 6
Adam D. Martinez
Mgr, Market Operations Divisional Projects Organization
ERCOT
(512) 248-3883
amartinez@ercot.com
Questions / Contact Information
Notes: <number>
<footer>
<header>
<date/time>