## Slide 1: RO Projects Update 2006 PPL Status & Budget Update 2007 PPL Update
Adam D. Martinez
Mgr, Market Ops Divisional Projects Organization
ERCOT
RMS Meeting
July 12, 2006

## Slide 2: 2006 PPL Status and Budget Update
Source | Project | Project No. | Current Phase/Status | 2006 Priority | 2006 Rank | 2006 Budget Range | 2006 Running Range
Market | Enhancement to FasTrak Tools | 50007 | Execution Phase | 1.0a | 0.03 | $1M-$3M | $1M-$3M
ERCOT | Service Oriented Architecture (TIBCO Parent) | 50121 | Execution Phase | 1.0a | 0.08 | N/A | $1M-$3M
ERCOT | Endpoint Services - Phase I (TIBCO Sub-project) | 50121_06 | Closed | 1.0a | 0.08 | $100k-$500k | $1M-$3M
ERCOT | Retail Business Processes (TIBCO sub-project) | 50121_07 | Execution Phase | 1.0a | 0.08 | $1M-$3M | $4M-$6M
ERCOT | Endpoint Services - Phase II (TIBCO sub-project) | 50121_08 | Execution Phase | 1.0a | 0.08 | $100-$500K | $4M-$6M
ERCOT | TX SET 2.1 | 40034 | Closed | 1.0a | 0.09 | <$100k | $4M-$6M
ERCOT | 2005 SIR Enhancements | 50026 | Closed | 1.0b | 0.89 | $100k-$500k | $4M-$6M
Market | ERCOT Outage Evaluation and Resolution, Ph. I &II | 60006_01 | Execution Phase | 1.1 | 8 | $1M-$3M | $4M-$6M
Market | Performance Measures Reporting | 60007_01 | Deferred to 2007 PPL | 1.1 | 9 | $1M  $0 | -
Market | Terms and Conditions Requirements | 60008_01 | Combined with TX SET 3.0 | 1.1 | 10 | $500k  $0 | -
RO Cut Line (Initial placement based on consolidated ERCOT PPL; RO allocation = $6.75M) |  |  |  |  |  |  | 
ERCOT | SOA Extend Footprint | 60010_01 | Cancelled, not on 2007 PPL | 1.1 | 13 | $500K-$1M  $0 | -
RO Capability Range (Line placement varies based on Forecasted Spend for Portfolio) |  |  |  |  |  |  | 
ERCOT | ESI ID Account Table Split | 60015_01 | Not Started; 2007 PPL impact | 1.1 | 23 | $100k-$500k  $0 | -
ERCOT | ERCOT.com Secured Area | 60077_01 | Planning Phase | 1.1 | 25.5 | $100k-$500k | $4M-$6M
ERCOT | EDW Siebel Transition | 50059_01 | Planning Phase | 1.1 | 26 | $500k-$1M | $6M-$8M
ERCOT | EDW TCH Transition | 50060_01 | Planning Phase | 1.1 | 27 | $100k-$500k | $6M-$8M
ERCOT | EDW EAI Transition | 50061_01 | Not Started; 2007 PPL impact | 1.1 | 28 | $100k-$500k  $0 | -
ERCOT | ETS Transition to EDW | 50088_01 | Not Started, 2007 PPL impact | 1.1 | 29 | $500k-$1M  $0 | -
Market | NEW NAME: TX SET 3.0, including Mass Transition and T&C's | 40038_01 | Planning Phase; major carry-over into 2007 PPL | 1.2 | 54 | $1M-$3M  $500-$1M | $6M-$8M
Current Stats: 3 Closed 0 Initiation 5 Planning 4 Execution 3 Not Started 3 Deferred/Combined/Cancelled
PLEASE NOTE: Changes since last RMS update noted in red font. PPL posted to ERCOT.com (http://www.ercot.com/services/comm/projects/index.html) may not
reflect recent changes noted here

## Slide 3: 2007 PPL Update – Key Dates
Date | Activity / Event | Expected Outcome / Deliverables | Status
05/02 | ERCOT RO CART reviews current divisional PPL | 2007 PPL draft with updated priorities, ranks and new projects | Complete
05/10 | RMS Review | Initial review and incorporation of RMS input to 2007 PPL | Complete
05/31 | ERCOT RO CART finalizes 2007 PPL for final review by RMS | 2007 PPL revision with updated priorities, ranks and new projects added | Complete
06/14 | RMS Review and Approval | Final RMS review and approval of 2007 PPL | Complete
06/19 | ERCOT Strategic Review Team approval | Review/approval of divisional PPLs | Complete
06/19 | ERCOT Executive Committee approval | Review/approval of divisional PPLs | Complete
06/22 | PRS Review | Initial review of all divisional PPLs | Complete
06/28 | Special PRS Review and Approval | Finalize recommendation and approval to send to TAC | Complete
07/06 | TAC Review and Approval | Final review and approval of all divisional PPLs | Complete
07/10 | ERCOT Executive Committee meeting | Follow up with TAC approval information | Complete
07/18 | Finance & Audit Committee | Preview of 2007 PPL with proposed priorities, ranks and requested funding levels by Program Area | Not Started
07/18 | Board of Directors | Review of all divisional PPLs | Not Started
08/15 | Finance & Audit Committee | Final review of all divisional PPLs | Not Started
08/15 | Board of Directors | Approval of all divisional PPLs | Not Started

## Slide 4: 2007 PPL Update – TAC Approved Version
Source | Source Doc | Project | Project No. | Current Status | 2007 Priority | 2007 Rank | 2007 Budget Range | 2007 Running Range
Market | PRR660 | TX. SET 3.0, including Mass Transition and T&C's | 40038_01 | Initiation | 0 – Carryover | 0.1 | $3M-$5M | $2M-$4M
ERCOT |  | EDW Siebel Transition | 50059_01 | Planning | 0 – Carryover | 0.2 | <$100k | $2M-$4M
ERCOT |  | ESI ID Account Table Split | 60015_01 | Not Yet Started | 0 – Carryover | 0.3 | $100k-$500k | $2M-$4M
ERCOT |  | EDW TCH (Transaction Clearinghouse) Transition | 50060_01 | Planning | 0 – Carryover | 0.4 | <$100k | $2M-$4M
ERCOT |  | ETS (ESIID Tracking System) Transition to EDW | 50088_01 | Not Yet Started | 0 – Carryover | 0.5 | $500k-$1M | $4M-$6M
ERCOT |  | EDW EAI Transition (inc. PaperFree & NAESB) | 50061_01 | Not Yet Started | 0 – Carryover | 0.6 | $100k-$500k | $4M-$6M
ERCOT |  | EIS Siebel to L* Data Comparison | New | New | 2 – High | 2 | $100k-$500k | $4M-$6M
Market | SCR748 | Website Enhancements for ERCOT Outages | New | New | 2 – High | 3 | $100k-$500k | $4M-$6M
Market |  | MarkeTrak Enhancements (Workflow & Reporting) | New | New | 2 – High | 4 | $500k-$1M | $6M-$8M
ERCOT |  | Exception Reporting / Monitoring Enhancements | New | New | 2 – High | 5 | $100k-$500k | $6M-$8M
ERCOT |  | Systematic Exception Reprocessing Functionality | New | New | 2 – High | 6 | $500k-$1M | $6M-$8M
ERCOT |  | Transition of Production Reporting to EIS - Retail | New | New | 2 – High | 7 | $100k-$500k | $6M-$8M
ERCOT |  | Integration of Commercial Operations Data in EIS (formerly Web Services that integrate L* and Siebel data for MPs) | 60028_01 | Not Yet Started | 2 – High | 8 | $100k-$500k | $6M-$8M
Estimated Resource Capability - $7,659,000 |  |  |  |  |  |  |  | 

## Slide 5
Adam D. Martinez
Mgr, Market Operations Divisional Projects Organization
ERCOT
(512) 248-3883
amartinez@ercot.com
Questions / Contact Information
Notes: <number>
<footer>
<header>
<date/time>