## Slide 1: Texas SET Version 3.0 Project PR40038_01
Retail Market Subcommittee Meeting
July 12, 2006

## Slide 2: Project PR40038_01 Consists of:
Mass Transition Long Term Automated Solution –
  ERCOT initiates the TX SET transaction to transfer the affected ESI IDs instead of transactions being initiated by POLRs during a Mass Transition
POLR Rule – Project 31416
  Develop new requirements and functionality to support Rule approved on June 29, 2006
Terms and Conditions – Project 29637
  Develop transactional solution, functionality, and processes to support the recently adopted Rule
Approx. 10-12 TX SET approved Change Controls for Implementation Guides
  Develop and approve change controls to clarify, correct, resolve problems, or enhance transaction functionality

## Slide 3: Status of Project – Mass Transition Long Term
All Change Controls have been identified and approved by TX SET on July 28, 2006
Market Requirements document has been drafted and near final completion, TX SET was awaiting POLR Rule approval
Retail Market Guide Revisions drafted and near final completion, TX SET was awaiting POLR Rule approval
Risk to Implementation Date of 07/01/2007:
  Low to No Risk based upon-
    All Requirements are finalized by 07/17/2006
    All Change Controls approved 07/28/2006

## Slide 4: Status of Project – POLR Rule Project 31416
Functionality/Process identified in the Rule:
  ERCOT shall create and manage Customer Billing contact data file in the event of a Mass Transition
  Document the process of assigning ESI IDs to POLR during a Mass Transition event
    Assignment of ESI IDs to POLR documentation has been drafted by ERCOT and will be part of the long term Retail Market Guide Revisions
  New customer class for Medium Non-Residential
Risk to Implementation Date 07/01/2007:
  Medium Risk based upon-
    Market agreed upon process and data requirements are identified and finalized for Customer billing data file
    Process for Assignment of ESI IDs identified and finalized
    All Requirements are finalized by 07/17/2006
    All Change Controls approved 07/28/2006

## Slide 5: Status of Project – Terms and Condition Project 29637
All Change Controls have been identified and approved by TX SET for the July 28, 2006 Change Control Conference Call
Market Requirements drafted and finalized
PRR 672 – Retail Market Timing Change Necessary for PUCT Project 29637
  PRS approved urgent timeline for August TAC and BOD discussion and possible approval to meet the v3.0 Implementation timeline
  Market Requirements identified in PRR, however ERCOT requirements and cost benefit analysis yet to be determined.
  Redlined changes only affect ERCOT Protocol timings
Risk to Implementation Date 07/01/2007:
  High Risk based upon:
    Will PRR 672 be approved through the ERCOT governance process in time enough that ERCOT can develop internal requirements and make system changes to meet production implementation date?
    ERCOT has completed an internal evaluation to determine alternatives for PRR 672 and there is time for Market approval of the alternatives along with time to develop
    All Requirements are finalized by 07/17/06
    All Change Controls are approved on 07/28/2006

## Slide 6: Approved Change Controls outside of T&Cs, POLR, and Mass Transition
All Change Controls have been identified and approved by TX SET on July 28, 2006
Requirements document created, if necessary, to capture functionality of change control
Risk to Implementation Date of 07/01/2007:
  Low to No Risk based upon-
    All Requirements are finalized by 07/17/2006
    All Change Controls approved 07/28/2006

## Slide 7: PR40038_01 Timelines
RBP PR50121_ 07
PR40038_01Tx SET 3.0 including Mass Transition and Ts & Cs (7/1/2007)
Jun 06
Jul 06
Aug 06
Sep 06
Oct 06
Nov 06
Dec 06
Jan 07
Feb 07
Mar 07
Apr 07
May 07
10/22Prod
7/15
5/1
Build
12/11
UAT
Stabilization
9/11
7/17
Business Req’mts
9/25
12/4
3/12
5/28
Conceptual Design
Detail Design
Build
UAT
7/1 Prod
Market Flight Testing
Market Requirements
7/3
Flight Testing
4/16 – connectivity
4/27 – Day 1
5/29 – Flight ends
Draft 3.0 TX SET Guides
9/1 – Due Date

## Slide 8: Recommendation
TX SET is recommending that RMS establish a Market Coordination Team (MCT) to:
  Manage TX SET v3.0 Project Scope
  Manage Project Schedules and Implementation Timeline
  Coordinate and Communicate Project progress:
    Market Participant Internal Design
    Market Participant Internal Development/Testing
    Implementation/Cut-over weekend task/timelines
    Go No-Go Criteria and Decisions
  Collaborate with RMS and/or Working Groups for their assistance when necessary to bring forward and resolve issues throughout the Project in order that the Production timelines can be met
  Allow the Market to have a single point of Communications for Project progress reports