## Slide 1
Update:
QA Build Out project
  All QA Build Out project activities are scheduled to be completed by 7/24/06
  MarkeTrak testing is on-schedule and is moving forward
  Do not anticipate any negative impacts to the MarkeTrak project
Summary of Project Status
PR-50007 Enhancements to FasTrak
As of July 5, 2006
Page 1

## Slide 2: MarkeTrak Project Schedule
June
July
August
QA Build-out Project Lock Down
(UAT & CERT Test Environments unavailable for 5 wks)
6/26-6/30
CERT Connectivity Test
7/17
Train the Trainer Sessions Start
(2 wks)
8/11
Final User Guides Avail
8/7
Mkt CERT Testing Start
(2 wks)
7/10
API & Bulk Insert UAT Start
(3 wks)
8/25
MP’s complete Internal Training
8/26
Go Live
6/2
GUI/Siebel interface UAT Complete
7/31
Train the Trainer Sessions End
7/13
API & Bulk Insert CERT Migration

## Slide 3
API Connectivity Testing
  Performed the testing during the week of June 26th
  5 MPs registered for this testing
  The purpose of the test was for the MPs to connect to the MarkeTrak URL and properly authenticate its digital certificate
  4 out of 5 MPs performed a successful test
PR-50007 Enhancements to FasTrak
As of July 5, 2006
Page 3

## Slide 4
MarkeTrak Training
  Houston training is July 18-21 at CenterPoint
  Dallas training is July 25-28 at TXU Energy
  Austin training is July 31st at ERCOT Taylor
  All training sessions will run from 9:00am to 4:00pm
  Individuals only need to attend one session
  Each session in Houston and Dallas is limited to 24 individuals
  Austin session at ERCOT Taylor is limited to 20 individuals
PR-50007 Enhancements to FasTrak
As of July 5, 2006
Page 4

## Slide 5
MarkeTrak Testing
  MarkeTrak Testing API/GUI: 8/7/06 – 8/18/06
  Testing Participants
    API testing is required (5 MPs)
    GUI testing is voluntary (4 MPs)
    API and GUI combined testing participants (3 MPs)
  Additional API ad-hoc testing will be permitted during testing period (8/7/06 – 8/18/06) only when ALL MPs have successfully complete API test scripts
  LIMITED ERCOT resources will be made available for API ad-hoc testing
PR-50007 Enhancements to FasTrak
As of July 5, 2006
Page 5

## Slide 6
Project Cutover Plan Highlights
Prior to Migration Weekend
  Reports of Issues >6 months old
    ERCOT will provide a report to MPs of issues older than 6 months
  Closing Issues >12 months old
    Two weeks prior to product migration ERCOT will close issues greater than 12 months old and make available a report to MPs
Migration Weekend
  Disable Entry of New Issues in FasTrak
    At 4:00pm on Friday prior to implementation, ERCOT will disable entry of new issues in FasTrak
  In-progress Issues in FasTrak
    MPs will have the ability to work in-progress issues in FasTrak
MarkeTrak is Operational in Production
  Entry of New Issues
    ERCOT will start accepting new issues into MarkeTrak on Monday, August 28th
PR-50007 Enhancements to FasTrak
As of July 5, 2006
Page 6

## Slide 7
Project Cutover Plan Highlights - cont.
FasTrak Data
  FasTrak Availability
    ERCOT will keep the FasTrak tool on-line (view and update only) for 90 calendar days after MarkeTrak is implemented
  Shutdown of Access to FasTrak
    One month prior to shutdown of FasTrak ERCOT will provide MPs a report of remaining open issues
    One week prior to shutdown of FasTrak ERCOT will close remaining open issues and provide report to MPs
Request for FasTrak Data After Shutdown
  ERCOT will maintain FasTrak data for a period of no longer than 7 years
    MPs can request FasTrak data from ERCOT after MarkeTrak implementation
    Lead times for these types of requests will be 7-10 business days
PR-50007 Enhancements to FasTrak
As of July 5, 2006
Page 7

## Slide 8
  Questions?
PR-50007 Enhancements to FasTrak
As of July 5, 2006
Page 8