| PRR Number | 672 | PRR Title | Retail Market Timing Necessary for PUCT Project 29637 |
| --- | --- | --- | --- |
| Impact Analysis Date | 07/31/06 |
| Cost/Budgetary Impact | Phase 1 : $250K - $500K Phase 2: No capital cost is required to complete Phase 2 analysis. Phase 3: To be evaluated following collaborative analysis and stabilization of PR-50121_07 – Retail Business Processes. Assuming no resource constraint and implementation of PR-40038_01 TX SET 3.0 on 7/1/2007 prior to PRR672 Phase 3 initiation, potentially > $5M. |
| Estimated Project Time Requirements* *Unless otherwise indicated, project time requirements begin upon project initiation. | Phase 1 – Potential to manage as a scope increase to project PR-40038, TX. SET 3.0, with a projected implementation date of July 1, 2007. This assumes that PRR672 Phase 1 is approved by the ERCOT Board no later than August 15, 2006. Phase 2 – Estimated time to complete analysis is 90 days. Phase 3 – To be evaluated following collaborative analysis and stabilization of PR-50121_07 – Retail Business Processes. Assuming implementation of PR-40038_01 TX SET 3.0 on 7/1/2007 prior to PRR672 Phase 3 initiation, potentially, 12-16 months. |
| ERCOT Staffing Impacts (across all areas) | Phase 1 – Staff impact to the following groups: Retail Customer Choice – 1 FTE Commercial Operations – 2 FTE Phase 2 – No long term staff impact. Temporary staff impact to the following groups: Retail Customer Choice Commercial Operations Market Operations DPO Retail Market Analysis Phase 3 – Staff impact to be evaluated following collaborative analysis and stabilization of PR-50121_07 – Retail Business Processes. Phase 3 has the potential to temporarily impact existing ERCOT staff for development of the functionality proposed by this PRR in the following groups: Retail Customer Choice Commercial Operations Retail Client Services Commercial Services Enterprise Integration Market Operations Testing Market Operations DPO Commercial Ops Data Integrity & Admin Ongoing support for Phase 3 has potential staff impact, in addition to Phase 1 staff impact, to the following groups: Retail Customer Choice – 1 FTE Commercial Operations – 2 FTE |
| ERCOT Computer System Impacts | In order to reduce risk to the implementation date of PR-40038 TX SET 3.0 required, a phased approach is recommended with Phase 1 to include priority move-ins as part of TX SET 3.0; Phase 2 to include a collaborative analysis of end-to-end business processes to improve transaction processing; and Phase 3 to consider system changes identified in the collaborative analysis, following stabilization of PR-50121_07 – Retail Business Processes and implementation of PR-40038_01 TX SET 3.0. Phase 1 Details: Phase 1 scope includes prioritizing the processing of 814_16 Move-In Requests containing a priority code of anything other than NULL or 01. Phase 1 computer system impacts could involve prioritization, sorting, and processing of move-ins. Implementation of Phase 1 could impact the following system/process areas: Paperfree NAESB peripherals TIBCO ETS protocol calculation / reporting changes Siebel Monitoring of systems to support required volumes and timings Assumptions for Phase 1: Priority MVIs are designated in EDI transaction by a priority code other than 01 or NULL. Transaction volumes submitted during annual validation and "large" volume transactions are excluded from the timing changes. "Large" volumes defined as more than 10% over the average daily volume being sent in a 24 hour period. PRR672 Phase 1 is approved by the ERCOT Board no later than August 15, 2006. Risk for Phase 1: Processing Priority MVIs first will have the effect of lowering the priority and potentially increasing processing time of all other transactions. Impact on Resource Availability: Project work for PRR672 Phase 1 has the potential to impact resources on the following projects: PR-40038 – TX SET 3.0, including Mass Transition and Terms and Conditions PR-60015 – ESI ID Account Table Split PR-50088 – ETS Transition to EDW (Enterprise Data Warehouse) PR-50061 – EDW EAI (Enterprise Application Integration) Transition New Project - Systematic Exception Reprocessing Functionality New Project – Exception Reporting / Monitoring Enhancements Regular Retail Releases PR-60006_01 - ERCOT Outage Evaluation and Resolution (TDTWG)--Phases I and II Impact with Other Projects: Technical dependency on other projects: PR- 50121_07 Retail Business Processes project. Changes to the Retail Transactions applications in support of the TIBCO framework are currently in progress and not scheduled to be implemented until Q4 2006. PR-40070 Austin QA Build-out project complete prior to performance testing. Phase 2 Details: Phase 2 scope includes a collaborative analysis of end-to-end business processes for ERCOT, CRs and TDSPs to improve end-to-end transaction processing and the ultimate service to end use customers. The outcome of this analysis would determine system changes that could be made to improve transaction timings. Assumption for Phase 2: Market Participant resource availability to be involved in the end-to-end analysis. Impact on Resource Availability: Over the next 90 days, project work for PRR672 Phase 2 has the potential to impact resources on the following projects: PR-60015 – ESI ID Account Table Split PR-50088 – ETS Transition to EDW (Enterprise Data Warehouse) PR-50061 – EDW EAI (Enterprise Application Integration) Transition Phase 3 Details: Phase 3 scope will consider system changes identified in the Phase 2 collaborative analysis, following stabilization of PR-50121_07 – Retail Business Processes and implementation of PR-40038 – TX SET 3.0. There is the potential to manage this effort as a scope change to project PR-60008_01 Terms and Conditions requirements, not limited to Texas SET changes. Impact on Resource Availability: TBD depending on active projects at time of project initiation for PRR672 Phase 3. Impact with Other Projects: Technical dependency on other projects: PR- 50121_07 Retail Business Processes project. Changes to the Retail Transactions applications in support of the TIBCO framework are currently in progress and not scheduled to be implemented until Q4 2006. Scheduling dependency on other projects: PR-40038 – TX SET 3.0, including Mass Transition and Terms and Conditions For the purpose of this Impact Analysis, assumptions (see above) have been made regarding the business requirements of this PRR. These assumptions and other requirements are to be confirmed or corrected as part of the project planning process. Any modification of assumptions or requirements during the project planning process will be reflected in the estimates of project time, cost, etc. |
| ERCOT Business Function Impacts | Phase 1 – No new business functions will be required for this PRR. Modifications to current business functions in the following areas: Retail Customer Choice Commercial Operations Phase 2 – None. Phase 3 - Business Function impacts to be evaluated following collaborative analysis and stabilization of PR-50121_07 – Retail Business Processes. Phase 3 could result in modifications to current business functions in the following areas: Retail Customer Choice Commercial Operations Retail Market Analysis Commercial Ops Data Integrity & Admin |
| Grid Operations & Practices Impacts | None. |

Alternatives for a More Efficient Implementation (include explanation of impacts)

NA

Evaluation of Interim Solutions (e.g., manual workarounds)

NA

Feasibility of Implementation

Impact on Resource Availability – All Phases: PR-40038 – TX SET 3.0, including Mass Transition and Terms and Conditions PR-60015 – ESI ID Account Table Split PR-50088 – ETS Transition to EDW (Enterprise Data Warehouse) PR-50061 – EDW EAI (Enterprise Application Integration) Transition PR-50059 - EDW Siebel Transition PR-50060 - EDW TCH (Transaction Clearinghouse) Transition New Project - Systematic Exception Reprocessing Functionality New Project – Exception Reporting / Monitoring Enhancements New Project - EIS Siebel to L* Data Comparison New Project - MarkeTrak Enhancements Regular Retail Releases PR-60006_01 - ERCOT Outage Evaluation and Resolution (TDTWG)--Phases I and II Impact to Other Projects – All Phases: Technical dependency on other projects: PR- 50121_07 Retail Business Processes project. Changes to the Retail Transactions applications in support of the TIBCO framework are currently in progress and not scheduled to be implemented until Q4 2006. Risk is high that resolution for testing and stability issues related to RBP will impact design and development work on PRR672. Scheduling dependency on other projects: PR-40038 – TX SET 3.0, including Mass Transition and Terms and Conditions

Comments

A scope change to PR-40038 TX. SET 3.0, including Mass Transition and Terms and Conditions in order to include all timing changes identified in PRR672 would put high risk on PR-40038’s mandated date of July 1, 2007. Current scope of PR-40038 TX SET 3.0 involves a different set of requirements than that of PRR672, such as cross-system architectural changes to support volumes and timings. Therefore, the two sets of requirements are not easily integrated. Although there is overlap in the impacted system/process areas, there are no economies gained by combining the two sets of requirements into one project.