## Slide 1: Texas Nodal Market Implementation ERCOT Board of Directors Meeting Program status briefing July 18,2006 Ron Hinsley, Chief Information Officer rhinsley@ERCOT.com

## Slide 2: Progress this Month
Market Participant Engagement & Readiness Package
  Received TPTF approval of the last large NPRR aimed at addressing ERCOT's >700 protocol clarification questions and syncronizing Zonal PRRs passed since the TNT baseline
  Secured TPTF approval of Course Curriculum Descriptions and a Training Audience Matrix which together propose targets for MP personnel readiness criteria and allow our training group to proceed with scheduling and budgeting of MP Training
  Approved by TAC, Nodal Market Participant Accountable Executive role & Telemetry and State Estimator criteria
  Delivered to TPTF, the 1st iteration of the Market Participant Nodal Activities document
Integrated Testing Package
  Established core team
  Distributed test lab RFP for bid
Commercial Systems Package
  Submitted Day Ahead Energy requirements to TPTF for approval
  Completed Level 4 process diagrams
NMMS/Network Model Package
  Completed first set of Use Cases and Business Process Diagrams
  Completed data mapping between EMS/NMMS
EMS/OS Package
  Completed substantial portion of EMS requirements and Use Cases; target is TPTF requirement approval in August
  Moved ABB SOW for the Outage Scheduler into execution cycle
MMS/SCED Package
  Executed ABB SOW and PSA
  Started technical document exchange between ABB and ERCOT
  Completed first major technical review of in-process MMS requirements documentation
Program Control Package
  Approval received of the Nodal Control and Quality Assurance policy and procedures
  Implemented control processes to track and report costs; these will be used in the September 1st program collection
CRR Package
  Executed Nexant SOW for system development
  Received initial deposit of Nexant deliverables
IDA Package
  Completed RUP training for the Nodal team; completed 1st class for TPTF on Use Case development
  Completed EDW Roadmap
Infrastructure Package
  Hired senior project manager
  First development environment installed
ERCOT Readiness & Transition Package
  ERCOT readiness team expanded to include all ERCOT directors
  Secured third party readiness advisor to track and report ERCOT readiness activities similar to approach used by MISO

## Slide 3
Overall Status
Overall program status is red, based on feasibility of 1/1/09 delivery
Program plan to be baselined 9/19/06
The size, complexity and risk of the program is not yet contained:
  The common network model, CRR and DAM are subject to significant uncertainty
  Expectations for extensive fork-lifting must be tempered by the fact of unique Texas Nodal Protocols
  Budgetary implications are not firm
Resolution of issues top Nodal priority
Scenario analyses will form options for substantial de-risking of custom Texas Nodal software and integration
Staffing issues remain:
  Resources for business requirements are the priority; toughest challenge is securing/growing “Texas Nodal” experts
  Key leadership areas vacant – EDW, Integration, Infrastructure, MIS and MP Readiness
A comprehensive staffing model is now being deployed, utilizing ERCOT staff, short-term staff augmentation, contractors and consultants
Business requirements are the short-term critical path challenge:
  Scale of effort required to achieve necessary quality and approval is not yet understood
  Mobilization and productivity levels behind expectations
  - Contracting took longer than planned
  - Vendors requiring more time to assemble their experts
  NPRRs will be impacted through the Nodal Change Control post 9/13/06 baseline
The combined NODAL team is driving to complete business requirements by October 30
The means to accelerate the production of a coherent Nodal work product is dependant upon Key MP protocol experts being dedicated to the Nodal Program

## Slide 4
Spending year to date
O&M (,000)
  Internal labor $ 2,051
  Equipment, tools, supplies 21
  Outside services 1,189
  Facilities and Utilities 131
  Employee expenses 21
  Interest and fees 37
  Other 4
  Total O&M: $3,454
Capital
  Total Capital $ 900
Total spending through June $4,354
Note: Total spending through May $2,953K

## Slide 5: Preliminary* Key Dates
6/7/06 Preferred vendors selected
7/5/06 Start joint requirements, use cases, test cases was 6/30/06
7/6/06 EDW Roadmap complete
7/10/06 Market Participant readiness activities list
7/30/06 MIS & Integration Roadmap complete
8/4/06 Integration vendor selected
        Scenario Development and Choices by 9/1
9/19/06 ERCOT Board of Directors meeting (commitment: date and dollars)
10/30/06 Requirements complete and approved *requires TPTF approval
3/31/07 Market Participant interface specs complete
4/1/07 EMS FAT begins
1/1/08 Market Participant SCED offers begin (EDS3)
7/1/08 Market systems, Market Participant offers (EDS4)
*Preliminary dates; pre-baselined program plan