|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Technical Advisory Committee Reliability and Operations Subcommittee for July 2006 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  | Section |
| 1. | Interconnection Requests Increase by 2,288 MW in July: Three new generation interconnection requests were received by ERCOT for screening studies in July. The total capacity in all active generation interconnection requests is 38,495 MW. |  |  |  |  |  |  | 1.0 |
| 2. | New Wind Generation in Operation: Horse Hollow 3 and Horse Hollow 4 (223.5 MW and 116 MW respectively) wind farm in Nolan County went into commercial operation in July. |  |  |  |  |  |  | 1.0 |
| 3. | Valley SES 1, 2 and 3 Not Needed for RMR: ERCOT System Planning and System Operations have determined that Valley SES 1, 2 and 3 are not required to be available to maintain transmission security on the ERCOT System and will not be pursuing Reliability Must Run (RMR) contracts for these units. |  |  |  |  |  |  | 2.0 |
| 4. | AEPTCC/ME Western Region Project Approved: TAC and the ERCOT Board approved in July a series of reliability improvement projects in the AEPTCC/MEC Western Region (Uvalde-Del Rio-Pearsall area) totaling approximately $ 160 million. |  |  |  |  |  |  | 3.0 |
| 5. | West Texas Dynamic Limit Study Underway: A study of dynamic limits for power transfer out of West Texas is underway. Base cases with dynamic models for wind farms including updated voltage and frequency protection data have been prepared for varying scenarios. |  |  |  |  |  |  | 4.0 |

1.0	Status of Active Generation Interconnection Requests

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” data folder posted in the “Operations and System Planning” data area on the ERCOT website.

1.1	New Generation Beginning Commercial Operations.

Horse Hollow 3 and Horse Hollow 4 (223.5 MW and 116 MW respectively, wind farms located in Nolan County) went into commercial operation in July 2006.

1.2	Active Generation Interconnection Requests.

The table below summarizes the active generation interconnection requests currently being processed by ERCOT System Planning.  The current 99 projects, reflecting 38,495 MW of capacity, are an increase of 2,288 MW of capacity over the June total of 36,207 MW.

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Currently tracking 99 active generation interconnection or change requests |  |  |  |  |  |
|  |  | North | South | West | Total |
| Security Screening Study |  | 1 | 3 | 3 | 7 |
| SSS Completed |  | 6 | 4 | 12 | 22 |
| Full Interconnect Study |  | 15 | 5 | 31 | 51 |
| FIS Completed |  | 1 | 1 | 3 | 5 |
| Interconnect Agreement Completed |  | 2 | 3 | 9 | 14 |
| Capacity for Grid, MW |  | 15,093 | 10,977 | 12,425 | 38,495 |
| Wind MW (under development) |  | 480 | 3,677 | 10,813 | 14,970 |

The table below summarizes the primary fuel-type of the active generation interconnection requests currently being processed by ERCOT System Planning.

| INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED BY FUEL TYPE |  |  |  |  |
| --- | --- | --- | --- | --- |
| Fuel-Type | Public Projects | Confidential (Non-public) | Total Capacity Under Review (MW) | % |
| Natural gas | 2,300 | 3,740 | 6,040 | 16% |
| Coal | 11,709 | 4,652 | 16,361 | 43% |
| Wind | 2,779 | 12,191 | 14,970 | 38% |
| Other | 12 | 1,112 | 1,124 | 3% |
| Totals | 16,680 | 21,815 | 38,495 | 100% |

1.3	Potential Future Generation Interconnections.

The table below summarizes the publicly-known potential future generation projects for the ERCOT region.

| FUTURE GENERATION INTERCONNECTIONS (PUBLIC PROJECTS) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR # | Site Name | Status | County | Region | Fuel | In Service Date | MW into Grid | Change from Last Report |
| 06INR0008 | Big Spring Electricity Gen Fac 1 | Interconnect Agreement | Howard | West | Waste heat | Aug-06 | 12 | Commercial Date Delayed |
| 06INR0016 | Dow 9 | Interconnect Agreement | Brazoria | South | Gas | Oct-06 | 0 |  |
| 05INR0018 | Horse Hollow 2 | Interconnect Agreement | Nolan | West | Wind | Oct-06 | 186 |  |
| 04INR0020 | WKN Wind 1 Snyder | Interconnect Agreement | Scurry | West | Wind | Dec-06 | 60 |  |
| 05INR0011 | Forest Creek | Interconnect Agreement | Sterling | West | Wind | Dec-06 | 215 |  |
| 04INR0011 | Mesquite Wind 1 | Interconnect Agreement | Shackelford | West | Wind | Dec-06 | 200 |  |
| 03INR0034 | Silver Star | Interconnect Agreement | Erath | West | Wind | Mar-07 | 60 |  |
| 04INR0015 | Cirello 1 | Interconnect Agreement | Taylor | West | Wind | Mar-07 | 233 |  |
| 06INR0035 | Colorado Bend Energy Center 1 | Interconnect Agreement | Wharton | South | Gas | Apr-07 | 275 |  |
| 06INR0036 | Quail Run Energy Center 1 | Interconnect Agreement | Ector | West | Gas | Apr-07 | 275 |  |
| 06INR0038 | Scurry County Wind 1 | Interconnect Agreement | Scurry | West | Wind | May-07 | 130 | Name Change |
| 05INR0015 | Gulf Wind 1 | Public Letter | Kenedy | South | Wind | Sep-07 | 300 |  |
| 06INR0021 | Barton Chapel Wind 1 | Interconnect Agreement | Jack | North | Wind | Oct-07 | 120 | New |
| 04INR0011 | Mesquite Wind 2 | Interconnect Agreement | Shackelford | West | Wind | Dec-07 | 200 |  |
| 05INR0015 | Gulf Wind 2 | Public Letter | Kenedy | South | Wind | Sep-08 | 300 |  |
| 09INR0006 | Oak Grove 1 | Public Letter | Robertson | North | Coal | Mar-09 | 790 |  |
| 09INR0008 | Big Brown 3 | Public Letter | Freestone | North | Coal | Apr-09 | 858 |  |
| 09INR0010 | Martin Lake 4 | Public Letter | Rusk | North | Coal | Apr-09 | 858 |  |
| 09INR0011 | Monticell0 4 | Public Letter | Titus | North | Coal | Apr-09 | 858 |  |
| 09INR0013 | Tradinghouse 3 | Public Letter | McLennan | North | Coal | Apr-09 | 858 |  |
| 09INR0014 | Valley 4 | Public Letter | Fannin | North | Coal | Apr-09 | 858 |  |
| 06INR0006 | Greenville | Public Letter | Hunt | North | Gas | May-09 | 1,750 | Name Change |
| 01INR0028 | Orion Delaware Mt. Wind Farm | Interconnect Agreement | Culberson | West | Wind | Jul-09 | 175 |  |
| FUTURE GENERATION INTERCONNECTIONS (PUBLIC PROJECTS) … Continued |  |  |  |  |  |  |  |  |
| INR # | Site Name | Status | County | Region | Fuel | In Service Date | MW into Grid | Change from Last Report |
| 08INR0003 | Sandow 5 | Public Letter | Milam | North | Lignite | Jul-09 | 585 |  |
| 05INR0015 | Gulf Wind 3 | Public Letter | Kenedy | South | Wind | Sep-09 | 300 |  |
| 09INR0009 | Lake Creek 3 | Public Letter | McLennan | North | Coal | Oct-09 | 858 |  |
| 09INR0012 | Morgan Creek 7 | Public Letter | Mitchell | West | Coal | Oct-09 | 858 |  |
| 09INR0006 | Oak Grove 2 | Public Letter | Robertson | North | Coal | Mar-10 | 790 |  |
| 09INR0013 | Tradinghouse 4 | Public Letter | McLennan | North | Coal | Apr-10 | 858 |  |
| 09INR0002 | J K Spruce 2 | Commitment Letter | Bexar | South | Coal | Jun-10 | 750 |  |
| 09INR0001 | Sandy Creek 1 | Public Letter | McLennan | North | Coal | Jun-10 | 800 |  |
| 05INR0015 | Gulf Wind 4 | Public Letter | Kenedy | South | Wind | Sep-10 | 300 |  |
| 10INR0002 | Hugo Plant | Public Letter | Choctaw, OK | North | Coal | Feb-11 | 500 |  |
| 11INR0001 | Twin Oaks 3 | Public Letter | Robertson | North | Coal | Jun-11 | 630 |  |
|  |  |  |  |  |  | Totals: | 16,800 |  |

2.0	Status of RMR Contracts

The table below summaries generating units currently under RMR Contract as of July 31, 2006.

| Unit | Generation Capacity (MW, Net) | RMR Contract Status | Contract Date | Current Anticipated Exit Date | Change Since Last Report |
| --- | --- | --- | --- | --- | --- |
| Laredo 1, 2, & 3 | 172 | Under Contract | 1/1/06-12/31/06 | 3Q 2010 under review | N/A |
| Atkins 3, 4, 5, 6 | 97 | Under Contract | 6/1/06-10/31/06 | 10/31/06 | RMR Exit Strategy Developed |
| Total MW Under RMR Contract as of July 31, 2006 | 269 |  |  |  |  |

Valley SES 1, 2 and 3 Notice of Suspension of Operations, dated July 5, 2006

ERCOT System Planning and System Operations have determined that Valley SES 1, 2 and 3 are not required to be available to maintain transmission security on the ERCOT System.   ERCOT will not be pursuing Reliability Must Run (RMR) contracts for these units.  This will serve as the initial and final determination for these units.

3.0	Regional Planning Activities

The following summarizes numerous significant activities associated with regional planning issues.

3.1	Long-term System Study (SB20).

  - The wind profiles to be used for the Competitive Renewable Energy Zone (CREZ) data development part of this study have been finalized and are posted.

  - The studies to develop the proxy thermal generation to be used in each scenario of this study have been completed and were presented to the RPGs at the July meeting.

  - ERCOT has worked with west Texas transmission owners to develop a set of potential transmission upgrades to be studied in association with different combinations of CREZs and levels of development within each CREZ.

  - Five-year Study (Pre-Nodal Study Follow-up).

  - Several needed reliability-driven projects, in addition to the small, non RPG-reviewable projects already included in the SSWG cases, have been identified for 2007-2009 through ERCOT analysis and consultation with the TOs.  These projects were presented to the RPGs at the July meeting.

  - Studies to identify and evaluate economic projects for 2007-2009 have begun, including mitigation of constraints associated with the wind scenario.

  - Entergy Study (PUCT Project 32217:  Entergy Gulf Coast Inc.’s Plan for Identifying Applicable Power Region Pursuant to PURA 39.452(F)).

  - Studies of alternatives to the projects presented at the March PUCT workshop have begun.

  - Entergy and ERCOT will be working with Powertech Labs to perform dynamic studies of the potential interconnection.

  - Southwest Power Pool (SPP) Studies.

  - Initial studies simulating transactions between regions have been performed.  SPP is reviewing.

  - Regional Planning Group Project Reviews.

  - Clemville project (STEC) is in an additional Study Mode period and STEC has responded to comments.

  - Venus-Sherry project did not receive any comments and is now under ERCOT Independent Review.

  - AEPTCC/Medina Electric Cooperative (MEC) projects for the Uvalde area were approved by the ERCOT Board in July.  The recommended projects will increase the reliability of the transmission system in the Uvalde-Del Rio-Pearsall area (Western Region).  The project includes the rebuild of the Hamilton Road-Uvalde 138kV line ($35.6M); the reconductor of the Del Rio138kV loop ($8.9M); a new CSPE Lytle to AEPTCC Lytle 138kV line with a 138/69kV autotransformer and the rebuild of the Lytle-Big Foot 69kV ($15.9M); a new Escondido-West Batesville 138kV line ($34.3M); a new Castroville-Uvalde 138kV line ($54.1M); and a new Palo Duro-Dilley 138kV line ($9.7M).  This area includes transmission operators South Texas Electric Cooperative (STEC) and City Public Service Energy (CPSE) in addition to AEPTCC and MEC.

  - Odessa 345/138kV Autotransformer project is currently in the RPG comment period.  This is a <$1 million project to move a larger auto that is being replaced at Valley to Odessa.

  - TNP/CNP 345kV Tie Project is currently in the RPG comment period.  This is a $22.1 million set of projects to provide support for TNP’s system south of Houston.

  - ERCOT’s Independent Review of the Centerpoint Dynamic Reactive Project was presented to the combined Regional Planning Group in a meeting on July 21, 2006 and will be presented to TAC and the BOD in August.

4.0	Transmission Services Activities

The following summarizes numerous significant activities associated with the Transmission Services group.

4.1 	Dynamic Analysis and Modeling.

- Reviewing responses to survey of “as-built” voltage and frequency protection data from wind generation farms.  Responses received from 12 out of 15 wind farm sites.  The responses from 4 of these sites require additional clarification.  A summary of response deficiencies was reported to Client Services on 7/5/06.

- A study of dynamic limits for power transfer out of West Texas is underway.  Base cases with dynamic models for wind farms including updated voltage and frequency protection data have been prepared for three transfer scenarios.  Preliminary runs has been done using a new run engine, internally developed by Staff, to automate multiple PSSe dynamics runs sequentially and plotting selected dynamic variables response to file.

- Supporting dynamic studies associated with the proposed integration of Entergy into ERCOT.  Participating in conference calls and meetings to define study scope and data requirements.

- Supporting ongoing Regional Planning efforts to develop a wind ancillary service when related to dynamics studies.

- Supporting ongoing DWG efforts to develop a transient voltage recovery criteria, update the DWG procedure manual and draft requirements for field testing of NERC generator performance standards (PRC-019,PRC-024,MOD-026,MOD-027).

- Annual Voltage Stability screening study for ERCOT system complete – initial report submitted to management 7/5/06.  Transient event screening study pending.

4.2	Case Building.

- Completed and posted SSWG 2007 Data Set Base Cases.

- Began work on the SPWG Future Year Short Circuit Database building.

4.3	Network Model Management System (NMMS) Support.

- Continued efforts to maintain consistency between planning and operations models

- Attend meeting with CRR team, Nexant, and operations to review technical needs for model needs of CRR auction engine.

- Attend meeting the Nodal team and TXU ED to discuss development of NMMS

4.4	Load Forecasting.

- Finished a first-pass on the development of the Residential and the aggregate of Business Non-IDR & No-Demand profile types forecast.

- Attended a software training class on MatLab.

- Renegotiated contract to obtain economic and demographic data.

- Produced load duration curves depicting the generation sources utilized to meet demand.

- Compared the load forecast with the actual record system peak set on July 17, 2006 and determined that the weather for that day was above the “normal” or average temperatures used in producing the official forecast that is included in the CDR.

- Provided input on load sensitivity for the 2006 NERC Summer Assessment.

- Developing a methodology to create a more efficient process to retrieve final cuts for settlement load data, including additional capabilities for retrieving generation data.

4.5	Congested Management Working Group Support

    - 2007 CSC analysis was conducted and the results sent to Congestion Management WG for final determination

4.6  	Studies underway or planned within System Planning Division

- Verifying TIPIT updates for 3rd quarter

4.7	Other.

- Began work on the 2007 transmission losses calculation with SSWG.

- Provided support to ERCOT Settlements for the identification of Congestion Management (CM) zones for new stations.

5.0	Upcoming Events/Deadlines

August

- Steady State WG quarterly TPIT base case updates are due August 1

- RPG Meeting on August 28 at ERCOT’s Austin office.

- August TPIT to be completed by August 31st.

- System Planning Map Orders should be received by ERCOT by August 31.

September

- Steady State WG 2007 Data Set B case creation to begin

- Sept 15 RAW data due to ERCOT for SSWG 2007 data set B

- Sept 13-14 NERC OC/PC meeting

- Sept 18-19 NERC TS meeting

- Sept 25 RPG Meeting

October

- Report on Existing and Potential Electric System Constraints and Needs to be published October 1 by ERCOT staff.

- Oct 30- Nov 1 SSWG DSB meeting at TCC 1

- TAC ROS Dynamics Working Group (DWG) meeting; October 3-4

- October 23 RPG Meeting