## Slide 1
Objective:
Achieve improved Market performance and reliability through a reduction of ERCOT Retail Systems unplanned outages
Scope/Why is this important?
Implement High Availability (HA) solutions for the NAESB application and Paperfree file server to target 99.99% availability for these systems in order to meet the 99.25% availability target for all retail systems.
Dependencies:
QA Build-out project
Project Objective / Scope / Dependencies
PR-60006_01 ERCOT Outage Evaluation
& Resolution Phases I & II
August 9, 2006
Page 1

## Slide 2
Phase:
Initiation – January 23, 2006
Planning – February 13, 2006
  NAESB RFP Posted – April 17, 2006
  Veritas Cluster Server RFP Posted – May 15, 2006
  NAESB Vendor Selected – May 26, 2006
  Veritas Cluster Server Vendor Selected – June 2, 2006
Execution – June 23, 2006
ITEST – August 29, 2006
Implementation/Go Live –
  October 1, 2006 - Paperfree production migration
  October 8, 2006 - NAESB production migration
Closing – December 14, 2006
Summary of Project Status
PR-60006_01 ERCOT Outage Evaluation
& Resolution Phases I & II
August 9, 2006
Page 2

## Slide 3
Recent:
NAESB contract signed July 27th
Paperfree contract finalized week of July 31st
Hardware installed in Development environment
NAESB Technical Architecture document prepared
Next steps:
Procure NAESB & Paperfree software
Application installation in Development environment week of August 14, 2006
NAESB Detailed Design document preparation
Summary of Project Status
PR-60006_01 ERCOT Outage Evaluation
& Resolution Phases I & II
August 9, 2006
Page 3

## Slide 4
Bus. Lead: Denise E. Taylor
phone number: 512-248-3932
e-mail: dtaylor@ercot.com
PM: Julie Thomas
phone number: 512-248-6552
email: jthomas@ercot.com
PPL: Source: Market Priority: 1.1 Rank: 8 Program Area: RO
What prompted the project:
SCR 745 Retail Outage Evaluation & Resolution
Phase I - NAESB/Proxy Clustered Environment
Phase II -Paperfree Clustered Environment
Supporting business driver:
  Providing solutions to reduce or virtually eliminate single points of failure would address a significant portion of the numbers and duration of unplanned outages
Additional Information
PR-60006_01 ERCOT Outage Evaluation
& Resolution Phases I & II
August 9, 2006
Page 4