## Slide 1: Texas SET Version 3.0 Project PR40038_01
Retail Market Subcommittee Meeting
August 9, 2006

## Slide 2: Accomplishments
POLR Rule – Project 31416
  Assignment of ESI ID process has been identified and documented by ERCOT. Plans are to incorporate this process into the Mass Transition (long-term) Retail Market Guide Revision.
  Process to identify a new class code for Small and Medium Non-Residential POLR Customer Class where at the time of a Mass Transition to POLR service having a peak demand in the previous 12-month period of less than or greater than 50 kW are communicated to the new POLR. This new POLR Customer Class segment will be included in the 814_14 TX SET Transaction allowing ERCOT to automate the process. In addition to the 814_14 transaction, ERCOT will post quarterly reports to their TML for the REP of Record to download providing them with the number of ESI IDs per POLR Class code.

## Slide 3: Accomplishments
POLR Rule – Project 31416
  TX SET reviewed Approved PRR 660 – We identified correction was required to comply with approved rule. The correction is to replace Retail Business Day reference with Calendar Day- new language is:
    In a Mass Transition event, ERCOT shall submit the 814_03 transaction requesting an off cycle meter read for the associated ESI IDs, for a date two (2) Calendar Days after the calendar date ERCOT initiates such transactions to the TDSP. The 814_03 shall contain a request for historical usage and the requested calendar date for the meter read date to transfer the ESI IDs. If an ESI ID does not have the capability to be read in a fashion other than a physical meter read, then the off cycle meter read may be estimated by the TDSP.

## Slide 4: Accomplishments
Terms and Conditions (Project 29637)
  Approved Change Control 2006-691, which included changes to the following (7) TX SET Implementation Guides:
    650_01, 650_02, 650_04
    810_02
    814_PC
    820_02
    867_03

## Slide 5: Accomplishments
Mass Transition Project
  Approved Change Control 2006-692, which included changes to the following (15) TX SET Implementation Guides:
    650_02
    814_02, 814_03, 814_04, 814_08, 814_09, 814_11, 814_13, 814_14, 814_15, 814_17, 814_19, 814_25, 814 27, 814_28

## Slide 6: Accomplishments
Approved the following individual (10) Change Controls will provide additional functionality and/or adding transaction/process clarification where needed:
  2004-674 – Transaction affected 867_02
  2004-678 – Transaction affected 814_22
  2005-687 – Transaction affected 814_19
  2006-693 – Transaction affected 814_20
  2006-694 – Transactions affected: 814_01, 814_04, 814_08, 814_10, 814_12, 814_16, 814_18, 814_20, 814_24, 814_25, 814_26, 814_28
  2006-695 – Transaction affected 814_05
  2006-696 – Transaction affected 814_20
  2006-697 – Transaction affected 867_04
  2006-698 – Transactions affected: 650_01, 650_02
  2006-699 – Transaction affected: 810_03

## Slide 7: Summary
12 Change Controls Approved by conference call deadline date of July 28, 2006
47 unique changes impacting transaction functionality to support PUCT Rule changes, business requirements, and/or providing Market with transaction/process clarification
34 unique transactions are impacted:
  650_01, 650_02, 650_04, 810_02, 810_03, 814_01, 814_02, 814_03, 814_04, 814_05, 814_08, 814_09, 814_10, 814_11, 814_12, 814_13, 814_14, 814_15, 814_16, 814_17, 814_18, 814_19, 814_20, 814_22, 814_24, 814_25, 814_26, 814_27, 814_28, 814_PC, 820_02, 867_02, 867_03, 867_04

## Slide 8: Open Action Items
Finalize version 3.0 Requirements Documentation prior to 8/21/2006
  Market Coordination Team Kick-off Meeting scheduled Thursday, 8/10/2006 tasked with finalizing all the market requirements
  Customer Billing Information communications: methodology, data, and periodic testing requirements. TX SET Sub-team tasked with developing and finalizing requirements on Thursday, 8/10/2006
Update and Finalize Mass Transition Long Term Retail Market Guide Revision
Update and Finalize Protocol Revisions to support v3.0 modifications
Hand-off all version 3.0 documents from TX SET to the Market Coordination Team Leader

## Slide 9: Open Action Items Timeline
August 8 –
  ERCOT will draft redline versions of Implementation Guides to be emailed to SET members for verification of updates
August 10 –
  Develop and finalize Customer Billing Information Requirements
  Finalize all version 3.0 Requirements
  Hand off TX SET v3.0 documentation to Market Coordination Team Lead to manage document updates/revisions where and if needed
August 18 –
  TX SET members will complete their verification of Implementation Guide Redlines and return to ERCOT for final TX SET discussion/signoff on August 22-24
  Submit Protocol changes to PRR 660 to PRS on a normal schedule
August 22-24 –
  TX SET Meeting final reviews of redline Implementation Guides
  Review and Update Protocols Sections 15, 19, and 24 to comply with changes approved via PUCT Rule and/or TX SET Change Controls
  Finalize Mass Transition Long Term Solution for Retail Market Guide Revision
September 1 –
  Publish TX SET Version 3.0 Implementation Guides to website
September 13 – RMS Open Meeting
  Protocol Revisions (PRR) submitted for approval
  Retail Market Guide Revision (RMGRR) submitted for approval

## Slide 10: PR40038_01 Timelines
RBP PR50121_ 07
PR40038_01Tx SET 3.0 including Mass Transition and Ts & Cs (7/1/2007)
Jun 06
Jul 06
Aug 06
Sep 06
Oct 06
Nov 06
Dec 06
Jan 07
Feb 07
Mar 07
Apr 07
May 07
10/22Prod
7/15
5/1
Build
12/11
UAT
Stabilization
9/11
7/17
Business Req’mts
9/25
12/4
3/12
5/28
Conceptual Design
Detail Design
Build
UAT
7/1 Prod
Market Flight Testing
Market Requirements
7/3
Flight Testing
4/16 – connectivity
4/27 – Day 1
5/29 – Flight ends
Draft 3.0 TX SET Guides
9/1 – Due Date
8/21

## Slide 11: Open Issue for RMS Discussion
POLR Rule- Project 31415 (n) Transition of customers to POLR service.
  (10) Information from the TDU and ERCOT to the POLRs shall be provided in Texas SET format. However, the TDU or ERCOT may supplement the information to the POLRs in other formats and fashions to expedite the transition to the POLRs. Such supplemental formats shall only be used in exceptional circumstances and at the option of the entity supplying the information. The transfer of information in accordance with this section will not constitute a violation of the customer protection rules that address confidentiality.
  During the POLR Data Requirements for Mass Transition Conference Call held on May 30, 2006 the following documents were developed by market participants on the call.

## Slide 12: Reminder Meeting Schedule
Thursday, August 10, 2006 –
  8:00 AM – 12:00 PM -
    Customer Billing Information Requirements Discussion Leader: Kyle Patrick
  1:00 PM – 5:00 PM -
    Market Coordination Team Kick-Off Meeting – Review/Sign-off of Version 3.0 Requirements – Leader: Susan Munson
Tuesday, August 22, 2006 -
  Market Coordination Team Meeting
Wednesday/Thursday, August 23-24
  TX SET Meetings

## Slide 13: Questions/Discussion