## Slide 1: Flight Update 08/09/2006

## Slide 2: Flight 0706
Details
Flight kick-off conference call – 07/07/06
Flight began – 07/10/06
Flight 0706 scheduled to conclude 08/22/06
  Contingency testing scheduled to conclude 09/12/06

## Slide 3: Flight 0706
Flight Manifest
6 TDSPs
0 New REPs – 0 New Relationships
0 New Umbrella DUNs
3 Existing REPs testing in new territory – 4 New Relationships
1 Existing REP testing new functionality
3 Existing REPs and 1 TDSP changing Service Providers
3 Existing REPs changing Banks
3249 Total Tasks (plus 428 Total MarkeTrak Tasks = 3677)

## Slide 4: Flight 0706
Progress
Connectivity complete
Flight started on time
As of 08/08/06 at 9:00 PM
  Day 22
    62.32% complete
    80.32% by end of day

## Slide 5: Flight 0706
Progress (continued)
5 outstanding transactions for Week 1
  0 Inbound to ERCOT
  0 Outbound from ERCOT
  5 Point-to-Point
17 outstanding transactions for Week 2
  2 Inbound to ERCOT
  3 Outbound from ERCOT
  12 Point-to-Point

## Slide 6: Flight 0706
Progress (continued)
42 outstanding transactions for Week 3
  10 Inbound to ERCOT
  14 Outbound from ERCOT
  18 Point-to-Point
63 outstanding transactions for Week 4
  17 Inbound to ERCOT
  7 Outbound from ERCOT
  39 Point-to-Point

## Slide 7: Flight 0706
Progress (continued)
547 outstanding transactions for Week 5
  406 Inbound to ERCOT
  121 Outbound from ERCOT
  20 Point-to-Point

## Slide 8: MarkeTrak Testing
Reminder
MarkeTrak Testing API/GUI: 08/07/06 – 08/18/06
Testing Participants
  API required testers (adding business functionality) - 5
  GUI volunteer testers – 4
  API and GUI combined testing participants – 3
Each testing participant has been paired between a CR and TDSP
Notification will be made to testing participants when MarkeTrak scripts are completed to allow for internal ‘sandbox’ training/testing

## Slide 9: MarkeTrak Testing
MarkeTrak Testing
4 scripts created for API testing
17 scripts created for GUI testing
1 ERCOT/CR Connectivity script (CON57) to be used for either API and/or GUI
1 ERCOT/TDSP Connectivity script (CON58) to be used for either API and/or GUI
428 Total Tasks for both API & GUI

## Slide 10: MarkeTrak Testing
Progress
CRs sent to ERCOT
  Day 21 – 17/108
  Day 22 – 2/25
  Day 23 – 4/48
ERCOT sent to MP
  Day 21 – 6/45
  Day 22 – 0/68
  Day 23 – 0/16
TDSPs sent to ERCOT
  Day 21 – 3/50
  Day 22 – 4/66
  Day 23 – 2/19

## Slide 11: MarkeTrak Testing Update
Known issues at this time
MarkeTrak testing started one day late (08/08/06)
All scripts (API & GUI) were able to begin testing except for MTGUI02 (Bulk Insert)
  Update to be provided to testing participants when this script is available to be tested
ERCOT aware of one script (MTGUI17 – DEV Characteristic) which needs to be modified

## Slide 12
Thank you!