## Slide 1: CO – CART Project Status
Protocol Revision Subcommittee Update 08/17/2006

## Slide 2: CO Projects
Document Management
Lawson - Time Tracking
Physical Security Project #1
CyberSecurity Project #1
CyberSecurity Project #2
Collateral Calculation
CyberSecurity Project #3
CyberSecurity Project #4
CyberSecurity Project #5
CyberSecurity Project #6
CyberSecurity Project #7
Vendor and Contract Management
Lawson - Process Flow
Lawson 8.1 Upgrade
Single Time Entry
Completed or near completion
New or Not Started
Active (at least in Initiation)

## Slide 3: Completed or Near Completion
Document Management $500k - $1M Implement a Document Management solution, beginning with Legal Department Scalable across the enterprise Went live in July
Lawson - Time Tracking $100k - $500k Implemented time tracking for all employees in Lawson. Completed January
Physical Security Project #1 $100k - $500k
CyberSecurity Project #1 $500k - $1M

## Slide 4: Active (at least in Initiation)
CyberSecurity Project #2 $ 100k - $500k
Collateral Calculation $100k - $500k Develop an automated credit monitoring and collateral calculation tool with reporting capability Currently in Execution – projected completion is September
CyberSecurity Project #3 $500k - $1M
CyberSecurity Project #4 $100k - $500k
CyberSecurity Project #5 $100k - $500k
CyberSecurity Project #6 $500k - $1M

## Slide 5: Active (at least in Initiation)
CyberSecurity Project #7 $100k - 500k
Vendor and Contract Management $100k - $500k Provide a database that will track and report vendors, contracts, and on-site consultants, to facilitate the enforcement of policies, procedures and financial information Currently in Execution – projected completion is September
Lawson - Process Flow $100k - $500k Enforce compliance and streamline several key business processes at ERCOT in the areas of Procurement, Finance, and HR Currently in Execution – projected completion is October
Lawson 8.1 Upgrade $100k - $500k Upgrade current Lawson application suite to 9.x Currently in Initiation
Single Time Entry < $100k Implement functionality in Lawson to enter project actual time Currently in Initiation

## Slide 6: New or Not Started
None.

## Slide 7: Integration & Resource Constraints
Currently projected to need additional funds for 2006