## Slide 1: Real-time Co-optimization WMS Update
Brandon Whittle
Lead, Real-time Market Operations
ERCOT

## Slide 2: Commission Order
Docket No. 31540
Final Order 5 April, 2006 Ordering Paragraph 3
  ERCOT and the electric-market stakeholders shall determine whether co-optimization is feasible and beneficial to implement in the wholesale market as approved by this Order. Any modifications to the protocols required to implement co-optimization shall be brought to the Commission for final approval.

## Slide 3: WMS Involvement
May WMS
  ERCOT was asked to question potential vendors about costs and schedule impacts for
    Real-time co-optimization
    Hour-ahead co-optimization
June WMS
  ERCOT response
    No specific cost or schedule impacts available
    Both Real-time and Hour-ahead possible
    Impacts to protocols and systems expected
July WMS
  Vendor selected, estimates will follow
See WMS minutes for details

## Slide 4: Current Status
ERCOT asked MMS vendor to determine cost and schedule impacts of implementing each of the two co-optimization options, neither of which have requirements defined.
Real Time Co-optimization (Hour Ahead)*
  MMS System Cost & Schedule Impact
    Minimum $950,000 + $250,000 risk**
    Minimum 2 months MMS project delay
    Potential 2 month impact on Texas Nodal, cost not quantified
  Must also consider:
    Settlement Impact Certain (cost not quantified, analysis in progress)
    Operational Staffing Impact
    Market Rules Changes – Proposed NPRR XXX
RT Co-optimization (Every SCED run)
  MMS System Cost & Schedule Impact
    Minimum $950,000
    Minimum 2 months MMS project delay
    Potential 2 month impact on Texas Nodal, cost not quantified
  Must also consider:
    Settlement Impact Certain (cost not quantified, must have additional information such as NPRR)
    EMS Impact Certain (cost not quantified, must have additional information such as NPRR)
    Operational mechanics between QSE and ERCOT
    Overlap of AS Deployment and Re-Allocation
    Market Rules Changes
* Also referred to as “Sequential Optimization” in Potomac Memo to PUCT
**Risk uncertainty due to new software development and the addition of a sequence

## Slide 5
Additional Questions?