| PRR Number | 676 | PRR Title | RPRS Solution with Nodal RUC-Type Procurement and Cost Allocation |
| --- | --- | --- | --- |
| Impact Analysis Date |  | 09/06/06 |  |
| Cost/Budgetary Impact |  | Option 1 (successive implementation): - PRR666, Modification of RPRS Under-Scheduled Capacity Charge Calculation and PRR687, Replacement Reserve Under-Scheduled Capacity Delineation, implementation budgeted at a cost of $300k. - PRR676 implementation cost estimated at $250k - $500k. Successive implementation of these PRRs would, therefore, result in a total estimated cost of $550 - $800K. Option 2 (simultaneous implementation): - PRR666 and PRR687 implementation is budgeted at a cost of $300k. - PRR676 estimated incremental cost is $100k - $250k. Simultaneous implementation of these PRRs would, therefore, result in a total estimated cost of $400K - $550K. |  |
| Estimated Project Time Requirements* *Unless otherwise indicated, project time requirements begin upon project initiation. |  | Option 1 (successive implementation): - The consolidated project for PRR666 and PRR687 could be completed between late October and mid-November 2006. - PRR676 could be implemented between mid-February and mid-March 2007. Option 2 (simultaneous implementation): - The combined project for PRR676, PRR666, and PRR687 could be completed between mid-January and mid-February 2007. |  |
| ERCOT Staffing Impacts (across all areas) |  | Short-term impacts: Package 2 (PRR676, PRR666, and PRR687): Settlement staff will perform settlement system changes to modify the Under-Scheduled Capacity Charge calculation and distribution of capacity procurement payments. Ongoing impacts: Long-term impact on current staff is expected to be minimal because the required processes will be automated. |  |
| ERCOT Computer System Impacts |  | Package 1: POS-MOS Package 2: Lodestar Package 3: Data Archive |  |
| ERCOT Business Function Impacts |  | No impact. |  |
| Grid Operations & Practices Impacts |  | No impact. |  |

Alternatives for a More Efficient Implementation (include explanation of impacts)

None

Evaluation of Interim Solutions (e.g., manual workarounds)

None

Feasibility of Implementation

Impact on Resource Availability: Nodal development staff resources may be used to develop system changes. Impact to Other Projects: Nodal market design and development may be impacted by the assignment of Nodal development resources to PRR676.

Comments

Start-date for initiating system change project is dependent on its prioritization among approved System and Market Operations projects, including the completion of projects currently in progress. “Option 1” scenario: Implementation of PRR676 would be initiated after PRR666 and PRR687 are implemented, requiring additional project testing and incurring additional overhead costs. “Option 2” scenario: Implementation of PRR676 would be initiated simultaneously with PRR666 and PRR687. Simultaneous implementation of PRR676, PRR666, and PRR687 would reduce implementation time-line, result in cost savings and create testing efficiencies. PRS voted to recommend approval of PRR687 on 8/31/06 to correct discrepancies in the Replacement Reserve Under Scheduled Capacity charge equation (PRR666). PRR687 will be implemented as part of the project implementing PRR666. PRR687 does not have an incremental cost impact on the project approved to implement PRR666.